## Summary Report
Test Case Execution
Date | 2021-01-28 | 2021-01-29 | 2021-02-01
Plan | 13 | 13 | 13
Actual | 29 | 10 | 0
Lag | 0% | 23.08% | 100%
Lead | 123.1% | 0% | 0%
Defect Life Cycle
Date | 2021-01-28 | 2021-01-29 | 2021-02-01 | Total
Defect Raised | 2 | 2 | 0 | 4
Defect Closed | 1 | 1 | 0 | 2
Defect Clarified | 0 | 0 | 0 | 0
Defect Deferred | 0 | 0 | 0 | 0
Defect Open | 1 | 1 | 0 | 2
Defect Closing Rate | 50% | 33.33% | 0% | 27.78%
Date | 2021-01-28 | 2021-01-29 | 2021-02-01
Total Defect Raised | 2 | 2 | 0
Defect by Sub Module
Sub Module Name | Defect
Manage Memo | 4
Manage Report | 0
Total | 4

## DSR Mail Body
Daily Status Report ¦Berlian Sistem Informasi ¦ CR OLSS ASSET SELLING COP PHASE 3
SIT | Planned Start Date | 2021-01-28 | RAG Status | Amber | Planned End Date | 2021-02-01
Round 1 | Actual Start Date | 2021-01-28 |  |  | Actual End Date | TBD
Status As on Date: | Days Planned | 3 |  |  | Days Elapsed | 2
2021-01-29 | Planned % | 66.67% |  |  | Actual Completion % | 100%
Highlights of the Day: 1.
Execution Summary
Status | Pass | Fail | CE-BUG | CE-PR | CE-FR + CE-NA | Total
Today Execution | 9 | 1 | 0 | 0 | 0 | 10
Total Execution | 37 | 2 | 0 | 0 | 0 | 39
Execution Summary |  |  | Defect Summary
Test Scope |  |  | Overall Defect Status
Total Planned TCs | 39 | 100% | Total Defects (Excluding Deferred) |  | 3
Deferred | 0 | 0% | Open Defects | 1 | Deferred | 0
Not Applicable | 0 | 0% | Closed Defects | 2 | Total Defect | 3
Executable TCs | 39 | 100% | Open Defects Summary
Plan Vs Actual |  |  | Severity/Status | Open with Dev | Open with SIT | Clarified
Planned | 26 | 66.67% | 1-Showstopper | 0 | 0 | 0
Actual | 39 | 100% | 2-High | 0 | 0 | 0
Lag/Lead | 13 | 33.33% | 3-Medium | 1 | 0 | 1
Breakup of Executed Test Cases |  |  | 4-Low | 0 | 0 | 0
Pass ( A ) | 37 | 94.87% | Total | 1 | 0 | 1
Fail ( B ) | 2 | 5.128% | Defects Summary (Excluding Deferred)
CE-Bug ( C ) | 0 | 0% | Severity/Status | Open | Closed | Total
Total Executed (A+B+C) | 39 | 100% | 1-Showstopper | 0 | 0 | 0
CE-PR | 0 | 0% | 2-High | 0 | 2 | 2
CE-FR | 0 | 0% | 3-Medium | 1 | 0 | 1
CE-NA | 0 | 0% | 4-Low | 0 | 0 | 0
No Run | 0 | 0% | Total | 1 | 2 | 3
Module Wise Execution Summary
Module Name | Pass | Fail | CE-BUG | CE-PR | CE-FR + CE-NA | Total
Credit Application | 0 | 0 | 0 | 0 | 0 | 0
Utility | 0 | 0 | 0 | 0 | 0 | 0
Insurance | 0 | 0 | 0 | 0 | 0 | 0
Loan Origination | 0 | 0 | 0 | 0 | 0 | 0
Account Maintenance | 0 | 0 | 0 | 0 | 0 | 0
Amendment | 0 | 0 | 0 | 0 | 0 | 0
Application Foundation | 0 | 0 | 0 | 0 | 0 | 0
Asset Document Management | 0 | 0 | 0 | 0 | 0 | 0
Change SKD | 0 | 0 | 0 | 0 | 0 | 0
Collection | 0 | 0 | 0 | 0 | 0 | 0
Credit Approval | 0 | 0 | 0 | 0 | 0 | 0
Product and Asset | 0 | 0 | 0 | 0 | 0 | 0
Report | 0 | 0 | 0 | 0 | 0 | 0
Repossession | 0 | 0 | 0 | 0 | 0 | 0
Disbursement | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0
Resource Wise Execution Summary
Name | Total Planned | Planned Till Date | Executed Till Date | Yet to be Executed | Defect Raised | Defect Closed
Rahadian | 0 | 0 | 0 | 0 | 0 | 0
Bunaya | 117 | 117 | 117 | 0 | 4 | 2
Suci | 0 | 0 | 0 | 0 | 0 | 0
Total | 117 | 117 | 117 | 0 | 4 | 2
Exit Criteria
Criteria | Test Execution | Pass Percentage | Showstopper | High | Medium and Low | Met/Not Met
Expected | 100% | 95% | 0% | 2% | 10% | Not Met
Actual | 100% | 94.87% | 0% | 0% | 33.33%
To be concern:
Test Execution Plan vs Actual |  | Notes
Planned | 66.67%
Actual | 100%
Lag/Lead | 33.33%
Execution Result Summary
Status | Pass | Fail | CE-BUG | CE-PR | CE-FR + CE-NA | Total
Today Execution | 9 | 1 | 0 | 0 | 0 | 10
Total Execution | 37 | 2 | 0 | 0 | 0 | 39
Pass Percentage | 94.87%
Notes
Defects Summary
Severity/Status | Open with Dev | Open with SIT | Open Defect Percentage
1-Showstopper | 0 | 0 | 0%
2-High | 0 | 0 | 0%
3-Medium | 1 | 0 | 33.33%
4-Low | 0 | 0
Total Open | 1 | 0
Clarified | 1
Deffered | 0
Closed+Clarified | 2
Notes
Formulas:
TBD = NETWORKDAYS.INTL(E5,[SIT, row below],1)

## Execution Plan
SR # | Complete % | Cycle | Phase | Round | Baseline Start Date | Baseline End Date | Duration (In days) | Actual Start Date | Actual End Date | Resource Names | # 0f Scenarios | # 0f Test Cases
[13 empty] | D1 | D2 | D3
[13 empty] | 2021-01-28 | 2021-01-29 | 2021-02-01
[13 empty] | Thu | Fri | Mon
1 |  | SIT | Test Execution | Round 1 | 2021-01-28 | 2021-02-01 | 3 | 2021-01-28 | TBD | SIT Team and BA | 6 | 39 | 13 | 13 | 13
2 |  | SIT | Defect Retesting | Round 1 | 2021-01-28 | 2021-02-01 | 3 | 2021-01-28 | TBD | SIT Team and BA |  |  |  | 5
[11 empty] | 6 | 39 | 13 | 13 | 13
Formulas:
Duration (In days) = IF([Baseline End Date]="",NETWORKDAYS.INTL([Baseline Start Date],TODAY(),1),NETWORKDAYS.INTL([Baseline Start Date],[Baseline End Date],1))

## Test Case Dump
Test Case ID* | Test Type* | Requirement ID | Module | Sub-Module | Application/System | Scenario ID | Scenario Description | Screen/Tab | Pre-Condition | Test Case Description | Test Data | Test Steps | Actor | Expected Result | Actual Results | Test Results | Defect Id | Iteration Number | Executed By | Execution Date (DD-MMM-YY) | Execution Remarks | Reviewed By | Reviewed Date (DD-MMM-YY) | Review Remarks | Designed By | Design Date (DD-MMM-YY)
SCN_OLSS_AS_001_TC_001 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 | To process Manage Memo for COP Transaction with condition : -- Disposal has Total Unit more than 1 -- Unit to be sold is 1 | Manage Memo Approval | 1. Admin Asset Selling should have access to OLSS | 1. To verify the successful login of Admin Asset Selling 2. To verify Admin Asset Selling has access to Manage Memo | Username : ANTONIUS FEDRIK Password : [free text] | 1. Enter the valid admin Asset Selling User ID 2. Enter valid password 3. Click on Login 4. Click on Asset Selling - Manage Memo | Admin Asset Selling | 1. System should allow Admin Asset Selling to Login into OLSS 2. System should allow Admin Asset Selling to access Manage Memo |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_002 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Disposal Selection | 1. Admin Asset Selling have permission to Create Memo 2. Disposal Number from MFAPPL is available in OLSS | 1. To verify Admin Asset Selling can select Disposal Number |  | 1. Click on Create 2. Select Memo Type : COP 3. Select Disposal Number 4. Click Continue | Admin Asset Selling | 1. System should allow Admin Asset Selling to go to Disposal Selection screen 2. System should show 3 option on Memo Type : Direct Selling, Car Ownership Program (COP), and Auction 3. System should allow Admin Asset Selling to select Memo Type Car Ownership Program (COP) 4. While Admin Asset Selling click on Disposal Number, system should show list of Disposal Number which can be proceed to Create Memo 5. System should allow Admin Asset Selling to click Continue and go to Create Memo Pengajuan - Car Ownership Program screen |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_003 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Create Memo Pengajuan - Car Ownership Program | 1. Admin Asset Selling has select Memo Type : Car Ownership Program 2. Admin Asset Selling has select Disposal Number | 1. To verify Admin Asset Selling can save and generate Memo Pengajuan |  | 1. Input Buyers Information -- Buyer Name -- Buyer Address -- To be paid 2. Click on Save and Generate 3. Click Yes on pop up confirmation | Admin Asset Selling | 1. System should show Total Asset is more than 1 and unit that can be sold is 1 also 2. System should allow Admin Asset Selling to input data Buyers Information 3. While user input field To Be Paid, system should automatically calculate field Offered Price 4. System should allow Admin Asset Selling to input Remark and click Save and Generate 5. After Admin Asset Selling click Save and Generate, system should go to Edit 5. Memo Status should be "Generate" |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_004 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Edit Memo Pengajuan - Car Ownership Program | 1. Memo Status is Generated | 1. To verify data Memo on OLSS same with data on MFAPPL |  | 1. Verify data on screen Edit Memo Pengajuan - Car Ownership Program 2. Click Edit on Table Profit Analysis | Admin Asset Selling | 1. System should show data disposal same with data on MFAPPL 2. System should show History Memo with the latest update is SAVE AND GENERATE 3. System should allow Admin Asset Selling click Edit on Table Profit Analysis 4. System should show Edit Profit Analysis screen |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_005 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Edit Profit Analysis | 1. Memo Status is Generated | 1. To verify Admin Asset Selling can Edit Profit Analysis 2. To verify OLSS will provide new calculation of expense and income for SKD Budget for Unit Sold 3. To verify Total unit will show the data of total unit sold based on data asset in memo. And detail about plat number will be provided in the screen as well. 4. To verify Profit budget in manage memo will show the calculation of profit/loss for data SKD budget for unit sold |  | 1. Verify data on screen Edit Profit Analysis 2. Change number at SKD Budget for Unit 3. Edit some of fields on Profit Analysis and validate 4. Click Save Changes | Admin Asset Selling | 1. System should allow user to Edit Profit Analysis and show Edit Profit Analysis screen 2. on the Agreement Info table, system should show Total Unit as Unit(s) to be sold and show detail about plat number 3. on the Profit Analysis table, system should provide 3 columns of table with order : SKD Budget All Unit, SKD Budget Unit Sold and Actual 4. SKD Budget All Unit should automatic generate total unit which available in SKD 5. SKD Budget Unit Sold should be generate pro rate based on how many Unit Sold 6. Actual should be generate automatically 7. System should allow user to edit each field on Table Profit Analysis 8. System should provide column of expense & income for SKD Budget unit sold 9. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Income and Column Category Income : Installment Income, Insurance Income, KTB Discount Direct to DSF and Residual Value. And Total Income can't be edited. 10. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Expanse on Column Category Expense : Product Price, Registration, Maintenance, Replacement, Insurance Cost, Mediator Fee, Mobilization, Demobilization, Interest Cost, Term of Payment and Interest Cost Before BAST. And Total Expense can't be edited. 11. For SKD Budget for Unit Sold, System should not allow user to Edit on Part of Profit on Column Category Expense : Profit. 12. For SKD Budget for Unit Sold, System should allow user to Edit Only at Part of Additional Expense on Column Category Expense ACTUAL: Additional Expense 1,2 and 3. And Total Additional Expense can't be edited. 13. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Additional Income on Column Category Income : VAT in Unit, VAT in Carroseries, VAT in Accessories, VAT in Maintenance and Field of e,f,g in Additional Income. And Total Additional Income can't be edited. 14. System should not allow to Edit Loss/Profit Actual, Gain/Loss After Sales and Net Potential (Loss/Profit). 15. While Net Potential (Loss/Profit) Actual is positive, system should show Profit with background is Blue. But if Net Potential (Loss/Profit) Actual is negative, system should show Loss with background is Red. 16. System should show selling price refer to Offered Price on Agreement Info |  | Fail | DEF_002 | 2 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_006 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Detail Memo Pengajuan - Car Ownership Program | 1. Memo Status is Generated | 1. To verify Profit budget in manage memo will show the calculation of profit/loss for data SKD budget for unit sold 2. To verify Admin Asset Selling can Submit Memo |  | 1. Go to Detail Memo Pengajuan 2. Validate Table Profit Analysis | Admin Asset Selling | 1. Profit Budget should be same with Net Potential (Loss/Profit) SKD Budget Unit Sold and Profit Estimation should be same with Net Potential (Loss/Profit) Actual. 2. While user click on Submit, status of Memo should be Submitted and need approval from Division Head 3. While Memo status is Submitted, user can't to edit Memo 4. Status Memo should be updated to Submitted, and Next Action is IRMA VERDIAN |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_007 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Detail Memo Pengajuan - Car Ownership Program | 1. Memo Status is Submitted | 1. To verify Division Head can Appprove Memo | Username : VERDIAN Password : [free text] | 1. Input Username and Password 2. Click on Asset Selling - Manage Memo 3. Click on Detail Memo Pengajuan 4. Input Remark and Click Approve | Division Head | 1. System should allow Head Office to access OLSS 2. Memo which has been Submitted should be appear in to do list Head Office 3. System should allow open and approve Detail Memo Pengajuan 4. Status Memo should be updated to Approved and Next Action is "Waiting Payment Confirmation from OLSS" |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_008 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Detail Memo Pengajuan - Car Ownership Program | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can confirm Payment Receive | Username : ANTONIUS FEDRIK Password : [free text] | 1. Input Username and Password 2. Click on Asset Selling - Manage Memo 3. Click on Detail Memo Pengajuan 4. Go to Payment Receive Tab 5. Thickmark "SOLD" on agreement number 6. Click Submit | Admin Asset Selling | 1. System should allow Admin Asset Selling to confirmation Payment Received 2. Next action should be Waiting Payment Received from MFAPPL 3. Report should be generated automatically after Admin Asset Selling confirm Payment Receive |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_009 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_001 |  | Detail Memo Pengajuan - Car Ownership Program | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can Print Report Profit Analysis |  | 1. Click on Asset Selling - Manage Memo 2. Click on Detail Memo Pengajuan 3. Go to Print Report tab 4. Click Download on Profit Analysis 5. Click Update on Profit Analysis 6. Click Save 7. Click Download on Profit Analysis 8. Verify data on Report Profit Analysis 9. Click icon Save to Excel 10. Verify data on Excel Report Profit Analysis | Admin Asset Selling | 1. System should allow Admin Asset Selling to update Approval Print Analysis on tab Print Report 2. If Admin Asset Selling click Download Report Profit Analysis without update approval, system should show validation : "Failed! Please Fill Screen Update Profit Analysis in Print Report – Update Button" 3. System should show All data in SKD Budget for unit sold (Period, Net Investment, Residual Value, and USL Month and data of expense and income) in report of Profit Analysis 4. System should allow Admin Asset Selling to print Report Profit Analysis in Excel Document |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_001_TC_010 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. |  |  | MFAPPL | SCN_OLSS_AS_001 |  |  | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can confirm Payment Receive in MFAPPL |  |  | Admin Asset Selling | 1. After payment receive has confirmed from MFAPPL, Next action in OLSS System should be update Waiting Report Approval Progress |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_002_TC_001 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_002 | To process Manage Report for COP Transaction with condition : -- Disposal has Total Unit more than 1 -- Unit to be sold is 1 Continued SCN_OLSS_AS_001 | Manage Report Approval | 1. Status Report is Created | 1. To verify Admin Asset Selling can Check Report | Username : ANTONIUS FEDRIK Password : [free text] | 1. Click on Asset Selling - Manage Report 2. Click on Detail Pengajuan Memo 3. Click Check | Admin Asset Selling | 1. While payment received has been confirmed in MFAPPL, system should allow Admin Asset Selling to Checked Memo 2. After Admin Asset Selling Checked Memo, status Memo should be updated to Checked |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_002_TC_002 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_002 |  | Manage Report Approval | 1. Status Report is Created | 1. To verify Admin Asset Selling can Print Report Lampiran Hasil Investasi |  | 1. Click on Asset Selling - Manage Report 2. Click on Detail Memo Pengajuan 3. Click Download on Lampiran Hasil Investasi 4. Verify data on Report Lampiran Hasil Investasi 5. Click icon Save to Excel 6. Verify data on Excel Report Lampiran Hasil Investasi | Admin Asset Selling | 1. System should allow Admin Asset Selling to update Approval Print Analysis on tab Print Report 2. System should show All data in SKD Budget for unit sold (Period, Net Investment, Residual Value, and USL Month and data of expense and income) in report of Lampiran Hasil Investasi 3. System should allow Admin Asset Selling to print Report Lampiran Hassil Investasi in Excel Document |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_002_TC_003 | SIT | IT-CFR-200420-855 Asset Selling COP #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_002 |  | Manage Report Approval | 1. Status Report is Checked | 1. To verify Division Head can Sign Report | Username : VERDIAN Password : [free text] | 1. Click on Asset Selling - Manage Report 2. Click on Detail Pengajuan Memo 3. Click Sign | Division Head | 1. System should allow Division Head Sign Report 2. Status Memo should be Signed |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_001 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 | To process Manage Memo for Direct Selling Transaction with condition : -- Disposal has Total Unit is 1 -- Unit to be sold is 1 | Manage Memo Approval | 1. Admin Asset Selling should have access to OLSS | 1. To verify the successful login of Admin Asset Selling 2. To verify Admin Asset Selling has access to Manage Memo | Username : ANTONIUS FEDRIK Password : [free text] | 1. Enter the valid admin Asset Selling User ID 2. Enter valid password 3. Click on Login 4. Click on Asset Selling - Manage Memo | Admin Asset Selling | 1. System should allow Admin Asset Selling to Login into OLSS 2. System should allow Admin Asset Selling to access Manage Memo |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_002 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Disposal Selection | 1. Admin Asset Selling have permission to Create Memo 2. Disposal Number from MFAPPL is available in OLSS | 1. To verify Admin Asset Selling can select Disposal Number |  | 1. Click on Create 2. Select Memo Type : Direct Selling 3. Select Disposal Number 4. Click Continue | Admin Asset Selling | 1. System should allow Admin Asset Selling to go to Disposal Selection screen 2. System should show 3 option on Memo Type : Direct Selling, Car Ownership Program (COP), and Auction 3. System should allow Admin Asset Selling to select Memo Type Direct Selling 4. While Admin Asset Selling click on Disposal Number, system should show list of Disposal Number which can be proceed to Create Memo 5. System should allow Admin Asset Selling to click Continue and go to Create Memo Pengajuan - Direct Selling screen |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_003 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Create Memo Pengajuan - Direct Selling | 1. Admin Asset Selling has select Memo Type : Direct Selling 2. Admin Asset Selling has select Disposal Number | 1. To verify Admin Asset Selling can save and generate Memo Pengajuan |  | 1. Input Buyers Information -- Buyer Name -- Buyer Address -- To be paid 2. Click on Save and Generate 3. Click Yes on pop up confirmation | Admin Asset Selling | 1. System should show Total Asset is 1 and unit that can be sold is 1 also 2. System should allow Admin Asset Selling to input data Buyers Information 3. While user input field To Be Paid, system should automatically calculate field Offered Price 4. System should allow Admin Asset Selling to input Remark and click Save and Generate 5. After Admin Asset Selling click Save and Generate, system should go to Edit 5. Memo Status should be "Generate" |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_004 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Edit Memo Pengajuan - Direct Selling | 1. Memo Status is Generated | 1. To verify data Memo on OLSS same with data on MFAPPL |  | 1. Verify data on screen Edit Memo Pengajuan - Direct Selling 2. Click Edit on Table Profit Analysis | Admin Asset Selling | 1. System should show data disposal same with data on MFAPPL 2. System should show History Memo with the latest update is SAVE AND GENERATE 3. System should allow Admin Asset Selling click Edit on Table Profit Analysis 4. System should show Edit Profit Analysis screen |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_005 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Edit Profit Analysis | 1. Memo Status is Generated | 1. To verify Admin Asset Selling can Edit Profit Analysis 2. To verify OLSS will provide new calculation of expense and income for SKD Budget for Unit Sold 3. To verify Total unit will show the data of total unit sold based on data asset in memo. And detail about plat number will be provided in the screen as well. 4. To verify Profit budget in manage memo will show the calculation of profit/loss for data SKD budget for unit sold |  | 1. Verify data on screen Edit Profit Analysis 2. Change number at SKD Budget for Unit 3. Edit some of fields on Profit Analysis and validate 4. Click Save Changes | Admin Asset Selling | 1. System should allow user to Edit Profit Analysis and show Edit Profit Analysis screen 2. on the Agreement Info table, system should show Total Unit as Unit(s) to be sold and show detail about plat number 3. on the Profit Analysis table, system should provide 3 columns of table with order : SKD Budget All Unit, SKD Budget Unit Sold and Actual 4. SKD Budget All Unit should automatic generate total unit which available in SKD 5. SKD Budget Unit Sold should be generate pro rate based on how many Unit Sold 6. Actual should be generate automatically 7. System should allow user to edit each field on Table Profit Analysis 8. System should provide column of expense & income for SKD Budget unit sold 9. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Income and Column Category Income : Installment Income, Insurance Income, KTB Discount Direct to DSF and Residual Value. And Total Income can't be edited. 10. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Expanse on Column Category Expense : Product Price, Registration, Maintenance, Replacement, Insurance Cost, Mediator Fee, Mobilization, Demobilization, Interest Cost, Term of Payment and Interest Cost Before BAST. And Total Expense can't be edited. 11. For SKD Budget for Unit Sold, System should not allow user to Edit on Part of Profit on Column Category Expense : Profit. 12. For SKD Budget for Unit Sold, System should allow user to Edit Only at Part of Additional Expense on Column Category Expense ACTUAL: Additional Expense 1,2 and 3. And Total Additional Expense can't be edited. 13. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Additional Income on Column Category Income : VAT in Unit, VAT in Carroseries, VAT in Accessories, VAT in Maintenance and Field of e,f,g in Additional Income. And Total Additional Income can't be edited. 14. System should not allow to Edit Loss/Profit Actual, Gain/Loss After Sales and Net Potential (Loss/Profit). 15. While Net Potential (Loss/Profit) Actual is positive, system should show Profit with background is Blue. But if Net Potential (Loss/Profit) Actual is negative, system should show Loss with background is Red. 16. System should show selling price refer to Offered Price on Agreement Info |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_006 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Detail Memo Pengajuan - Direct Selling | 1. Memo Status is Generated | 1. To verify Profit budget in manage memo will show the calculation of profit/loss for data SKD budget for unit sold 2. To verify Admin Asset Selling can Submit Memo |  | 1. Go to Detail Memo Pengajuan 2. Validate Table Profit Analysis | Admin Asset Selling | 1. Profit Budget should be same with Net Potential (Loss/Profit) SKD Budget Unit Sold and Profit Estimation should be same with Net Potential (Loss/Profit) Actual. 2. While user click on Submit, status of Memo should be Submitted and need approval from Division Head 3. While Memo status is Submitted, user can't to edit Memo 4. Status Memo should be updated to Submitted, and Next Action is IRMA VERDIAN |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_007 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Detail Memo Pengajuan - Direct Selling | 1. Memo Status is Submitted | 1. To verify Division Head can Appprove Memo | Username : VERDIAN Password : [free text] | 1. Input Username and Password 2. Click on Asset Selling - Manage Memo 3. Click on Detail Memo Pengajuan 4. Input Remark and Click Approve | Division Head | 1. System should allow Head Office to access OLSS 2. Memo which has been Submitted should be appear in to do list Head Office 3. System should allow open and approve Detail Memo Pengajuan 4. Status Memo should be updated to Approved and Next Action is "Waiting Payment Confirmation from OLSS" |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_008 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Detail Memo Pengajuan - Direct Selling | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can confirm Payment Receive | Username : ANTONIUS FEDRIK Password : [free text] | 1. Input Username and Password 2. Click on Asset Selling - Manage Memo 3. Click on Detail Memo Pengajuan 4. Go to Payment Receive Tab 5. Thickmark "SOLD" on agreement number 6. Click Submit | Admin Asset Selling | 1. System should allow Admin Asset Selling to confirmation Payment Received 2. Next action should be Waiting Payment Received from MFAPPL 3. Report should be generated automatically after Admin Asset Selling confirm Payment Receive | System allow user to click Submit Payment Receive in many times | Fail | DEF_004 | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_009 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_003 |  | Detail Memo Pengajuan - Direct Selling | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can Print Report Profit Analysis |  | 1. Click on Asset Selling - Manage Memo 2. Click on Detail Memo Pengajuan 3. Go to Print Report tab 4. Click Download on Profit Analysis 5. Click Update on Profit Analysis 6. Click Save 7. Click Download on Profit Analysis 8. Verify data on Report Profit Analysis 9. Click icon Save to Excel 10. Verify data on Excel Report Profit Analysis | Admin Asset Selling | 1. System should allow Admin Asset Selling to update Approval Print Analysis on tab Print Report 2. If Admin Asset Selling click Download Report Profit Analysis without update approval, system should show validation : "Failed! Please Fill Screen Update Profit Analysis in Print Report – Update Button" 3. System should show All data in SKD Budget for unit sold (Period, Net Investment, Residual Value, and USL Month and data of expense and income) in report of Profit Analysis 4. System should allow Admin Asset Selling to print Report Profit Analysis in Excel Document |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_003_TC_010 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. |  |  | MFAPPL | SCN_OLSS_AS_003 |  |  | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can confirm Payment Receive in MFAPPL |  |  | Admin Asset Selling | 1. After payment receive has confirmed from MFAPPL, Next action in OLSS System should be update Waiting Report Approval Progress |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_004_TC_001 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_004 | To process Manage Report for Direct Selling Transaction with condition : -- Disposal has Total Unit is 1 -- Unit to be sold is 1 Continued SCN_OLSS_AS_003 | Manage Report Approval | 1. Status Report is Created | 1. To verify Admin Asset Selling can Check Report | Username : ANTONIUS FEDRIK Password : [free text] | 1. Click on Asset Selling - Manage Report 2. Click on Detail Pengajuan Memo 3. Click Check | Admin Asset Selling | 1. While payment received has been confirmed in MFAPPL, system should allow Admin Asset Selling to Checked Memo 2. After Admin Asset Selling Checked Memo, status Memo should be updated to Checked |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_004_TC_002 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_004 |  | Manage Report Approval | 1. Status Report is Created | 1. To verify Admin Asset Selling can Print Report Lampiran Hasil Investasi |  | 1. Click on Asset Selling - Manage Report 2. Click on Detail Memo Pengajuan 3. Click Download on Lampiran Hasil Investasi 4. Verify data on Report Lampiran Hasil Investasi 5. Click icon Save to Excel 6. Verify data on Excel Report Lampiran Hasil Investasi | Admin Asset Selling | 1. System should allow Admin Asset Selling to update Approval Print Analysis on tab Print Report 2. System should show All data in SKD Budget for unit sold (Period, Net Investment, Residual Value, and USL Month and data of expense and income) in report of Lampiran Hasil Investasi 3. System should allow Admin Asset Selling to print Report Lampiran Hassil Investasi in Excel Document |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_004_TC_003 | SIT | IT-CFR-200420-855 Asset Selling Direct Selling #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_004 |  | Manage Report Approval | 1. Status Report is Checked | 1. To verify Division Head can Sign Report | Username : VERDIAN Password : [free text] | 1. Click on Asset Selling - Manage Report 2. Click on Detail Pengajuan Memo 3. Click Sign | Division Head | 1. System should allow Division Head Sign Report 2. Status Memo should be Signed |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_001 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 | To process Manage Memo for Auction Transaction with condition : -- Disposal has Total Unit more than 1 -- Unit to be sold is 2 | Manage Memo Approval | 1. Admin Asset Selling should have access to OLSS | 1. To verify the successful login of Admin Asset Selling 2. To verify Admin Asset Selling has access to Manage Memo | Username : ANTONIUS FEDRIK Password : [free text] | 1. Enter the valid admin Asset Selling User ID 2. Enter valid password 3. Click on Login 4. Click on Asset Selling - Manage Memo | Admin Asset Selling | 1. System should allow Admin Asset Selling to Login into OLSS 2. System should allow Admin Asset Selling to access Manage Memo |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_002 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Disposal Selection | 1. Admin Asset Selling have permission to Create Memo 2. Disposal Number from MFAPPL is available in OLSS | 1. To verify Admin Asset Selling can select Disposal Number |  | 1. Click on Create 2. Select Memo Type : Auction 3. Select Disposal Number 4. Click Continue | Admin Asset Selling | 1. System should allow Admin Asset Selling to go to Disposal Selection screen 2. System should show 3 option on Memo Type : Direct Selling, Car Ownership Program (COP), and Auction 3. System should allow Admin Asset Selling to select Memo Type Auction 4. While Admin Asset Selling click on Disposal Number, system should show list of Disposal Number which can be proceed to Create Memo 5. System should allow Admin Asset Selling to click Continue and go to Create Memo Pengajuan - Auction screen |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_003 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Create Memo Pengajuan - Auction | 1. Admin Asset Selling has select Memo Type : Auction 2. Admin Asset Selling has select Disposal Number | 1. To verify Admin Asset Selling can save and generate Memo Pengajuan |  | 1. Input Buyers Information -- Buyer Name -- Buyer Address -- To be paid 2. Click on Save and Generate 3. Click Yes on pop up confirmation | Admin Asset Selling | 1. System should show Total Asset is 1 and unit that can be sold is 1 also 2. System should allow Admin Asset Selling to input data Buyers Information 3. While user input field To Be Paid, system should automatically calculate field Offered Price 4. System should allow Admin Asset Selling to input Remark and click Save and Generate 5. After Admin Asset Selling click Save and Generate, system should go to Edit 5. Memo Status should be "Generate" |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_004 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Edit Memo Pengajuan - Auction | 1. Memo Status is Generated | 1. To verify data Memo on OLSS same with data on MFAPPL |  | 1. Verify data on screen Edit Memo Pengajuan - Auction 2. Click Edit on Table Profit Analysis | Admin Asset Selling | 1. System should show data disposal same with data on MFAPPL 2. System should show History Memo with the latest update is SAVE AND GENERATE 3. System should allow Admin Asset Selling click Edit on Table Profit Analysis 4. System should show Edit Profit Analysis screen |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_005 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Edit Profit Analysis | 1. Memo Status is Generated | 1. To verify Admin Asset Selling can Edit Profit Analysis 2. To verify OLSS will provide new calculation of expense and income for SKD Budget for Unit Sold 3. To verify Total unit will show the data of total unit sold based on data asset in memo. And detail about plat number will be provided in the screen as well. 4. To verify Profit budget in manage memo will show the calculation of profit/loss for data SKD budget for unit sold |  | 1. Verify data on screen Edit Profit Analysis 2. Change number at SKD Budget for Unit 3. Edit some of fields on Profit Analysis and validate 4. Click Save Changes | Admin Asset Selling | 1. System should allow user to Edit Profit Analysis and show Edit Profit Analysis screen 2. on the Agreement Info table, system should show Total Unit as Unit(s) to be sold and show detail about plat number 3. on the Profit Analysis table, system should provide 3 columns of table with order : SKD Budget All Unit, SKD Budget Unit Sold and Actual 4. SKD Budget All Unit should automatic generate total unit which available in SKD 5. SKD Budget Unit Sold should be generate pro rate based on how many Unit Sold 6. Actual should be generate automatically 7. System should allow user to edit each field on Table Profit Analysis 8. System should provide column of expense & income for SKD Budget unit sold 9. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Income and Column Category Income : Installment Income, Insurance Income, KTB Discount Direct to DSF and Residual Value. And Total Income can't be edited. 10. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Expanse on Column Category Expense : Product Price, Registration, Maintenance, Replacement, Insurance Cost, Mediator Fee, Mobilization, Demobilization, Interest Cost, Term of Payment and Interest Cost Before BAST. And Total Expense can't be edited. 11. For SKD Budget for Unit Sold, System should not allow user to Edit on Part of Profit on Column Category Expense : Profit. 12. For SKD Budget for Unit Sold, System should allow user to Edit Only at Part of Additional Expense on Column Category Expense ACTUAL: Additional Expense 1,2 and 3. And Total Additional Expense can't be edited. 13. For SKD Budget for Unit Sold, System should allow user to Edit on Part of Additional Income on Column Category Income : VAT in Unit, VAT in Carroseries, VAT in Accessories, VAT in Maintenance and Field of e,f,g in Additional Income. And Total Additional Income can't be edited. 14. System should not allow to Edit Loss/Profit Actual, Gain/Loss After Sales and Net Potential (Loss/Profit). 15. While Net Potential (Loss/Profit) Actual is positive, system should show Profit with background is Blue. But if Net Potential (Loss/Profit) Actual is negative, system should show Loss with background is Red. 16. System should show selling price refer to Offered Price on Agreement Info |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_006 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Detail Memo Pengajuan - Auction | 1. Memo Status is Generated | 1. To verify Profit budget in manage memo will show the calculation of profit/loss for data SKD budget for unit sold 2. To verify Admin Asset Selling can Submit Memo |  | 1. Go to Detail Memo Pengajuan 2. Validate Table Profit Analysis | Admin Asset Selling | 1. Profit Budget should be same with Net Potential (Loss/Profit) SKD Budget Unit Sold and Profit Estimation should be same with Net Potential (Loss/Profit) Actual. 2. While user click on Submit, status of Memo should be Submitted and need approval from Division Head 3. While Memo status is Submitted, user can't to edit Memo 4. Status Memo should be updated to Submitted, and Next Action is IRMA VERDIAN |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_007 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Detail Memo Pengajuan - Auction | 1. Memo Status is Submitted | 1. To verify Division Head can Appprove Memo | Username : VERDIAN Password : [free text] | 1. Input Username and Password 2. Click on Asset Selling - Manage Memo 3. Click on Detail Memo Pengajuan 4. Input Remark and Click Approve | Division Head | 1. System should allow Head Office to access OLSS 2. Memo which has been Submitted should be appear in to do list Head Office 3. System should allow open and approve Detail Memo Pengajuan 4. Status Memo should be updated to Approved and Next Action is "Waiting Payment Confirmation from OLSS" |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_008 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Detail Memo Pengajuan - Auction | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can confirm Payment Receive | Username : ANTONIUS FEDRIK Password : [free text] | 1. Input Username and Password 2. Click on Asset Selling - Manage Memo 3. Click on Detail Memo Pengajuan 4. Go to Payment Receive Tab 5. Thickmark "SOLD" on agreement number 6. Click Submit | Admin Asset Selling | 1. System should allow user to check Sold or Unsold on Asset List and click on Submit. 2. Next action should be Waiting Payment Received from MFAPPL 3. Report should be generated automatically after Admin Asset Selling confirm Payment Receive |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_009 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Memo | OLSS | SCN_OLSS_AS_005 |  | Detail Memo Pengajuan - Auction | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can Print Report Profit Analysis |  | 1. Click on Asset Selling - Manage Memo 2. Click on Detail Memo Pengajuan 3. Go to Print Report tab 4. Click Download on Profit Analysis 5. Click Update on Profit Analysis 6. Click Save 7. Click Download on Profit Analysis 8. Verify data on Report Profit Analysis 9. Click icon Save to Excel 10. Verify data on Excel Report Profit Analysis | Admin Asset Selling | 1. System should allow Admin Asset Selling to update Approval Print Analysis on tab Print Report 2. If Admin Asset Selling click Download Report Profit Analysis without update approval, system should show validation : "Failed! Please Fill Screen Update Profit Analysis in Print Report – Update Button" 3. System should show All data in SKD Budget for unit sold (Period, Net Investment, Residual Value, and USL Month and data of expense and income) in report of Profit Analysis 4. System should allow Admin Asset Selling to print Report Profit Analysis in Excel Document |  | Pass |  | 1 | Bunaya | 2021-01-29 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_005_TC_010 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. |  |  | MFAPPL | SCN_OLSS_AS_005 |  |  | 1. Memo Status is Approved | 1. To verify Admin Asset Selling can confirm Payment Receive in MFAPPL |  |  | Admin Asset Selling | 1. After payment receive has confirmed from MFAPPL, Next action in OLSS System should be update Waiting Report Approval Progress |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_006_TC_001 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_006 | To process Manage Report for Auction Transaction with condition : -- Disposal has Total Unit more than 1 -- Unit to be sold is 2 Continued SCN_OLSS_AS_005 | Manage Report Approval | 1. Status Report is Created | 1. To verify Admin Asset Selling can Check Report | Username : ANTONIUS FEDRIK Password : [free text] | 1. Click on Asset Selling - Manage Report 2. Click on Detail Pengajuan Memo 3. Click Check | Admin Asset Selling | 1. While user has click on Submit on Payment Receive, next action data Memo should appear in screen of Index Report Approval from Create Manage Report. 2. While payment received has been confirmed in MFAPPL, system should allow Admin Asset Selling to Checked Memo 3. After Admin Asset Selling Checked Memo, status Memo should be updated to Checked |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_006_TC_002 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_006 |  | Manage Report Approval | 1. Status Report is Created | 1. To verify Admin Asset Selling can Print Report Lampiran Hasil Investasi |  | 1. Click on Asset Selling - Manage Report 2. Click on Detail Memo Pengajuan 3. Click Download on Lampiran Hasil Investasi 4. Verify data on Report Lampiran Hasil Investasi 5. Click icon Save to Excel 6. Verify data on Excel Report Lampiran Hasil Investasi | Admin Asset Selling | 1. System should allow Admin Asset Selling to update Approval Print Analysis on tab Print Report 2. System should show All data in SKD Budget for unit sold (Period, Net Investment, Residual Value, and USL Month and data of expense and income) in report of Lampiran Hasil Investasi 3. System should allow Admin Asset Selling to print Report Lampiran Hassil Investasi in Excel Document |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27
SCN_OLSS_AS_006_TC_003 | SIT | IT-CFR-200420-855 Asset Selling Auction #46850. | Asset Selling | Manage Report | OLSS | SCN_OLSS_AS_006 |  | Manage Report Approval | 1. Status Report is Checked | 1. To verify Division Head can Sign Report | Username : VERDIAN Password : [free text] | 1. Click on Asset Selling - Manage Report 2. Click on Detail Pengajuan Memo 3. Click Sign | Division Head | 1. System should allow Division Head Sign Report 2. Status Memo should be Signed |  | Pass |  | 1 | Bunaya | 2021-01-28 |  |  |  |  | Bunaya | 2021-01-27

## Execution Summary
Execution Summary¦Berlian Sistem Informasi ¦ CR OLSS ASSET SELLING PHASE 3 |  |  |  |  | 2021-01-29
Test Execution Summary \ Type | SIT
| Total Execution | Today's Execution
Total Planned | 39 | 13
Removed during Execution | 0 | 0
CE-NA | 0 | 0
CE-FR | 0 | 0
Executable | 39 | 13
Not Executable due to Pre-requisite | 0 | 0
Total Executed (Actual) | 39 | 10
Pass | 37 | 9
Fail | 2 | 1
CE-Bug | 0 | 0
Balance Execution | 0 | 3
% Pass | 94.87% | 90%
% Fail | 5.128% | 10%
% Completion | 100% | 76.92%
Total Defects Raised | 3
Total System Downtime (In Hrs) | 0:00
Detail Execution Summary: Project Name
Module | All | Credit Application | Disbursement | Insurance | Loan Origination
Total Planned | 0 | 0 | 0 | 0 | 0
Removed during Execution | 0 | 0 | 0 | 0 | 0
CE-NA | 0 | 0 | 0 | 0 | 0
CE-FR | 0 | 0 | 0 | 0 | 0
Executable | 0 | 0 | 0 | 0 | 0
Not Executable due to Pre-requisite | 0 | 0 | 0 | 0 | 0
Total Executed (Actual) | 0 | 0 | 0 | 0 | 0
Pass | 0 | 0 | 0 | 0 | 0
Fail | 0 | 0 | 0 | 0 | 0
CE-Bug | 0 | 0 | 0 | 0 | 0
Balance Execution | 0 | 0 | 0 | 0 | 0
% Pass | 0% | 0% | 0% | 0% | 0%
% Fail | 0% | 0% | 0% | 0% | 0%
% Completion | 0% | 0% | 0% | 0% | 0%
Module | All | Credit Application | Disbursement | Insurance | Loan Origination
Total Defects | 0 | 0 | 0 | 0 | 0
New | 0 | 0 | 0 | 0 | 0
Resend | 0 | 0 | 0 | 0 | 0
Duplicate | 0 | 0 | 0 | 0 | 0
Assign to BSI Dev | 0 | 0 | 0 | 0 | 0
In-Progress BSI Dev | 0 | 0 | 0 | 0 | 0
Assign to COFINS Dev | 0 | 0 | 0 | 0 | 0
In-Progress CONFINS Dev | 0 | 0 | 0 | 0 | 0
Clarification | 0 | 0 | 0 | 0 | 0
Deferred | 0 | 0 | 0 | 0 | 0
SIT Ready | 0 | 0 | 0 | 0 | 0
SIT Reopen | 0 | 0 | 0 | 0 | 0
UAT Ready | 0 | 0 | 0 | 0 | 0
UAT Reopen | 0 | 0 | 0 | 0 | 0
Closed | 0 | 0 | 0 | 0 | 0

## Downtime Tracker (hidden)
Date | Day | DipoLink | ACA | CONFINS
2019-12-24 | Tue | 0:00 | 0:00 | 0:00
2019-12-26 | Thu | 0:00 | 0:00 | 0:00
2019-12-27 | Fri | 0:00 | 0:00 | 0:00
2019-12-30 | Mon | 0:00 | 0:00 | 0:00
2020-01-02 | Thu | 0:00 | 0:00 | 0:00
2020-01-03 | Fri | 0:00 | 0:00 | 0:00
|  | 0 | 0 | 0
Formulas:
DipoLink = SUM(C2:[DipoLink, row above])
ACA = SUM(D2:[ACA, row above])
CONFINS = SUM(E2:[CONFINS, row above])
Note on C2: bsilending001: Manual
Note on D2: bsilending001: Manual
Note on E2: bsilending001: Manual
Note on C3: bsilending001: Manual
Note on D3: bsilending001: Manual
Note on E3: bsilending001: Manual
Note on C4: bsilending001: Manual
Note on D4: bsilending001: Manual
Note on E4: bsilending001: Manual
Note on C5: bsilending001: Manual
Note on D5: bsilending001: Manual
Note on E5: bsilending001: Manual
Note on C6: bsilending001: Manual
Note on D6: bsilending001: Manual
Note on E6: bsilending001: Manual
Note on C7: bsilending001: Manual
Note on D7: bsilending001: Manual
Note on E7: bsilending001: Manual

## Defect Dump
Project ID/CR Number | Defect ID | Test Case ID | Defect Type | Module | Sub-Module | Defect Summary | Defect Description | Clarification Notes | Phase | Round | Application Name | Status | Severity | Priority | Defect Category | Defect RCA | Reported By | Reported On | Assigned To | Updated On | Closed By | Closure Date | Expected Defect Resolution Date | Actual Release date | Defect Aging
IT-CFR-200420-855 Asset Selling COP #46850. | DEF_001 | SCN_OLSS_AS_001_TC_005 | Defect | Asset Selling | Manage Memo | System show number at SKD Budget for Unit same with total assets on SKD | Reproduce : 1. Verify data on screen Edit Profit Analysis Actual result : 1. System show number at SKD Budget for Unit same with total assets on SKD Expected result : 1. System should show number at SKD Budget for Unit same with total asset sold |  | SIT |  | OLSS | Closed | High | High | Development Issue |  | Bunaya | 2021-01-28 | Agung |  | Bunaya | 2021-01-28
IT-CFR-200420-855 Asset Selling COP #46850. | DEF_002 | SCN_OLSS_AS_001_TC_005 | Defect | Asset Selling | Manage Memo | Some of fields in SKD Budget for Unit still empty, while user input on SKD Budget Total Unit | Reproduce : 1. Verify data on screen Edit Profit Analysis 2. Edit field Insurance Income, KTB Discount Direct to DSF and Residual Value SKD Budget Total Unit Actual result : 1. Some of fields in SKD Budget for Unit still empty Expected result : 1. Insurance Income, KTB Discount Direct to DSF and Residual Value, Product Price, Registration, Maintenance, Replacement, Insurance Cost, Mediator Fee, Mobilization, Demobilization, Interest Cost, etc in SKD Budget for Unit should Auto Calculated pro rate (by unit quantity) based on insurance income for SKD Budget all total unit and quantity of units sold. | OLSS need to generate automatically pro-rate as well once user input or modify data in SKD Budget All Total Unit to decrease the effort for user to input data in SKD Budget Unit Sold. | SIT |  | OLSS | Closed | High | High |  |  | Bunaya | 2021-01-28 | Agung |  | Bunaya | 2021-01-29
IT-CFR-200420-855 Asset Selling COP #46850. | DEF_003 | SCN_OLSS_AS_001_TC_005 | Defect | Asset Selling | Manage Memo | System allow user save Edit Profit Analysis with negative value | Reproduce : 1. Click on Edit Profit Analysis 2. Input negative value on all fields 3. Click Save Actual result : 1. System allow user save Edit Profit Analysis with negative value Expected result : 1. System should show error validation if user input negative value |  | SIT |  | OLSS | Assign to BSI Dev | Medium | Medium |  |  | Bunaya | 2021-01-29 | Agung
IT-CFR-200420-855 Asset Selling COP #46850. | DEF_004 | SCN_OLSS_AS_003_TC_008 | Clarification | Asset Selling | Manage Memo | System allow user to click Submit Payment Receive in many times | Reproduce : 1. Click on Detail Profit Analysis 2. Click Payment Receive tab 3. Thickmark Sold on all agreement 4. Click Submit 5. Click Submit Again 6. Click Submit Again Actual result : 1. System allow user to click Submit Payment Receive in many times 2. System show in History that user has Submit Payment Receive in 3 times Expected result : 1. System should not allow to click Submit after all agreement has been Submit Payment Confirmation |  | SIT |  | OLSS | Clarification | Medium | Medium |  |  | Bunaya | 2021-01-29 | Rayang

## Defect Summary
Overall Defect Summary | [6 empty] | Overall Defect Ageing | [5 empty] | Defect Resolution
Status | Responsible Team | Showstopper | High | Medium | Low | Total | Days | Showstopper | High | Medium | Low | Total | Status | Showstopper | High | Medium | Low | Total
New | QA Manager/BA | 0 | 0 | 0 | 0 | 0 | 0-5 | 0 | 0 | 0 | 0 | 0 | Development Issue | 0 | 1 | 0 | 0 | 1
Resend | SIT/UAT Tester | 0 | 0 | 0 | 0 | 0 | 6-10 | 0 | 0 | 0 | 0 | 0 | Deployment Issue | 0 | 0 | 0 | 0 | 0
Duplicate | SIT/UAT Tester | 0 | 0 | 0 | 0 | 0 | 11-15 | 0 | 0 | 0 | 0 | 0 | Infrastructure Issue | 0 | 0 | 0 | 0 | 0
Assign to BSI Dev | BSI Developer | 0 | 0 | 1 | 0 | 1 | 16-20 | 0 | 0 | 0 | 0 | 0 | GAP in BRD | 0 | 0 | 0 | 0 | 0
In-Progress BSI Dev | BSI Developer | 0 | 0 | 0 | 0 | 0 | >20 | 0 | 0 | 0 | 0 | 0 | GAP in FSD | 0 | 0 | 0 | 0 | 0
Assign to COFINS Dev | CONFINS Developer | 0 | 0 | 0 | 0 | 0 | Total | 0 | 0 | 0 | 0 | 0 | Clarification | 0 | 0 | 0 | 0 | 0
In-Progress CONFINS Dev | CONFINS Developer | 0 | 0 | 0 | 0 | 0 | [6 empty] | Duplicate | 0 | 0 | 0 | 0 | 0
Clarification | SIT/UAT Tester | 0 | 0 | 1 | 0 | 1 | Overall Defect Ageing - Open Defects | [5 empty] | Data Issue | 0 | 0 | 0 | 0 | 0
Deferred | QA Manager/BA | 0 | 0 | 0 | 0 | 0 | Days | Showstopper | High | Medium | Low | Total | Not Classified | 0 | 0 | 0 | 0 | 0
SIT Ready | SIT Tester | 0 | 0 | 0 | 0 | 0 | 0-5 | 0 | 0 | 0 | 0 | 0 | Total | 0 | 1 | 0 | 0 | 1
SIT Reopen | BSI Developer | 0 | 0 | 0 | 0 | 0 | 6-10 | 0 | 0 | 0 | 0 | 0
UAT Ready | UAT Tester | 0 | 0 | 0 | 0 | 0 | 11-15 | 0 | 0 | 0 | 0 | 0
UAT Reopen | BSI Developer | 0 | 0 | 0 | 0 | 0 | 16-20 | 0 | 0 | 0 | 0 | 0
Closed | - | 0 | 2 | 0 | 0 | 2 | >20 | 0 | 0 | 0 | 0 | 0
Total | - | 0 | 2 | 2 | 0 | 4 | Total | 0 | 0 | 0 | 0 | 0
Defect Retesting
Defect ID | Status | Fail | CE-Bug | Total
DEF_001 | OLSS | 0 | 0 | 0
DEF_002 | OLSS | 0 | 0 | 0
DEF_003 | OLSS | 0 | 0 | 0
DEF_004 | OLSS | 0 | 0 | 0
DEF_005 | #N/A | 0 | 0 | 0
DEF_006 | #N/A | 0 | 0 | 0
DEF_007 | #N/A | 0 | 0 | 0
DEF_008 | #N/A | 0 | 0 | 0
DEF_009 | #N/A | 0 | 0 | 0
DEF_010 | #N/A | 0 | 0 | 0
DEF_011 | #N/A | 0 | 0 | 0
DEF_012 | #N/A | 0 | 0 | 0
DEF_013 | #N/A | 0 | 0 | 0
DEF_014 | #N/A | 0 | 0 | 0
DEF_015 | #N/A | 0 | 0 | 0
DEF_016 | #N/A | 0 | 0 | 0
DEF_017 | #N/A | 0 | 0 | 0
DEF_018 | #N/A | 0 | 0 | 0
DEF_019 | #N/A | 0 | 0 | 0
DEF_020 | #N/A | 0 | 0 | 0
DEF_021 | #N/A | 0 | 0 | 0
DEF_022 | #N/A | 0 | 0 | 0
DEF_023 | #N/A | 0 | 0 | 0
DEF_024 | #N/A | 0 | 0 | 0
DEF_025 | #N/A | 0 | 0 | 0
DEF_026 | #N/A | 0 | 0 | 0
DEF_027 | #N/A | 0 | 0 | 0
DEF_028 | #N/A | 0 | 0 | 0
DEF_029 | #N/A | 0 | 0 | 0
DEF_030 | #N/A | 0 | 0 | 0
DEF_031 | #N/A | 0 | 0 | 0
DEF_032 | #N/A | 0 | 0 | 0
DEF_033 | #N/A | 0 | 0 | 0
DEF_034 | #N/A | 0 | 0 | 0
DEF_035 | #N/A | 0 | 0 | 0
DEF_036 | #N/A | 0 | 0 | 0
DEF_037 | #N/A | 0 | 0 | 0
DEF_038 | #N/A | 0 | 0 | 0
DEF_039 | #N/A | 0 | 0 | 0
DEF_040 | #N/A | 0 | 0 | 0
DEF_041 | #N/A | 0 | 0 | 0
DEF_042 | #N/A | 0 | 0 | 0
DEF_043 | #N/A | 0 | 0 | 0
DEF_044 | #N/A | 0 | 0 | 0
DEF_045 | #N/A | 0 | 0 | 0
DEF_046 | #N/A | 0 | 0 | 0
DEF_047 | #N/A | 0 | 0 | 0
DEF_048 | #N/A | 0 | 0 | 0
DEF_049 | #N/A | 0 | 0 | 0
DEF_050 | #N/A | 0 | 0 | 0
DEF_051 | #N/A | 0 | 0 | 0
DEF_052 | #N/A | 0 | 0 | 0
DEF_053 | #N/A | 0 | 0 | 0
DEF_054 | #N/A | 0 | 0 | 0
DEF_055 | #N/A | 0 | 0 | 0
DEF_056 | #N/A | 0 | 0 | 0
DEF_057 | #N/A | 0 | 0 | 0
DEF_058 | #N/A | 0 | 0 | 0
DEF_059 | #N/A | 0 | 0 | 0
DEF_060 | #N/A | 0 | 0 | 0
DEF_061 | #N/A | 0 | 0 | 0
DEF_062 | #N/A | 0 | 0 | 0
DEF_063 | #N/A | 0 | 0 | 0
DEF_064 | #N/A | 0 | 0 | 0
DEF_065 | #N/A | 0 | 0 | 0
DEF_066 | #N/A | 0 | 0 | 0
DEF_067 | #N/A | 0 | 0 | 0
DEF_068 | #N/A | 0 | 0 | 0
DEF_069 | #N/A | 0 | 0 | 0
DEF_070 | #N/A | 0 | 0 | 0
DEF_071 | #N/A | 0 | 0 | 0
DEF_072 | #N/A | 0 | 0 | 0
DEF_073 | #N/A | 0 | 0 | 0
DEF_074 | #N/A | 0 | 0 | 0
DEF_075 | #N/A | 0 | 0 | 0
DEF_076 | #N/A | 0 | 0 | 0
DEF_077 | #N/A | 0 | 0 | 0
DEF_078 | #N/A | 0 | 0 | 0
DEF_079 | #N/A | 0 | 0 | 0
DEF_080 | #N/A | 0 | 0 | 0
DEF_081 | #N/A | 0 | 0 | 0
DEF_082 | #N/A | 0 | 0 | 0
DEF_083 | #N/A | 0 | 0 | 0
DEF_084 | #N/A | 0 | 0 | 0
DEF_085 | #N/A | 0 | 0 | 0
DEF_086 | #N/A | 0 | 0 | 0
DEF_087 | #N/A | 0 | 0 | 0
DEF_088 | #N/A | 0 | 0 | 0
DEF_089 | #N/A | 0 | 0 | 0
DEF_090 | #N/A | 0 | 0 | 0
DEF_091 | #N/A | 0 | 0 | 0
DEF_092 | #N/A | 0 | 0 | 0
DEF_093 | #N/A | 0 | 0 | 0
DEF_094 | #N/A | 0 | 0 | 0
DEF_095 | #N/A | 0 | 0 | 0
DEF_096 | #N/A | 0 | 0 | 0
DEF_097 | #N/A | 0 | 0 | 0
DEF_098 | #N/A | 0 | 0 | 0
DEF_099 | #N/A | 0 | 0 | 0
DEF_100 | #N/A | 0 | 0 | 0
DEF_101 | #N/A | 0 | 0 | 0
DEF_102 | #N/A | 0 | 0 | 0
DEF_103 | #N/A | 0 | 0 | 0
DEF_104 | #N/A | 0 | 0 | 0
DEF_105 | #N/A | 0 | 0 | 0
DEF_106 | #N/A | 0 | 0 | 0
DEF_107 | #N/A | 0 | 0 | 0
DEF_108 | #N/A | 0 | 0 | 0
DEF_109 | #N/A | 0 | 0 | 0
DEF_110 | #N/A | 0 | 0 | 0
DEF_111 | #N/A | 0 | 0 | 0
DEF_112 | #N/A | 0 | 0 | 0
DEF_113 | #N/A | 0 | 0 | 0
DEF_114 | #N/A | 0 | 0 | 0
DEF_115 | #N/A | 0 | 0 | 0
DEF_116 | #N/A | 0 | 0 | 0
DEF_117 | #N/A | 0 | 0 | 0
DEF_118 | #N/A | 0 | 0 | 0
DEF_119 | #N/A | 0 | 0 | 0
DEF_120 | #N/A | 0 | 0 | 0
DEF_121 | #N/A | 0 | 0 | 0
DEF_122 | #N/A | 0 | 0 | 0
DEF_123 | #N/A | 0 | 0 | 0
DEF_124 | #N/A | 0 | 0 | 0
DEF_125 | #N/A | 0 | 0 | 0
DEF_126 | #N/A | 0 | 0 | 0
DEF_127 | #N/A | 0 | 0 | 0
DEF_128 | #N/A | 0 | 0 | 0
DEF_129 | #N/A | 0 | 0 | 0
DEF_130 | #N/A | 0 | 0 | 0
DEF_131 | #N/A | 0 | 0 | 0
DEF_132 | #N/A | 0 | 0 | 0
DEF_133 | #N/A | 0 | 0 | 0
DEF_134 | #N/A | 0 | 0 | 0
DEF_135 | #N/A | 0 | 0 | 0
DEF_136 | #N/A | 0 | 0 | 0
DEF_137 | #N/A | 0 | 0 | 0
DEF_138 | #N/A | 0 | 0 | 0
DEF_139 | #N/A | 0 | 0 | 0
DEF_140 | #N/A | 0 | 0 | 0
DEF_141 | #N/A | 0 | 0 | 0
DEF_142 | #N/A | 0 | 0 | 0
DEF_143 | #N/A | 0 | 0 | 0
DEF_144 | #N/A | 0 | 0 | 0
DEF_145 | #N/A | 0 | 0 | 0
DEF_146 | #N/A | 0 | 0 | 0
DEF_147 | #N/A | 0 | 0 | 0
DEF_148 | #N/A | 0 | 0 | 0
DEF_149 | #N/A | 0 | 0 | 0
DEF_150 | #N/A | 0 | 0 | 0
DEF_151 | #N/A | 0 | 0 | 0
DEF_152 | #N/A | 0 | 0 | 0
DEF_153 | #N/A | 0 | 0 | 0
DEF_154 | #N/A | 0 | 0 | 0
DEF_155 | #N/A | 0 | 0 | 0
DEF_156 | #N/A | 0 | 0 | 0
DEF_157 | #N/A | 0 | 0 | 0
DEF_158 | #N/A | 0 | 0 | 0
DEF_159 | #N/A | 0 | 0 | 0
DEF_160 | #N/A | 0 | 0 | 0
DEF_161 | #N/A | 0 | 0 | 0
DEF_162 | #N/A | 0 | 0 | 0
DEF_163 | #N/A | 0 | 0 | 0
DEF_164 | #N/A | 0 | 0 | 0
DEF_165 | #N/A | 0 | 0 | 0
DEF_166 | #N/A | 0 | 0 | 0
DEF_167 | #N/A | 0 | 0 | 0
DEF_168 | #N/A | 0 | 0 | 0
DEF_169 | #N/A | 0 | 0 | 0
DEF_170 | #N/A | 0 | 0 | 0
DEF_171 | #N/A | 0 | 0 | 0
DEF_172 | #N/A | 0 | 0 | 0
DEF_173 | #N/A | 0 | 0 | 0
DEF_174 | #N/A | 0 | 0 | 0
DEF_175 | #N/A | 0 | 0 | 0
DEF_176 | #N/A | 0 | 0 | 0
DEF_177 | #N/A | 0 | 0 | 0
DEF_178 | #N/A | 0 | 0 | 0
DEF_179 | #N/A | 0 | 0 | 0
DEF_180 | #N/A | 0 | 0 | 0
DEF_181 | #N/A | 0 | 0 | 0
DEF_182 | #N/A | 0 | 0 | 0
DEF_183 | #N/A | 0 | 0 | 0
DEF_184 | #N/A | 0 | 0 | 0
DEF_185 | #N/A | 0 | 0 | 0
DEF_186 | #N/A | 0 | 0 | 0
DEF_187 | #N/A | 0 | 0 | 0
DEF_188 | #N/A | 0 | 0 | 0
DEF_189 | #N/A | 0 | 0 | 0
DEF_190 | #N/A | 0 | 0 | 0
| Total | 0 | 0 | 0

## Data Validation
Defect Type | Phase | Round | Application Name | Severity | Priority | Defect Status | Defect Category | Sub Module
Defect | SIT | ROUND 1 | OLSS | High | High | New | Development Issue | Manage Memo
Clarification | UAT | ROUND 2 | ACA | Medium | Medium | Resend | Deployment Issue | Manage Report
New Requirement | REGERESSION |  | CONFINS | Low | Low | Duplicate | Infrastructure Issue
| SANITY |  |  | Showstopper |  | Assign to BSI Dev | GAP in BRD
[6 empty] | In-Progress BSI Dev | GAP in FSD
[6 empty] | Assign to COFINS Dev | Clarification
[6 empty] | In-Progress CONFINS Dev | Duplicate
[6 empty] | Clarification | Data Issue
[6 empty] | Deferred | Not Classified
SIT Ready
SIT Reopen
UAT Ready
UAT Reopen
Closed