## Issue Lists
No. | Raise Date | Raised by | Phase | Issue Description/Discussion Activity/Follow up Activity | Issue Type | Issue Status | Priority | PIC | Due Date | Comment From Developer Related Issue Occured | Checking Results by BSI | Actual Closure Date | Remarks
1 | 2019-10-29 | Marion | SIT | When SKD created, NI amount for that SKD is wrong. But when we click on price product/ RV field and click something in keyboard, the NI amount for that SKD change to right amount. Needs to discuss whether it is fixed in this CR or new problem | Bugs | Closed | High | Marion
2 | 2019-10-29 | Marion | SIT | When Checker not check any checklist, after pop up "Are you sure you want to check" and click button Yes, the process stopping. There should be pop up "Please fill all approval list" | Bugs | Closed | High | Marion
3 | 2019-10-29 | Marion | SIT | Pop Up "Please fill all approval list & approval date" should be same as other pop up in OLSS | Bugs | Open | Low | Marion
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## 1
informasi pertama begini. Kolom total net investment sudah menunjukan angka yang benar. Nilai RV with VAT juga. Kolom product price masih salah
setelah di klik field nya dan ketik apapun di keyboard, nilai NI akan otomatis berubah dengan NI yang benar, namun RV masih termasuk VAT (seharusnya exclude VAT)
namun ketika disubmit, nilai NI, RV dan net menunjukan angka yang benar

## 2
Checklist ga dicek semua, button yes diklik sekali lalu tidak bisa diklik lagi dan pop up warning tidak keluar.

## validation list (hidden)
Phase | Issue Type | Issue Status | Priority | PIC
SIT | Bugs | Open | Low | Aulia
UAT | Setting | On progress fixing by PG | Medium | Marion
| Data | Retest by BA | High | Nisa
Closed