## Issue Lists
No. | Raise Date | Raised by | Phase | Issue Description/Discussion Activity/Follow up Activity | Issue Type | Issue Status | Priority | PIC | Due Date | Comment From Developer Related Issue Occured | Checking Results by BSI | Actual Closure Date | Remarks
1 | 2019-10-29 | Marion | SIT | When SKD created, NI amount for that SKD is wrong. But when we click on price product/ RV field and click something in keyboard, the NI amount for that SKD change to right amount. Needs to discuss whether it is fixed in this CR or new problem | Bugs | Closed | High | Ahmad Sobari
2 | 2019-10-29 | Marion | SIT | When Checker not check any checklist, after pop up "Are you sure you want to check" and click button Yes, the process stopping. There should be pop up "Please fill all approval list" | Bugs | Closed | High | Ahmad Sobari
3 | 2019-10-30 | Marion | SIT | Pop Up "Please fill all approval list & approval date" change to be the same as other pop up | Bugs | Open | Low | Ahmad Sobari
4 | 2019-10-30 | Marion | SIT | Approval date not show after SKD checked | Bugs | Open | Low | Ahmad Sobari
5 | 2019-10-30 | Marion | SIT | Print Report List of SKD cannot be printed (note from Pak Fajar: maybe the directory path folder wrongly mapped) | Bugs | Open | High | Ahmad Sobari
6 | 2019-10-30 | Marion | SIT | The checklist button that Admin OPL not check, after SKD checked the checklist checked. Should be remain blank as not checked | Bugs | Open | Medium | Ahmad Sobari
7 | 2019-10-30 | Marion | SIT | Approver should be cannot change checklist field. Only Admin OPL can | Bugs | Open | Medium | Ahmad Sobari
8 | 2019-10-30 | Marion | SIT | SKD Print out need to be fixed | Bugs | Open | Low | Ahmad Sobari
9 | 2019-10-30 | Marion | SIT | Approver name in SKD print out and checklist is different | Bugs | Open | Low | Ahmad Sobari
10 | 2019-10-30 | Marion | SIT | When SKD approved, the next approval column should be blank | Bugs | Open | Low | Ahmad Sobari
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## 1
informasi pertama begini. Kolom total net investment sudah menunjukan angka yang benar. Nilai RV with VAT juga. Kolom product price masih salah
setelah di klik field nya dan ketik apapun di keyboard, nilai NI akan otomatis berubah dengan NI yang benar, namun RV masih termasuk VAT (seharusnya exclude VAT)
namun ketika disubmit, nilai NI, RV dan net menunjukan angka yang benar

## 2
Checklist ga dicek semua, button yes diklik sekali lalu tidak bisa diklik lagi dan pop up warning tidak keluar.

## 4
approval date nya kosong setelah SKD di cek

## 5
muncul error saat print list SKD

## 6
awalnya yang dicek baris 1,3,5 tapi setelah sukses dicek, malah ke-cek semua

## 8
tulisannya ada yang ketumpuk

## 9
0000423/4/01/10/2019

## 10
status approved, next approval nya IRMA VERDIAN
seharusnya kosong

## validation list (hidden)
Phase | Issue Type | Issue Status | Priority | PIC
SIT | Bugs | Open | Low | Aulia
UAT | Setting | On progress fixing by PG | Medium | Marion
| Data | Retest by BA | High | Nisa
Closed