## Sheet1
No | Problem | Status | PIC
1 | Fungsi approval date saat check SKD?
2 | Pada search list SKD, search criteria minta ditambahkan approval date supaya bisa print report berdasarkan tanggal approve | CR baru | Pak Bari
3 | Revise button di SKD apa fungsinya? Apa masih diperlukan?
4 | Muncul error saat cancel SKD "Failed! The record you attempted to edit was modified by another user after you got the original value. The edit operation was cancelled. If you still want to edit this record, click the save change button again.Otherwise click the Back to list hyperlink" namun status SKD tetap tercancel. | Perlu di debug | Pak Bari
5 | Tampilan O/S NI bergeser di SKD | DONE
6 | Tampilan O/S NI di report SKD? | Perlu di cek | Pak Bari
7 | Reject button di SKD apa fungsinya? Jika di klik, maka akan muncul error "Please fill remarks" namun remarks disable.
8 | List SKD bergeser 1 kolom (misplaced) | DONE
9 | 1 SKD displit jadi 2 agreement, nilai NI per agreement tidak sesuai | SKD 1584 & 1583 nilai Price belum sesuai, nilai agreement belum sesuai | Pak Bari
10 | SKD yang sudah dicancel dengan status cancelling, button cancel belum disable dan masih bisa di klik dan menambah revision history | on queue | Pak Bari
11 | Agreement yang dicancel masih muncul di tabel NI | status di apps masih cancelling (belum approve cancellation) jadi belum mengurangi NI
12 | Agreement yang partial OS NI nya tidak sesuai dengan quantity agreement | SKD 1583 | Pak Bari

## case NI
case Bu Herni:
yang seharusnya muncul: | http://10.1.1.37/olss_training/Skd/Detail/1583
Description | Agreement | Status SKD | Status Agreement | Customer Name | Price | RV | Net
SKD No: 0000392/4/01/09/2019 |  | Approved |  | BUDGET | 11650000000 | 4909090909.0909 | 6740909090.9091
| 0000337/4/01/09/2019 |  | Cancelled | BUDGET | 5825000000 | 2454545454.5455 | 3370454545.4545
| 0000338/4/01/09/2019 |  | Approved | BUDGET | 5825000000 | 2454545454.5455 | 3370454545.4545
| 0000339/4/01/09/2019 |  | Approved | BUDGET | 5825000000 | 2454545454.5455 | 3370454545.4545
case di SIT
http://10.1.1.38/olss_crsonny_merge/Skd/Detail/1586
Description | Agreement | Status SKD | Status Agreement | Customer Name | Price | RV | Net
SKD No: 0000434/4/01/09/2019 |  | Approved |  | G4S SECURITY SERVICES | 16350000000 | 1767272727.2727 | 14582727272.7273
| 0000326/4/01/09/2019 |  | Submitted | G4S SECURITY SERVICES | 5450000000 | 589090909.0909 | 4860909090.9091
| 0000327/4/01/09/2019 |  | Submitted | G4S SECURITY SERVICES | 5450000000 | 589090909.0909 | 4860909090.9091
| 0000328/4/01/09/2019 |  | Submitted | G4S SECURITY SERVICES | 5450000000 | 589090909.0909 | 4860909090.9091