## Issue Lists
No. | Raise Date | Raised by | Phase | Issue Description/Discussion Activity/Follow up Activity | Issue Type | Issue Status | Priority | PIC | Due Date | Comment From Developer Related Issue Occured | Checking Results by BSI | Actual Closure Date | Remarks
1 |  |  | SIT |  | Bugs | On progress fixing by PG | Medium | Aulia
2 | 28-08-19 | Aulia | SIT | When Conduct "Save as Draft" while creating SKD, it shows error message, but the process is success | Bugs | Closed | Low | Sobari | 29-08-19 |  | Passed | 29-08-19
3 | 28-08-19 | Aulia | SIT | When Conduct "Submit" while creating SKD, it shows error message, but the process is success | Bugs | Closed | Low | Sobari | 29-08-19 |  | Passed | 29-08-19
4 | 28-08-19 | Aulia | SIT | When Conduct "Submit" while Edit SKD from draft, it shows error message and the process is failed (Status is stil draft) | Bugs | Closed | High | Sobari | 29-08-19 |  | Passed | 29-08-19
5 | 28-08-19 | Aulia | SIT | When conduct SKD Cancellation, there's error message (please fill all approval list) | Bugs | Closed | High | Sobari | 29-08-19 |  | Passed | 28-08-19
6 | 28-08-19 | Aulia | SIT | button not shown when HOD want to conduct Approve / Reject Cancellation | Bugs | Closed | High | Sobari | 29-08-19 |  | Passed | 28-08-19
7 | 29-08-19 | Aulia | SIT | Remark field cannot be edited when HOD want to conduct Reject Cancellation | Bugs | Closed | Medium | Sobari | 30-08-19 |  | Passed | 29-08-19
8 | 29-08-19 | Aulia | SIT | When conduct "Reject Cancellation", status change to Checked when it supposed to change into Submitted | Bugs | Closed | High | Sobari | 30-08-19 |  | Passed | 30-08-19
9 | 29-08-19 | Aulia | SIT | button "checked" is not shown when user "Herni Hembang" want to checked the SKD | Bugs | Closed | High | Sobari | 30-08-19 |  | Passed | 30-08-19
10 | 29-08-19 | Aulia | SIT | Error when "Submit" create SKD | Bugs | Closed | High | Sobari | 30-08-19 |  | Passed | 30-08-19
11 | 29-08-19 | Aulia | SIT | When conduct "Reject Cancellation", status is still Cancelling when it supposed to change into Submitted | Bugs | Closed | High | Sobari | 30-08-19 |  | Passed | 30-08-19
12 | 30-08-19 | Aulia | SIT | when create skd, when select OPL Calculation number, shows error message | Bugs | Closed | Low | Sobari | 30-08-19 |  | Passed | 30-08-19
13 | 30-08-19 | Aulia | SIT | When conduct check SKD, error message found, but the process is success | Bugs | Closed | Low | Sobari | 30-08-19 |  | Passed | 30-08-19
14 | 2019-09-02 | Aulia | SIT | When conduct Cancel SKD by MO, Remark column cannot be entered and Cancel button did not shown | Bugs | Closed | High | Sobari | 2019-09-03 |  | Passed | 2019-09-02
15 | 2019-09-02 | Aulia | SIT | Error when Check SKD by AD | Bugs | Closed | High | Sobari | 2019-09-03 |  | Passed | 2019-09-02
16 | 2019-09-02 | Aulia | SIT | Error when Approve / Reject Cancellation | Bugs | Closed | High | Sobari | 2019-09-03 |  | Passed | 2019-09-02
17 | 2019-09-03 | Aulia | SIT | When Approved cancel SKD, Quotation and Caclculation supposed to be cancelled, but status is still valid | Bugs | Closed | High | Sobari | 2019-09-04
18 | 2019-09-03 | Nisa | SIT | Button Approved doesn't exist when HOB view Agreement Detail | Bugs | Closed | High | Sobari | 2019-09-04 |  | Resolved | 2019-09-03
19 | 2019-09-03 | Marion | SIT | Total O/S Net Investment column in SKD misplaced | Bugs | Closed | Low | Sobari
20 | 2019-09-03 | Marion | SIT | after agreement canceled, cancel button still active and still can be cancelled. It is adding status history | Bugs | Closed | Low | Sobari
21 | 2019-09-03 | Marion | SIT | SKD no 0000401/4/01/09/2019, net investment 11,5B (net investment 67B have this error too) , approver's name and role showing double, approver should be only until VP, VP's name blank, already checked and/or give remark in all column but still showing pop up warning "please fill all approval list" | Bugs | Closed | High | Sobari
22 | 2019-09-03 | Nisa | SIT | notif checked di halaman login muncul setelah logout | Bugs | Open | Low | Sobari
23 | 2019-09-03 | Nisa | SIT | field agreement dan status agreement di tabel OSNI saat view SKD masih null blm terisi keterangannya | Bugs | Closed | High | Sobari | 2019-09-04 |  | Resolved | 2019-09-04
24 | 2019-09-04 | Marion | SIT | Table Net Investment in SKD Detail still not showing agreement number and agreement status | Bugs | Closed | High | Sobari
25 | 2019-09-04 | Marion | SIT | Net Investment Calculation in SKD Detail still miscalculate. Need confirmation to user. | Development | Open | High | Firman
26 | 2019-09-04 | Nisa | SIT | remarks saat cancel view agreement tdk bisa diinput | Bugs | Closed | Low | Sobari
27 | 2019-09-04 | Nisa | SIT | button cancel seharusnya tidak ada pada agreement yg berstatus open | Bugs | Closed | Medium | Sobari |  |  | Resolved | 2019-09-17
28 | 2019-09-04 | Nisa | SIT | Cancel button should be unavailable for SKD in which the Agreement status is Open | Bugs | Closed | Medium | Sobari |  |  |  | 2019-09-16
29 | 2019-09-04 | Marion | SIT | SKD 0000405/4/01/09/2019 already created into two agreement. one of the agreement is cancelled. when new agreement created, show warning "0 more unit(s) available to cover" | Bugs | Closed | High | Sobari
30 | 2019-09-04 | Marion | SIT | SKD 0000406/4/01/09/2019, user VERDIAN already approve cancelation, then show error "Failed! The record you attempted to edit was modified by another user after you got the original value. The edit operation was canceled. If you still want to edit this record, click the Save Changes button again. Otherwise click the Back to List hyperlink." the status already cancelled, but in revision status, status cancelled by VERDIAN not showing and user STEFAN CHANDRA still can cancel it then the status will be "CANCELLING" | Bugs | Open | Medium | Sobari
31 | 2019-09-05 | Marion | SIT | NI 52B, approval scheme should be only until PD, but it is showing until BOC | Bugs | Closed | Low | Sobari
32 | 2019-09-05 | Marion | SIT | user BING WAN cannot approve agreement | Bugs | Closed | Medium | Sobari
33 | 2019-09-05 | Nisa | SIT | Cancel button should be unavailable for Agreement with Close Incomplete Status | Bugs | Closed | Medium | Sobari |  |  | Resolved | 2019-09-17
34 | 2019-09-05 | Nisa | SIT | Cancel button should be unavailable for SKD in which the Agreement status is Close Incomplete | Bugs | Closed | Medium | Sobari |  |  | Resolved | 2019-09-18
35 | 2019-09-13 | Nisa | SIT | Different value in OSNI table and above data, data include carroserie (SKD ID 1554) | Bugs | Open | Medium | Firman
36 | 2019-09-13 | Nisa | SIT | Price value 0 in all skd number (1486) | Bugs | Closed | Medium | Sobari |  |  |  | 2019-09-13
37 | 2019-09-13 | Nisa | SIT | Miscalculate in total OSNI | Bugs | Closed | Medium | Sobari |  |  |  | 2019-09-13
38 | 16-09-19 | Nisa | SIT | Cancel button should be unavailable for Agreement with Canceled Status | Bugs | Closed | Low | Sobari
39 | 2019-09-17 | Marion | SIT | Total qty agreement can be more than qty SKD (ID SKD 1581) | Bugs | Closed | Medium | Sobari
40 | 2019-09-16 | Bu Herni | UAT | 1 SKD displit jadi 2 agreement, nilai NI per agreement tidak sesuai; SKD 1583 nilai Price belum sesuai, nilai agreement belum sesuai | Bugs | Open | High | Firman
41 | 2019-09-16 | Bu Herni | UAT | Tampilan OS NI di Report SKD perlu dicek. sedangkan environment SIT & UAT tidak bisa print report. Goal: SKD bisa diprint dan tampilan page OS NI sama antara di kolom OS NI dengan di report | Bugs | Open | High | Firman
42 | 2019-09-16 | Bu Herni | UAT | SKD yang sudah dicancel dengan status cancelling, button cancel belum disable dan masih bisa di klik dan menambah revision history | Bugs | Closed | Low | Sobari
43 | 2019-09-16 | Bu Herni | UAT | Muncul error saat cancel SKD "Failed! The record you attempted to edit was modified by another user after you got the original value. The edit operation was cancelled. If you still want to edit this record, click the save change button again.Otherwise click the Back to list hyperlink" namun status SKD tetap tercancel. ID 1576 | Bugs | Open | Low | Sobari
44 | 2019-09-16 | Bu Herni | UAT | Hide revise button under login HERNI HEMBANG when SKD status Submitted & Checked (ID 1585) and hide Reject & Revise button under login VERDIAN when SKD status Checked (ID 1586) | Bugs | Closed | Low | Sobari
45 | 2019-09-23 | Marion | SIT | MO cannot cancel approved SKD ID 1587, login by STEFAN CHANDRA. | Bugs | Closed | High | Sobari
46 | 2019-09-23 | Marion | SIT | Cancelled SKD should be cannot approve again, ID 1543, login by HERNI HEMBANG/ VERDIAN. the button approve still exist. should be hidden. and user HERNI HEMBANG can approve SKD (should be cannot) | Bugs | Closed | High | Sobari
47 | 2019-09-24 | Marion | SIT | From SKD ID <= 1585 , there's error when submit agreement partial. but for SKD ID > 1585 no error | Bugs | Open | High | Sobari
48 | 2019-09-24 | Marion | SIT | SKD ID 1583, error when submit agreement full QTY "Failed! There are remaining Accessories/Carroserrie that still haven't been created in an Agreement. Please include the Agreement with the Accessories/Carroserrie paired with at least 1 Unit." which the SKD dont have any accessories or carroserries | Bugs | Closed | High | Sobari
49 | 2019-09-24 | Marion | SIT
50 | 2019-09-30 | Nisa | SIT | Field SKD number seharusnya berada dalam baris yg berbeda dgn field Agreement number | Bugs | Closed | Low | Firman |  |  |  | 2019-10-01
51 | 2019-09-30 | Nisa | SIT | Agreement with different unit amount has same value of NI | Bugs | Open | Low | Firman
52 | 2019-09-30 | Nisa | SIT | Value NI of SKD after all unit has been used | Bugs | Closed | Medium | Firman |  |  |  | 2019-10-02
53 | 2019-09-30 | Nisa | SIT | There is error notif but skd status changed to cancelled, and revision history doesn’t added | Bugs | Open | Low | Sobari
54 | 2019-09-30 | Nisa | SIT | Status Calculation still valid although SKD has been canceled | Bugs | Open | High | Sobari
55 | 2019-10-02 | Nisa | SIT | Failed to open old SKD detail | Bugs | Open | High | Sobari

## issue 38
1467; agreement ini sudah approved cancel - statusnya cancelled. namun user HERNI HEMBANG masih terlihat button cancel dan masih aktif. jika diklik maka status akan berubah jadi cancelling lagi.
seharusnya jika agreement sudah cancel, tidak boleh ada button apapun yang terlihat/ masih aktif

## issue 40
Expected result nya scroll ke bawah
Description | Agreement | Status SKD | Status Agreement | Customer Name | Price | RV | Net
SKD No: 0000392/4/01/09/2019 |  | Approved |  | BUDGET | 11650000000 | 4909090909.09 | 6740909090.91
| 0000337/4/01/09/2019 |  | Cancelled | BUDGET | 5825000000 | 2454545454.55 | 3370454545.45
| 0000338/4/01/09/2019 |  | Approved | BUDGET | 5825000000 | 2454545454.55 | 3370454545.45
| 0000339/4/01/09/2019 |  | Approved | BUDGET | 5825000000 | 2454545454.55 | 3370454545.45

## issue 42
belum bisa ditest karena bugs user MO tidak bisa cancel SKD (issue 45)

## issue 43
perlu di debug karena error ini jarang terjadi.

## issue 45
user STEFAN CHANDRA seharusnya bisa cancel SKD yang dia buat. di SKD 1587 tidak ada button cancel (seharusnya ada)

## validation list (hidden)
Phase | Issue Type | Issue Status | Priority | PIC
SIT | Bugs | Open | Low | Aulia
UAT | Setting | On progress fixing by PG | Medium | Marion
| Data | Retest by BA | High | Nisa
Closed

## issue 46
setelah user VERDIAN approve cancel, user HERNI HEMBANG & VERDIAN bisa approve kembali. bisa dites di SKD ID 1512
tes untuk SKD yang baru dibuat tidak ada karena bugs MO tidak bisa cancel SKD (issue 45)

## issue 47
contoh SKD ID 1585, 1584

## issue 48
SKD ID 1583, qty 10 UNIT, waktu mau ditarik agreement qty 10 UNIT, muncul error failed karena ada aksesoris/karoseri yang belum ditarik. padahal di SKD tersebut tidak ada aksesoris/karoseri