## Issue Lists
No. | Raise Date | Raised by | Phase | Issue Description/Discussion Activity/Follow up Activity | Issue Type | Issue Status | Priority | PIC | Due Date | Comment From Developer Related Issue Occured | Checking Results by BSI | Actual Closure Date | Remarks
1 | 2019-10-29 | Marion | SIT | When SKD created, NI amount for that SKD is wrong. But when we click on price product/ RV field and click something in keyboard, the NI amount for that SKD change to right amount. Needs to discuss whether it is fixed in this CR or new problem | Bugs | Closed | High | Ahmad Sobari
2 | 2019-10-29 | Marion | SIT | When Checker not check any checklist, after pop up "Are you sure you want to check" and click button Yes, the process stopping. There should be pop up "Please fill all approval list" | Bugs | Closed | High | Ahmad Sobari
3 | 2019-10-30 | Marion | SIT | Pop Up "Please fill all approval list & approval date" change to be the same as other pop up | Bugs | Closed | Low | Ahmad Sobari
4 | 2019-10-30 | Marion | SIT | Approval date not show after SKD checked | Bugs | Closed | Low | Ahmad Sobari
5 | 2019-10-30 | Marion | SIT | Print Report List of SKD cannot be printed (note from Pak Fajar: maybe the directory path folder wrongly mapped) | Bugs | Closed | High | Ahmad Sobari
6 | 2019-10-30 | Marion | SIT | The checklist button that Admin OPL not check, after SKD checked the checklist checked. Should be remain blank as not checked | Bugs | Closed | Medium | Ahmad Sobari
7 | 2019-10-30 | Marion | SIT | Approver should be cannot change checklist field. Only Admin OPL can | Bugs | Closed | Medium | Ahmad Sobari
8 | 2019-10-30 | Marion | SIT | SKD Print out need to be fixed | Bugs | Closed | Low | Ahmad Sobari
9 | 2019-10-30 | Marion | SIT | Approver name in SKD print out and checklist is different | Bugs | Retest by BA | High | Ahmad Sobari
10 | 2019-10-30 | Marion | SIT | When SKD approved, the next approval column should be blank | Bugs | Closed | Low | Ahmad Sobari
11 | 2019-11-01 | Marion | SIT | Approver's name for BOD should be Shareholder's Meeting | Bugs | Open | Low | Ahmad Sobari
12 | 2019-11-01 | Marion | SIT | When error "Please Fill All Approval List & Approval Date", page should be automatic go to top so user can know there's this error | Bugs | Closed | Low | Ahmad Sobari
13 | 2019-11-01 | Marion | SIT | Checklist already filled but stil show error "Please Fill All Approval List & Approval Date" | Bugs | Closed | High | Ahmad Sobari
14 | 2019-11-01 | Marion | SIT | Approval date should be can change after SKD checked. BUT ONLY ADMIN OPL CAN and status SKD = Submitted/ Checked | Bugs | Closed | High | Ahmad Sobari
15 | 2019-11-01 | Marion | SIT | Show Approval date in Print Out List of SKD | Bugs | Retest by BA | Low | Ahmad Sobari
16 | 2019-11-01 | Marion | SIT | Approver VERDIAN & MASANORI GOTO cannot approve SKD 1626 (NI 160M) | Bugs | Open | High | Ahmad Sobari
17 | 2019-11-04 | Marion | SIT | Print out SKD PDF needs to be fixed (see sheet 17) | Bugs | Retest by BA | Low | Ahmad Sobari
18 | 2019-11-04 | Marion | SIT | Print out SKD for NI > 90B only until MASANORI GOTO, should be until SHAREHOLDER'S MEETING | Bugs | Retest by BA | Low | Ahmad Sobari
19 | 2019-11-04 | Marion | SIT | SKD NI > 90B can be checked without checklist the button; 0000433/4/01/11/2019; update 5 Nov: SKD with all NI can be checked if already choose approval date and check checklist button at least one box (ID 1638) | Bugs | Retest by BA | Low | Ahmad Sobari
20 | 2019-11-06 | Marion | SIT | In print out SKD, if the NI > 90 B, then "Approved By" will show Direktur OPL (11) – Collection & HR Director (27) – Operational Director (26) – VP Marketing (13) – VP Operation (70) – PD (14) 's full names. (jobtitles ID) | New Requirement | Retest by BA | Medium | Ahmad Sobari
21 | 2019-11-06 | Marion | SIT | Approver's name in print out SKD should be active role; http://10.1.1.37/olss_crapproval/Skd/Report/1637 approver 2 is ERYENNY which is not active | Bugs | Retest by BA | Low | Ahmad Sobari
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## 1 (hidden)
informasi pertama begini. Kolom total net investment sudah menunjukan angka yang benar. Nilai RV with VAT juga. Kolom product price masih salah
setelah di klik field nya dan ketik apapun di keyboard, nilai NI akan otomatis berubah dengan NI yang benar, namun RV masih termasuk VAT (seharusnya exclude VAT)
namun ketika disubmit, nilai NI, RV dan net menunjukan angka yang benar

## 2 (hidden)
Checklist ga dicek semua, button yes diklik sekali lalu tidak bisa diklik lagi dan pop up warning tidak keluar.

## 4 (hidden)
approval date nya kosong setelah SKD di cek

## 5 (hidden)
muncul error saat print list SKD

## 6 (hidden)
awalnya yang dicek baris 1,3,5 tapi setelah sukses dicek, malah ke-cek semua

## 8 (hidden)
tulisannya ada yang ketumpuk

## 9
0000423/4/01/10/2019

## 10 (hidden)
status approved, next approval nya IRMA VERDIAN
seharusnya kosong

## 11 (hidden)
harusnya namanya Shareholder's Meeting

## 12 (hidden)
Jika ada error Please Fill All Approval List & Approval Date, harus otomatis naik ke atas, ke arah error nya

## 14 (hidden)
untuk admin OPL, checklist table bisa di edit jika statusnya SUBMITTED

## 15
tambahkan kolom approval date di print out list of SKD

## 16
approver tidak bisa approve SKD; MASANORI GOTO & VERDIAN

## 17
Print Out PDF SKD minta dibetulkan tampilan nya

## 19
belum diceklist dan dikasih remarks sudah bisa checked

## validation list (hidden)
Phase | Issue Type | Issue Status | Priority | PIC
SIT | Bugs | Open | Low | Aulia
UAT | Setting | On progress fixing by PG | Medium | Marion
| Data | Retest by BA | High | Nisa
Closed