## Issue Lists
No. | Raise Date | Raised by | Phase | Issue Description/Discussion Activity/Follow up Activity | Issue Type | Issue Status | Priority | PIC | Due Date | Comment From Developer Related Issue Occured | Checking Results by BSI | Actual Closure Date | Remarks
1 | 2019-12-23 | Marion | SIT | After click save in Update Perjanjian Jual Beli screen, download button cannot be clicked. Must re-open the memo. | Bugs | Closed | Medium | Fadillah Aditya
2 | 2019-12-23 | Marion | SIT | Report type cannot be edited. | Bugs | Closed | High | Fadillah Aditya
3 | 2019-12-23 | Marion | SIT | When load the Update Perjanjian Jual Beli screen, it is always showing report type Pribadi, although the last time report type is Badan Hukum | Bugs | Closed | Medium | Fadillah Aditya
4 | 2019-12-23 | Marion | SIT | Margin report too small, at least 3 cm | Bugs | Closed | Minor | Fadillah Aditya
5 | 2019-12-23 | Marion | SIT | Add button Back in download page | Bugs | Closed | Minor | Fadillah Aditya
6 | 2019-12-26 | Marion | SIT | Report number not running (second report number still 00001, should be 00002) | Bugs | Closed | High | Fadillah Aditya
7 | 2019-12-26 | Marion | SIT | BPKB's name cannot be copy paste | Bugs | Closed | High | Fadillah Aditya
8 | 2019-12-26 | Marion | SIT | Data of Report submit date wrong, ID 418 should be 12 November | Bugs | Closed | Medium | Fadillah Aditya
9 | 2019-12-26 | Marion | SIT | Pribadi, 1 asset: - margin too small - harga kendaraan format should be Rp. 140.789.550,- - no need TOTAL HARGA KENDARAAN field | Bugs | Closed | Minor | Fadillah Aditya
10 | 2019-12-26 | Marion | SIT | report showing double asset (needs to add 1 table opluobjectlease to the query to link which agreement from the sold asset) | Bugs | Closed | High | Fadillah Aditya
11 | 2019-12-27 | Marion | SIT | when click save button, screen update PJB wont close | Bugs | Closed | High | Fadillah Aditya
12 | 2019-12-27 | Marion | SIT | Report month in roman should be showing month of memo submit | Bugs | Closed | Medium | Fadillah Aditya
13 | 2019-12-27 | Marion | SIT | download file for word, hide '2003' words | Bugs | Open | Minor | Fadillah Aditya
14 | 2019-12-27 | Marion | SIT | if the amount is 100, the amount in words showing 'SeRatus'. should be 'Seratus' | Bugs | Closed | Minor | Fadillah Aditya
15 | 2019-12-27 | Marion | SIT | Warning when download button clicked before data screen Update PJB saved | Bugs | Closed | Minor | Fadillah Aditya
16 | 2019-12-30 | Marion | SIT | Template pribadi - multiple asset (ID 446) : - Amount in words not rounded, different with total harga kendaraan - Total asset should be only 12, the report showing 24 - Amount TOTAL in Lampiran Perjanjian Jual Beli not rounded - Remove space or enter in Berita Acara Serah Terima Kendaraan | Bugs | Closed | Minor | Fadillah Aditya
17 | 2019-12-30 | Marion | SIT | Template company - multiple asset (ID 449): - Remove box in title Lampiran Perjanjian Jual Beli - Remove space or enter in Berita Acara Serah Terima Kendaraan | Bugs | Closed | Minor | Fadillah Aditya
18 | 2020-01-09 | Marion | SIT | Report number showing year 2020 although the submit date is 2019 | Bugs | Closed | Medium | Fadillah Aditya
19 | 2020-01-09 | Marion | SIT | Template pribadi - one asset (ID 373): - Harga Kendaraan field not rounded - Amount in words not rounded | Bugs | Closed | Medium
20 | 2020-01-13 | Antonius F | UAT | Milyar & Trilyun in words should be Miliar & Triliun | Bugs | Open | Minor
21 | 2020-01-13 | Antonius F | UAT | Reset number every year | Bugs | Open | Minor
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## 1 (hidden)
informasi pertama begini. Kolom total net investment sudah menunjukan angka yang benar. Nilai RV with VAT juga. Kolom product price masih salah
setelah di klik field nya dan ketik apapun di keyboard, nilai NI akan otomatis berubah dengan NI yang benar, namun RV masih termasuk VAT (seharusnya exclude VAT)
namun ketika disubmit, nilai NI, RV dan net menunjukan angka yang benar

## 2 (hidden)
Checklist ga dicek semua, button yes diklik sekali lalu tidak bisa diklik lagi dan pop up warning tidak keluar.

## 4 (hidden)
approval date nya kosong setelah SKD di cek

## 5 (hidden)
muncul error saat print list SKD

## 6 (hidden)
awalnya yang dicek baris 1,3,5 tapi setelah sukses dicek, malah ke-cek semua

## 8 (hidden)
tulisannya ada yang ketumpuk

## 10 (hidden)
status approved, next approval nya IRMA VERDIAN
seharusnya kosong

## 11 (hidden)
harusnya namanya Shareholder's Meeting

## 12 (hidden)
Jika ada error Please Fill All Approval List & Approval Date, harus otomatis naik ke atas, ke arah error nya

## 14 (hidden)
untuk admin OPL, checklist table bisa di edit jika statusnya SUBMITTED

## validation list (hidden)
Phase | Issue Type | Issue Status | Priority | PIC
SIT | Bugs | Open | Low | Aulia
UAT | Setting | On progress fixing by PG | Medium | Marion
| Data | Retest by BA | High | Nisa
Closed