## Priority (hidden)
Service # | Change # | Ticket DSF ITD | Title | Status | Requestor | Effect | Mandays | Priority | CR Type | Release Date | Reschedule Release Date
S0179754 |  | IT-CR-250919-731 (#35969) | Automatic Sync MFAPPL to OLSS | On Progress | Olivia Setiawan (OPL) |  |  | 1 | Big | W1 Nov
S0143140 | C0023190 | IT-CR-250418-264 (#10269) | Change Approval SKD in OLSS | On Progress | Mirza Dwita (OPL) |  |  | 2 | Big | W2 Oct | W1 Nov
S0169552 | C0023822 | IT-CR-210619-638 | Change SKD Approval Scheme | On Progress | Herni Hembang (OPL) |  | 18 MD | 2 | Big | W2 Jan 2020 | W1 Nov
S0165486 | C0023661 | IT-CR-070519-593 (#29066) | Change Print Invoice Template Tanda Terima Doc | SIT | Astuti Dewi (OPL) |  | 3 MD | 3 | Small | W2 Dec | W1 Nov
S0147214 | C0023246 | CR with RFC | Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | SIT | Antonius Fedrik (OPL) |  | 15 MD | 4 | Big | W4 May | W3 Dec
S0169553 |  | IT-CR-280619-642 | PJB (Perjanjian Jual Beli) for OLSS Menu Asset Selling | Open | Antonius Fedrik (OPL) |  | 11 MD | 5 | Big | W3 Jan 2020 | W3 Mar 2020
S0171701 |  | IT-CR-080719-649 | Additional field in column 'Budget' and 'Actual' based on Number of Unit in Lampiran Investasi in menu Asset Selling (Manage Memo/View Profit Analysis). | Open | Antonius Fedrik (OPL) |  |  | 6 | Small | W2 Feb 2020 | W1 May 2020
S0177966 |  | IT-CR-100919-724 | Calculate PPN PPh for maintenance | Open | Fahmi Afandi (OPL) |  |  | 7 | Medium | W3 Mar 2020 | W2 Jun 2020
S0169246 |  | IT-CR-200519-610 | Enhancement in Management Module (Additional Information for Periode Kontrak, Progress Status dan Registration Status). | Open | Pathul Wadi (OPL) |  | 15 MD | 8 | Big | W1 Jan 2020 | W3 Feb 2020
S0171207 |  | IT-CR-100719-654 | Add button 'Edit' in menu Monitoring Document to update Insurance Data (Insco, Policy Number, Start Date & End Date). => will affect with the new CR | Open | Lestaryono (OPL) |  |  | 9 | Small | W4 Jul 2019 | W1 Apr 2020
S0174451 |  | IT-CFR-170719-661 #32392 | Enhance management module with additional field and column. => will affect with the new CR | Open | Pathul Wadi (OPL) |  |  | 10 | Big | W3 Mar 2020 | W2 Jun 2020
|  | IT-CFR-071019-750 #36566 | Additional Field 'Police Number' in Billing Print Out | Open | Astuti Dewi (OPL) |  | 15 MD | 11 | Big |  |  | consider to check the field on staging
|  | IT-CFR-250919-734 #35976 | Remove Duplicate Showing Agreement in Screen | Open | Olivia Setiawan (OPL) |  | 10 MD | 12 | Medium
|  | IT-CFR-250919-733 #35972 | Activate Module "Manage Warning Letter" | On Hold | Olivia Setiawan (OPL) |  | 12 MD | 13 | Medium
|  |  | Change Formula Selling Price for Auction in Asset Selling Module (layout) |  |  |  |  | 14
S0147213 | C0023245 | CR with RFC | Cancellation SKD & Agreement Part 2 | On Hold | Herni Hembang (OPL) |  |  |  | Big | W2 May

## Summary
No | Service # | Change # | Ticket DSF ITD | Title | Status | Requestor | Priority | CR Type
1 | S0179754 |  | IT-CR-250919-731 (#35969) | Automatic Sync MFAPPL to OLSS | Deployed on 29th Nov | On Progress | Olivia Setiawan (OPL) | Big
2 | S0169553 | C0023933 | IT-CR-280619-642 | PJB (Perjanjian Jual Beli) for OLSS Menu Asset Selling | Development | Antonius Fedrik (OPL) | Priority - daily activity | Medium
3 | S0183856 | C0023940 | IT-CR-080719-649 | Additional field in column 'Budget' and 'Actual' based on Number of Unit in Lampiran Investasi in menu Asset Selling (Manage Memo/View Profit Analysis). | Requirement | Antonius Fedrik (OPL) | Priority - needs to be calculated by system to avoid human error | Medium
4 | S0147214 | C0023246 | CR with RFC | Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | SIT | Antonius Fedrik (OPL) | On Progress | Big

## CR List
No | Service # | Change # | Ticket DSF ITD | Category | Title | Module | Status | Remarks | Requestor | Mandays | Priority | CR Type | Release Date | Release Date
1 | S0147214 | C0023246 | CR with RFC | CR | Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | Asset Selling | UAT | On Progress | Antonius Fedrik (OPL) | 15 MD | 1 | Big | W4 May | W3 Dec
2 | S0169553 | C0023933 | IT-CR-280619-642 | CR | PJB (Perjanjian Jual Beli) for OLSS Menu Asset Selling | Asset Selling | Development | Priority - daily activity | Antonius Fedrik (OPL) | 11 MD | 2 | Medium | W3 Jan 2020 | W2 Jan 2020
3 | S0183856 | C0023940 | IT-CR-080719-649 | CR | Additional field in column 'Budget' and 'Actual' based on Number of Unit in Lampiran Investasi in menu Asset Selling (Manage Memo/View Profit Analysis). | Asset Selling | Development | Priority - needs to be calculated by system to avoid human error | Antonius Fedrik (OPL) | 13 MD | 3 | Medium | W2 Feb 2020 | W2 Jan 2020
4 |  |  | IT-CR-100919-724 | CR | Calculate PPN PPh for maintenance | Asset Maintenance | Open | Priority - needs to be calculated by system to avoid human error | Fahmi Afandi (OPL) | 15 MD | 4 | Big | W3 Mar 2020 | W3 Jan 2020
5 |  |  | IT-CR-200519-610 | CR | Enhancement in Management Module (Additional Information for Periode Kontrak, Progress Status dan Registration Status). | Asset Management | Open | Priority - management module must be enhanced so cost of the asset can be recorded by system and asset can be maintained well by system (avoid human error) | Pathul Wadi (OPL) | 38 MD | 5 | Big | W1 Jan 2020 | W3 Feb 2020
6 |  |  | IT-CFR-170719-661 #32392 | CR | Enhance management module with additional field and column. => will affect with the new CR | Asset Management | Open |  | Pathul Wadi (OPL) |  |  |  | W3 Mar 2020
7 |  |  | IT-CFR-250919-734 #35976 | CR | Remove Duplicate Showing Agreement in Screen | Collection | Open | Priority | Olivia Setiawan (OPL) | 10 MD | 6 | Medium |  | W5 Jan 2020
8 |  | C0023245 | CR with RFC | CR | Cancellation SKD & Agreement Part 2 | Marketing | Open | Low Priority - needs CR automatic Sync MFAPPL to OLSS & CR Calculation Outstanding NI deployed | Herni Hembang (OPL) | 25 MD | 7 | Big | W2 May | needs further discussion

## CR OLSS
Progress CR-OLSS Production Period December 2019
[16 empty] | 2016 | 2017 | [11 empty] | 2018 |  | 2019 | [11 empty] | 2020
No | Service # | Change # | Ticket DSF ITD | Title | Module | Status | Remarks | Requestor | Mandays | Priority | CR Type | Release Date | Reschedule Release Date | PIC |  | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP
1 | S0147214 | C0023246 | CR with RFC | Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | Asset Selling | SIT | On Progress | Antonius Fedrik (OPL) | 15 MD | 1 | Big | W4 May | W3 Dec | CRISTIN | Plan
[14 empty] | FIRMANSYAH | Actual
2 | S0169553 | C0023933 | IT-CR-280619-642 | PJB (Perjanjian Jual Beli) for OLSS Menu Asset Selling | Asset Selling | Development | Priority - daily activity | Antonius Fedrik (OPL) | 11 MD | 2 | Medium | W3 Jan 2020 | W2 Jan 2020 | MARION | Plan
[14 empty] | FADILLAH | Actual
3 | S0183856 | C0023940 | IT-CR-080719-649 | Additional field in column 'Budget' and 'Actual' based on Number of Unit in Lampiran Investasi in menu Asset Selling (Manage Memo/View Profit Analysis). | Asset Selling | Development | Priority - needs to be calculated by system to avoid human error | Antonius Fedrik (OPL) | 13 MD | 3 | Medium | W2 Feb 2020 | W2 Jan 2020 | RAYANG | Plan
[14 empty] | AHMAD SOBARI | Actual
4 |  |  | IT-CR-100919-724 | Calculate PPN PPh for maintenance | Asset Maintenance | Open | Priority - needs to be calculated by system to avoid human error | Fahmi Afandi (OPL) | 15 MD | 4 | Big | W3 Mar 2020 | W3 Jan 2020 | RAYANG | Plan
[14 empty] | FADILLAH | Actual
5 |  |  | IT-CR-200519-610 | Enhancement in Management Module (Additional Information for Periode Kontrak, Progress Status dan Registration Status). | Asset Management | Open | Priority - management module must be enhanced so cost of the asset can be recorded by system and asset can be maintained well by system (avoid human error) | Pathul Wadi (OPL) | 38 MD | 5 | Big | W1 Jan 2020 | W3 Feb 2020 | MARION | Plan
[14 empty] | AHMAD SOBARI | Actual
6 |  |  | IT-CFR-170719-661 #32392 | Enhance management module with additional field and column. => will affect with the new CR | Asset Management | Open |  | Pathul Wadi (OPL) |  |  |  | W3 Mar 2020 |  | MARION | Plan
[14 empty] | AHMAD SOBARI | Actual
7 |  |  | IT-CFR-250919-734 #35976 | Remove Duplicate Showing Agreement in Screen | Collection | Open | Priority | Olivia Setiawan (OPL) | 10 MD | 6 | Medium |  | W5 Jan 2020 | RAYANG | Plan
[14 empty] | FADILLAH | Actual
8 |  | C0023245 | CR with RFC | Cancellation SKD & Agreement Part 2 | Marketing | Open | Low Priority - needs CR automatic Sync MFAPPL to OLSS & CR Calculation Outstanding NI deployed | Herni Hembang (OPL) | 25 MD | 7 | Big | W2 May | needs further discussion | RAYANG | Plan
[14 empty] | FADILLAH | Actual
Legend:
Preparation - Analyze and Design
| Development & UAT Prep |  | (if duration less than 1 week, just put this colour)
| SIT&UAT |  | (if duration less than 2 week, 1st week for development, 2nd week for SIT&UAT)
Deployment
It will be handled by "project". See lower table.
Previous schedule
1 | Develop B2B
CR Category |  | EFFORT (REQUIREMENT, DESIGN, DEVELOPMENT, SIT)
| BIG CR | > 20 MD
| MEDIUM CR | 11 - 20 MD
| SMALL CR | <= 10 MD

## Summary CR OLSS (hidden)
Row Labels | Count of Status
Development
S0147211 | 1
S0164989 | 1
Hold
S0136137 | 1
S0147212 | 1
Open
S0126984 | 1
S0132095 | 1
S0137795 | 1
S0143140 | 1
S0165486 | 1
SIT
S0137870 | 1
S0161446 | 1
UAT
S0147213 | 1
UAT Script in progress
S0147214 | 1
(blank)
(blank)
Grand Total | 13

## Potential CR
No | Service # | Change # | Ticket DSF ITD | Title | Status | Requestor | Priority | PIC
1 |  |  |  | Change Input and Print Payment Approval | Need to confirm to user | Junaidi Didy |  |  | needs further discussion
2 |  |  | IT-CR-100719-654 | Add button 'Edit' in menu Monitoring Document to update Insurance Data (Insco, Policy Number, Start Date & End Date). => will affect with the new CR | Needs Legal Opinion; can be dropped if DSF create SOP regarding policy of insurance. Risk of manual: human error (can be skipped) | Lestaryono
3 |  |  | 'IT-CFR-250919-734 #35976 | Activate Module "Manage Warning Letter" | Low Priority - Do manually | Olivia Setiawan
4 |  |  | IT-CFR-071019-750 #36566 | Additional Field 'Police Number' in Billing Print Out | Needs Legal Opinion, based on PSAK 73 which will be valid on Jan 2020, there are some asset information that cannot be written openly, such as police number | Astuti Dewi
5 |  |  |  | Calculation Outstanding Net Investment in SKD | Needs CR Form | Herni Hembang
6 |  |  |  | Change Formula Selling Price for Auction in Asset Selling Module (layout) | Needs CR Form | Antonius Fedrik
7 |  |  |  | Additional Information for Email Notification STNK & KEUR | Needs CR Form | Pathul Wadi
8 |  |  |  | Change Progress Status in Monitoring Document Complement |  | Pathul Wadi
9 |  |  |  | Change Role 'Suwardi Gunawan' from acknowledger to approver in report Asset Selling & Payment Approval |  | Antonius Fedrik
10 |  |  |  | Agreement from Migration showing "No Registration" because the data is not complete |  | Pathul Wadi
EFFORT (REQUIREMENT, DESIGN, DEVELOPMENT, SIT)
| BIG CR | > 20 MD
| MEDIUM CR | 11 - 20 MD
| SMALL CR | <= 10 MD

## CR CLOSED
No | Service # | Change # | Ticket DSF ITD | Title | Status | Requestor | Actual Release Date
1 | X0097536 | C0017795 | IT/CFR/14-11-2016/177 | Currently calculation in SKD Formula are incorrect, changes are mad in several fields. | Done | DSF | 2016-12-22
2 | X0098512 | C0017792 | IT/CFR/06-11-2016/207 Currently Basic Premium and Total Gross Premium shared the same value. Total Gross value should have been the total of all insurance fees. | Currently Basic Premium and Total Gross Premium shared the same value. Total Gross value should have been the total of all insurance fees. | Done | DSF | 2016-12-22
3 | S0098385 | C0017622 | IT/CFR/25-11-2016/196 Adding Validation Script Produc Registration Code | Adding Validation Script Produc Registration Code | Done | DSF | 2017-01-20
4 | X0098667 | C0018047 | IT/CFR/17-01-2017/013 1. Change logic in Monitoring Complement document screen. 2. Change Status List of STNK | 1. Change logic in Monitoring Complement document screen. 2. Change Status List of STNK | Done | DSF | 2017-02-01
5 | X0102023 | C0018323 | IT/CFR/03-03-2017/059 Item Monitoring Document (STNK, KEUR, Insurance Policy) can not save when user update. | Item Monitoring Document (STNK, KEUR, Insurance Policy) can not save when user update. | Done | DSF | 2017-02-02
6 | S0104525 S0104410 | (no change of source code) | IT/CFR/15-03-2017/074 Change approver for HOD and Director | Change approver for HOD and Director | Done | DSF | 2017-03-22
7 | X0103966 | C0018782 | xxx | Error when create BAST replacement car. URL not redirect to the correct path. | Done | DSF | 2017-03-30
8 | S0104524 | C0019039 | IT/CFR/06-03-2017/060 Change doc signer in Invoice and Kwitansi. | Change doc signer in Invoice and Kwitansi. | Done | DSF | 2017-04-03
9 | S0107506 | C0019682 | IT/CFR/12-04-2017/110 STNK KEUR for over 60 days. | STNK KEUR for over 60 days. | Done | DSF | 2017-06-05
10 | S0107716 | C0019537 | IT/CFR/04-05-2017/133 Logic for Paging in Grid and Sorting by Date | Logic for Paging in Grid and Sorting by Date | Done | DSF | 2017-06-07
11 | S0107780 | C0019994 | IT/CFR/08-05-2017/137 CR View Invoice (7 days) | CR View Invoice (7 days) | Done | DSF | 2017-06-12
12 | S0113433 | C0021266 | IT/CFR/21-07-2017/218 Perbaikan logic join Police Number and PoliceNumberAct pada Tb_OPL_Unit. | Perbaikan logic join Police Number and PoliceNumberAct pada Tb_OPL_Unit. | Done | DSF | 2017-10-18
13 | S0113432 | (not yet created) | IT/CFR/21-07-2017/214 Perbaikan logic pembentukan SKDNo pada SKD Net Investment dan SKD History. | Perbaikan logic pembentukan SKDNo pada SKD Net Investment dan SKD History. | Cancelled | DSF | -
14 | S0113430 | C0021133 | IT/CFR/21-07-2017/217 Perbaikan logic pembentukan DSF Office pada saat proses PO. | Perbaikan logic pembentukan DSF Office pada saat proses PO. | Done | DSF | 2017-11-20
15 | S0114933 | C0021081 | IT/CFR/18-08-2017/251 Being requested to change the signature approval doc of SKD (CR 251). | Being requested to change the signature approval doc of SKD (CR 251). | Done | DSF | 2017-11-20
16 | S0113431 | C0021121 | IT/CFR/21-07-2017/216 Ubah logic IsDelete pada database OLSS untuk modul SKD. | Ubah logic IsDelete pada database OLSS untuk modul SKD. | Done | DSF | 2017-11-30
17 | S0113506 | C0021419 | IT/CFR/27-07-2017/224 Penambahan data Customer Name, Product Type, Agreement Number, dan Chasis Number di Monitoring Complement Document OLSS STNK dan KEUR. | Penambahan data Customer Name, Product Type, Agreement Number, dan Chasis Number di Monitoring Complement Document OLSS STNK dan KEUR. | Done | DSF | 2017-12-12
18 | S0113435 | C0021120 | IT/CFR/21-07-2017/215 Disable tombol Submit dan Save as Final untuk modul SKD dan Unit Preparation Management. | Disable tombol Submit dan Save as Final untuk modul SKD dan Unit Preparation Management. | Done | DSF | 2017-12-15
19 | S0124547 | C0022726 | IT/CFR/15-12-2017/136 Change bank name in invoice | Change bank name in invoice | Done | DSF | 2018-01-23
20 | S0130618 | C0022861 C0022862 | IT-CR-270418-269 (#10366) VAT In update and Invoice Date update for reduce Data Maintenance. | VAT In update and Invoice Date update for reduce Data Maintenance. | Done | DSF | 2018-04-04
21 | S0130969 | C0022872 | IT/CFR/09-03-2018/217 Fix Start Period OLSS | Fix Start Period OLSS | Done | DSF | 2018-04-19
22 | S0133382 | C0022925 | IT-IR-160418-85 (9894) Total Monthly Installment formula incorrent. Permanent solution of X0132903 | Total Monthly Installment formula incorrent. Permanent solution of X0132903 | Done | DSF | 2018-04-19
23 | X0135125 | C0022942 | xxx Check OLSS Account Issue | Check OLSS Account Issue | Done | DSF | 2018-05-15
24 | X0135323 | C0022948 | xxx Approval Asset Selling Missing | Approval Asset Selling Missing | Done | DSF | 2018-05-18
25 | X0135335 | C0022950 | xxx Cannot input payment on OLSS | Cannot input payment on OLSS | Done | DSF | 2018-05-18
26 | X0136075 | C0022967 | xxx Check Input Supplier Data Issue | Check Input Supplier Data Issue | Done | DSF | 2018-05-28
27 | X0135884 | C0022957 | xxx Check Input Customer Data Issue | Check Input Customer Data Issue | Done | DSF | 2018-05-23
28 | S0134772 | C0022929 | IT/CFR/020518/271 (#10317) Update Work Order in Submit on System OLSS | Update Work Order in Submit on System OLSS | Done | DSF | 2018-06-06
29 | - | - | xxx Change Penalty Rate logic OLSS | Change Penalty Rate logic OLSS | Cancelled | DSF | -
30 | S0136838 | C0020905 | xxx Add New Function to Validate Tax Invoice Number | Add New Function to Validate Tax Invoice Number | Cancelled | DSF | -
31 | S0136839 | C0020976 | xxx Accommodate MFAPPL Debit Note Credit Note feature (Contract Extension) | Accommodate MFAPPL Debit Note Credit Note feature (Contract Extension) | Cancelled | DSF | -
32 | X0138896 | C0020977 | xxx Being reported that error BAST final. | Being reported that error BAST final. | Done | DSF | 2018-07-17
33 | S0136129 | C0021097 | IT/IRF/070618/92 (#11904) Permanent Fix Attachment Memo Auction 'lelang ke' | Permanent Fix Attachment Memo Auction 'lelang ke' | Done | DSF | 2018-07-31
34 | X0140042 | C0020983 | xxx Double Asset Code, selling price 0, wrong payment date, and wrong profit analysis result | Double Asset Code, selling price 0, wrong payment date, and wrong profit analysis result | Done | DSF | 2018-07-05
35 | S0142359 | C0022697 | xxx Search Work Order in Maintenance Payment Approval Problem | Search Work Order in Maintenance Payment Approval Problem | Done | DSF | 2018-08-28
36 | S0142269 | C0021819 | xxx Go Live Integration OLSS Phase 3 & 4 | Go Live Integration OLSS Phase 3 & 4 | Done | DSF | 2018-08-24
37 | S0142483 | C0021645 | xxx Adding Search Criteria and Column Name Correction | Adding Search Criteria and Column Name Correction | Done | DSF | 2018-08-29
38 | S0143474 | C0021645 | xxx Check cannot Save Payment Approval | Check cannot Save Payment Approval | Done | DSF | 2018-09-13
39 | S0143475 | C0022582 | xxx Adding Search Criteria Invoice Number in Manage Invoice | Adding Search Criteria Invoice Number in Manage Invoice | Done | DSF | 2018-09-13
40 | P0142612 | C0022691 | xxx Tuning lookup WO Number Payment Approval | Tuning lookup WO Number Payment Approval | Done | DSF | 2018-08-31
41 | X0142627 | C0022692 | xxx Formula Payment Approval Bug Fixing | Formula Payment Approval Bug Fixing | Done | DSF | 2018-08-31
42 | X0142628 | C0022727 | xxx Disable Create Invoice Bug Fixing | Disable Create Invoice Bug Fixing | Done | DSF | 2018-08-31
43 | S0143857 | C0022729 | xxx Error OPL Expense Template | Error OPL Expense Template | Done | DSF | 2018-09-21
44 | S0144348 | C0022746 | xxx Deploy Fixing Issue for Book Value & Gainloss | Deploy Fixing Issue for Book Value & Gainloss | Done | DSF | 2018-09-25
45 | X0146798 | C0022788 | xxx Profit Analysis and Report Investment Difference Fix | Profit Analysis and Report Investment Difference Fix | Done | DSF | 2018-10-24
46 | X0148297 | C0022799 | xxx Maintenance Amount Calculation OLSS Failure | Maintenance Amount Calculation OLSS Failure | Done | DSF | 2018-11-08
47 | X0147380 | C0022809 | xxx Difference Unit Value | Difference Unit Value | Done | DSF | 2018-11-16
48 | X0147382 | C0022845 | xxx Difference Value Between Screen and Print Out | Difference Value Between Screen and Print Out | Done | DSF | 2018-11-16
49 | X0147383 | C0022821 | xxx Difference Unit Value in Print Out | Difference Unit Value in Print Out | Done | DSF | 2018-11-16
50 | X0147384 | C0022847 | xxx Check Error in BAST Replacement Car B 1919 PRL | Check Error in BAST Replacement Car B 1919 PRL | Done | DSF | 2018-11-22
51 | X0149487 | C0022857 | xxx Cannot Change Asset Status | Cannot Change Asset Status | Done | DSF | 2018-11-27
52 | S0150756 | C0022887 | xxx Check Cannot Synchronize Customer Data from ACA | Check Cannot Synchronize Customer Data from ACA | Done | DSF | 2018-12-14
53 | S0151021 | C0022860 | IT/DM/211118 (#2468) Change label setting in Print WO | Change label setting in Print WO | Done | DSF | 2018-12-26
54 | S0154061 | C0022888 | xxx Re-deploy Ticket S0130969 CR Start Period Logic | Re-deploy Ticket S0130969 CR Start Period Logic | Done | DSF | 2019-01-27
55 | X0154690 | C0022889 | xxx | Fix Error Monitoring Complement Document | Done | DSF | 2019-01-30
56 | S0145394 | C0022974 | CR New OLSS Calculation Method | CR New OLSS Calculation Method | Done | DSF | 2019-02-07
57 | X0155132 | C0022975 | xxx Print Report Historical Maintenance Error | Print Report Historical Maintenance Error | Done | DSF | 2019-02-04
58 | X0154920 | C0022992 | xxx Asset Selection Error | Asset Selection Error | Done | DSF | 2019-02-06
59 | X0155443 | C0022998 | xxx Error Monitoring Complement Document | Error Monitoring Complement Document | Done | DSF | 2019-02-07
60 | X0155758 | C0022997 | xxx Cannot Print WO | Cannot Print WO | Done | DSF | 2019-02-12
61 | X0155883 | C0022988 | xxx OLSS Calculation Save Error | OLSS Calculation Save Error | Done | DSF | 2019-02-12
62 | X0156617 | C0023011 | xxx Wrong Monthly Installment | Wrong Monthly Installment | Done | DSF | 2019-02-19
63 | X0157000 | C0023058 | xxx Error Value RV and Monthly Installment in Calculation, Quotation, and SKD | Error Value RV and Monthly Installment in Calculation, Quotation, and SKD | Done | DSF | 2019-02-25
64 | S0128476 | C0023056 | IT/CFR/09-02-2018/186 Change logic Last Service Date for maintenance Work Order | Change logic Last Service Date for maintenance Work Order | Done | DSF | 2019-03-11
65 | S0159159 | C0023069 | xxx Double asset in asset selling | Double asset in asset selling | Done | DSF | 2019-03-19
66 | S0159303 | C0023095 | xxx Check Difference Value Monthly Installment | Check Difference Value Monthly Installment | Done | DSF | 2019-03-20
67 | X0158508 | C0023090 | xxx Double Data Code Asset in Based Price Information | Double Data Code Asset in Based Price Information | Done | DSF | 2019-03-12
68 | P0158917 | C0022728 | xxx Fix report Asset Selling | Fix report Asset Selling | Done | DSF | 2019-03-15
69 | S0158832 | C0023135 | xxx fix Agreement 247/4/01 cannot update KEUR | fix Agreement 247/4/01 cannot update KEUR | Done | DSF | 2019-03-15
70 | S0159132 | C0023155 | xxx Error in Manage Report Menu Memo 00034/AUC/02/2019 | Error in Manage Report Menu Memo 00034/AUC/02/2019 | Done | DSF | 2019-03-19
71 | X0156317 | C0022969 | xxx Set to Draft old Calculation wrong value impact from new Calculation | Set to Draft old Calculation wrong value impact from new Calculation | Done | DSF | 2019-03-11
72 | X0157894 | C0020484 | xxx Cannot do Payment Receive | Cannot do Payment Receive | Done | DSF | 2019-03-05
73 | X0157737 | C0023188 | xxx Fix Value in Proposal Calculation | Fix Value in Proposal Calculation | Done | DSF | 2019-03-04
74 | P0160179 | C0023029 | xxx Set to Draft Problem Ticket | Set to Draft Problem Ticket | Done | DSF | 2019-03-28
75 | X0160186 | C0023331 | xxx Check Different Value Monthly Installment | Check Different Value Monthly Installment | Done | DSF | 2019-03-28
76 | S0159919 | C0022979 | IT/CFR/140319-555 (#26828) Changes in New Calculation Formula | Changes in New Calculation Formula | Done | Herni Hembang | 2019-04-30
77 | S0154339 | C0023277 | IT/CFR/220119-508 (#23562) Add Address Detail in Menu Supplier Data | Add Address Detail in Menu Supplier Data | Done | Pathul Wadi | 2019-04-02
78 | S0134076 | C0023345 | IT/CFR/250418/263 (#10268) Provide New Field in OLSS (Add PO Date) | Provide New Field in OLSS (Add PO Date) | Done | Herni Hembang | 2019-04-30
79 | X0162820 | C0023381 | xxx | Wrong ROA Value | Done | Herni Hembang | 2019-04-26
80 | S0134599 | C0023465 | IT-CR-210518-295 (#11292) | Change BAST Logic of Storing OPL Unit | Done | Junaidi Didy | 2019-05-07
81 | X0163002 | C0023637 | xxx | Fix Monthly Installment Difference | Done | Herni Hembang | 2019-05-10
82 | X0164814 | C0023642 | xxx | Basic Premium Difference | Done | Herni Hembang | 2019-05-15
83 | X0164915 | C0023644 | xxx | Monthly Installment Difference | Done | Herni Hembang | 2019-05-15
84 | S0164916 | C0023645 | xxx | SKD Price List | Done | Herni Hembang | 2019-05-15
85 | S0128471 | C0022825 | IT/CFR/02-02-2018/179 | Add Option Responsibility Party | Cancelled | Herni Hembang | 2019-05-21
86 | S0166468 | C0023672 | xxx | Data Buyer Double | Done | Antonius Fedrik | 2019-06-10
87 | S0161446 | C0023621 | IT-CR-080419-571 (#27937) | Change Mapping Customer Name | Done | Herni Hembang | 2019-07-23
88 | X0170885 | C0023755 | xxx | Fixing NPWP format and Address, Fixing Customer Address Mapping, and Fixing Business Economy Sector Mapping | Done | Herni Hembang | 2019-07-23
89 | S0147211 | C0023243 | CR with RFC | Print Dynamic Agreement | Cancelled | Herni Hembang | 2019-08-06
90 | S0171524 | C0023798 | IT-CR-200519-610 | Create Email Notification for temporary solution of Enhancement in Management Module (S0169246) | Done | Pathul Wadi | 2019-08-23
91 | S0171480 | C0023838 | IT-CR-230719-665 | Add new column for Supplier Address in Maintenance Payment Approval & Supplier Information. | Done | Fahmi Afandi | 2019-09-16
92 | S0132095 | C0022919 | IT/CFR/15-02-2018/194 | Remove rounding logic for VAT in Calculation & SKD. | Cancelled | Hasan Nurdin (OPL)
93 | S0126984 | C0023076 | IT-CR-120619-625 | Requested to give permanent solution for CR Maintenance Calculation Budget (Generate Yearly Number Automatically). | Done | Junaidi Didy (OPL) | 2019-10-08
94 | S0147213 | C0023245 | CR with RFC | Cancellation SKD & Agreement Part 1 | Done with no deployment | Herni Hembang (OPL) | 2019-10-03
95 | S0137870 | C0023077 | IT-CR-310518-307 (#11615) | Request to change logic of Agreement Numbering (Related to Project Phase 3&4 Data Cleansing) | Cancelled | Herni Hembang (OPL)
96 | S0137795 | C0023003 | IT-CR-210618-330 (#12184) | Add new function Print Detail Invoice Penagihan Maintenenance Kendaraan (Related to Project Phase 3&4) | Cancelled | Olivia Setiawan (OPL)
97 | S0164989 | C0023674 | IT-CR-140519-602 (#29534) | Automatic Sync ACA to OLSS | Done | Herni Hembang (OPL) | 2019-10-11
98 | S0143140 | C0023190 | IT-CR-250418-264 (#10269) | Change Approval SKD in OLSS | Done with no deployment | Herni Hembang (OPL) | 2019-10-29
99 | S0164404 |  |  | Overdue Migration OLSS | Done | Raymond Tan | 2019-09-26
100 | S0169552 | C0023822 | IT-CR-210619-638 | Change SKD Approval Scheme | Done | Herni Hembang (OPL) | 2019-11-12
101 | S0165486 | C0023661 | IT-CR-070519-593 (#29066) | Change Print Invoice Template Tanda Terima Doc | Done | Astuti Dewi (OPL) | 2019-11-19
102 | S0179754 |  | IT-CR-250919-731 (#35969) | Automatic Sync MFAPPL to OLSS | Done | Olivia Setiawan (OPL) | 2019-11-29

## Summary CR CLOSED (hidden)
Actual Release Date | (Multiple Items)
Row Labels | Count of Status
Cancelled
S0128471 | 1
Cancelled Total | 1
Done
S0134599 | 1
S0164916 | 1
X0163002 | 1
X0164814 | 1
X0164915 | 1
Done Total | 5
Grand Total | 6

## ACA (only project) (hidden)
Progress CR-ACA Production as of 18 Aug 2017
[10 empty] | 2016 | 2017 | [11 empty] | 2018
No | Service # | Change # | Ticket DSF ITD | Title | Status | Requestor | Priority | Remarks |  | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN
1 | (not yet created) | (not yet created) | (not coming yet) | Interface ACA MFAPPL related to impact of DRC analysis. | Open | Ahmad Fikri | 6 | Request from user. Impact of DRC impact analysis. | Plan
Actual
2 | S0111790 | C0020458 | IT/CFR/16-06-17/192 | Grace period in installment calculation | On progress | Ahmad Fikri | 4 | Request from user | Plan
Actual
3 | S0109013 | C0019820 | IT/CFR/05-05-15/56 | KYC report and Run ACA validation | Development preparation | Ahmad Fikri | 10 | Request from user | Plan
Actual
4 | S0107522 | (not yet created) | (not request to ITD yet) | Automatic update Sector Econ before generate LBPP | Open | Christina (BSI) | 8 | Requested by CONFINS team | Plan
Actual
5 | (not yet created) | (not yet created) | (not yet created) | SLIK | Open | Kartini | 13 | Request from user. OJK regulation. | Plan
Actual
Legend
Preparation
|  |  |  | Development & UAT Prep | (if duration less than 1 week, just put this colour)
|  |  |  | SIT&UAT | (if duration less than 2 week, 1st week for development, 2nd week for SIT&UAT)
Deployment
Will be handled by "project"
Assessment for SLIK can be conducted here
|  |  | Total | 5
|  |  | Close CR = | 0
|  |  | Open CR = | 5
This sheet is coming from "ACA" sheet, but only for items that will be hadled by project team (new member of ACA team)
On 18 Aug 2017, this sheet move back to "ACA" sheet as requested by Mr. Fikri. It placed below table of regulaar table. See "ACA" sheet.
Note on H4: bsi00304: updated on 26 July 2017
Note on AR5: bsi00304: will be developed by other resource (outsource)
Note on AH10: bsi00304: requirement gathering done on 29 May 2017.

## To Do Item
No | Item | Status | PIC | Due date | Remarks | Create in this list
1 | Plan Deploy S0134599 Change BAST Logic | Closed | Neny | W1 May | Deployment Done
2 | Analyze Ticket S0128471 Add Option Responsibility Party, possibility this ticket will be closed | Closed | Neny | W1 May | Close ticket based on CR already done in project phase 3&4
3 | Plan Deploy S0147213 Cancel SKD & Agreement | UAT In Progress | Herni Hembang | TBD | Currently waiting for Bu Herni to conduct UAT with additional scenario (reminder sent on 29 May 2019 & 12 June 2019) then merging source code to OLSS QA and re-UAT (internal by BSI) before deploy to OLSS Prod. On 14 June 2019, Bu Herni ask additional requirement to reduce approval level ( from 8 users to 2 users). And will conduct UAT after those requirement is fulfilled (S0167113). Approval level is changed on 18 June 2019, still waiting for user feedback. Because there will be potential CR regarding approval signer label on SKD doc. printing.
4 | Plan Deploy S0147214 Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | UAT script in progress | Neny | W3 Jun | Info from user (Pak Anton) by email on 12 June 2019: Dear Bu Neny Saya tidak memilik dokumen tersebut bu, Dan menurut saya case ini sudah done, karena sudah terakomodir dalam project asset selling yg sudah berjalan saat ini. Terimakasih. Notes: - BSI tetap akan melakukan pembuatan UAT script untuk CR ini berdasarkan RFC dan email-email terkait. - Tanggal 25 Juni 2019 eskalasi ke PakTirta dan Pak Verdian terkait UAT script yang membutuhkan konfirmasi dari Pak Anton.
5 | Remind Mr. Teddy, Mr. Gilang for CR OLSS continuity | Closed | Raymond | W3 May | Reminder sent 22 May 2019
6 | Set Meeting with Mr. Eddy and Mr. Achmad for Overdue Migration Production Problem | Closed | Raymond | W3 May (Wed/Thur) | Invitation sent 22 May 2019
7 | Request logic enhancement in OLSS for Calculation and SKD | Hold | Neny | TBD | User (Bu Herni) confirmed to HOLD on 22 May 2019 (via email).
8 | Ada 6 tiket open di redmine. | Closed | Neny & Kenneth | W2 Jun | Already informed to Kenneth for each CR status.
9 | Disable Model Code yg lama di OLSS agar sama dengan Model Code yg ada di confins dan BI. | Open | Neny & Kenneth | TBD | Waiting for further discussion with BI Team. Already registered in Redmine #31556 and CMDB S0168840
10 | Print Dynamic Agreement | Hold | DSF | TBD | Hold di meeting OLS Operation 25 Jun 2019 (Raymond Tan & Pak Tirta) karena requirement dirasa sudah tidak relevan dengan operasional di cabang. Informasi ini akan disampaikan di dalam MOM. Meeting result on 2 Jul 2019: - BSI request to cancel but DSF will consider whether cancel or not. - DSF ask to change requirement. - Pak Tirta request blank template which listed in RFC. Meeting result on 6 Aug 2019: CR Print Dynamic Agreement is cancelled.
11 | CR for Invoice TOP Based on Invoice Receipt Date | Open | DSF | TBD | Possible request to enhance TOP Invoice operational.
12 | Request logic enhancement in OLSS for Calculation and SKD | Closed | DSF | W2 Jul | Ask Bu Herni whether cancel or not.
13 | Issue berulang: amount invoice berbeda dengan amount installment | Closed | BSI | W2 Jul | Ask Pak Firmansyah about detail issue.
14 | Quotation Used as PO | Closed | DSF | W2 Jul | Status is cancelled based on meeting with Pak Irma Ferdian & Pak Tirta (2 July 2019)
15 | Untuk CR Monitoring Document STNK, alternative solution (workaround) dari Pak Tirta: - Buatkan scheduler yg bisa men-generate report tsb dgn kondisi: STNK dgn due date <= 45 hari dikeluarkan datanya (raw data dalam bentuk excel file) | Closed | BSI | W4 Jul | Ask Pak Firmansyah & Pak Sobari related possibility to generate raw data by scheduler. Update on 16 Jul 2019: - Already confirmed to Pak Joko related detail requirement.
16 | Assessment for new requirement of Print Dynamic Agreement | Closed | BSI | W4 Jul | Paralelly, ITD will prepare CR Form & BSI will inform to BRM related new changes.
17 | Sobari and Neny testing Invoice (incident) | Closed | BSI | 2019-07-11 | Already deployed to OLSS Production at 11 July 2019.
18 | Request logic enhancement in OLSS for Calculation and SKD is cancelled based on user confirmation (Bu Herni). | Closed | BSI | W3 Jul | Email from BU Herni (Fri 7/12/2019 2:54 PM): Dear Bu Neny, Terkait service request Request S0136137 : logic enhancement in OLSS for Calculation and SKD tidak dilanjutkan (dicancel) karena sudah diakomodir pada calculation yang digunakan saat ini. Terimakasih. Regards, Herni
19 | Discuss with Raymond Tan related CR Form for ticket change 'Email Notification' (temporary solution of CR Enhancement in Management Module). | Closed | BSI | W4 Jul | Ada tambahan notes di CR Form Enhancement Management Module).
20 | Buat ulang screnario untuk Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | Open | BSI | TBD
21 | User UAT Automatic Sync consider to change from Bu Herni to … | Open | BSI | W2 Sep | Ask Raymond Tan to define the user.

## Issue Log
No | Service # | Change # | Ticket DSF ITD | Title | Status | Log Issue | Date

## hist
2018
No | Service # | Change # | Ticket DSF ITD | Title | Status | Requestor | Priority | Remarks | PIC |  | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JUN | JUN | JUN | JUN | JUN | JUN | JUN | JUN | JUN
1 | S0128471 | C0022825 | IT/CFR/02-02-2018/179 | Add Option Responsibility Party | Cancelled | Herni Hembang (OPL) |  | Request from user | NENY | Plan
[9 empty] | FIRMANSYAH | Actual
2 | S0147211 | C0023243 | CR with RFC | Print Dynamic Agreement | Cancelled | Herni Hembang (OPL) |  | Request from user | NENY | Plan
[9 empty] | FIRMANSYAH | Actual
Note on H2: bsi00304: updated on 26 July 2017

## requirement
S0147214 | C0023246 | CR with RFC | Changing Report Asset Selling Report Method and Sending Data to MFAPPL Method | SIT | Antonius Fedrik (OPL) | - Menambahkan total di payment receive tab untuk kolom net received & balance
- 1 report bisa terdiri dari lebih dari 1 memo
- harga di kolom auction & DSF offered price dapat di copy paste saat create memo pengajuan
- minta ditambahkan informasi nomor mesin dan rangka saat create memo pengajuan
S0169553 |  | IT-CR-280619-642 | PJB (Perjanjian Jual Beli) for OLSS Menu Asset Selling | Open | Antonius Fedrik (OPL) | - Menambahkan print out untuk Perjanjian Jual Beli, di mana sudah ada template nya, tinggal ditambahkan beberapa informasi dari memo yang sudah approved (seperti nama buyer, alamat buyer, dll) serta informasi unit nya
S0171701 |  | IT-CR-080719-649 | Additional field in column 'Budget' and 'Actual' based on Number of Unit in Lampiran Investasi in menu Asset Selling (Manage Memo/View Profit Analysis). | Open | Antonius Fedrik (OPL) | - Menambahkan kolom quantity unit pada profit analysis yang memunculkan total unit pada agreement. Jika quantity unit tersebut dirubah, maka nilai pada kolom budget dan actual akan prorate sesuai dengan quantity nya.
S0169246 |  | IT-CR-200519-610 | Enhancement in Management Module (Additional Information for Periode Kontrak, Progress Status dan Registration Status). | Open | Pathul Wadi (OPL) | - Menambahkan menu untuk input keterangan budget untuk registrasi, field untuk input biaya yang terkait dengan jasa STNK, KEUR, biaya ijin bongkar muat barang, dll.
S0174451 |  | IT-CFR-170719-661 #32392 | Enhance management module with additional field and column. | Open | Pathul Wadi (OPL) | - Menambahkan modul untuk enhance modul management sesuai excel yang diberikan user

## KBIJ SLIK (hidden)
draft
No | Activity | PIC | 2017 |  |  |  | 2018 |  |  | Note
|  |  | OCT |  | NOV | DEC | JAN | FEB | MAR
CR SLIK + KBIJ
ACA System
1 | ACA - Workshop and Assessment ACA | Neny
+ Create data mapping
+ CR Requirement ( create CR Form)
2 | ACA- Develop B to B KBIJ | PG3
3 | ACA - CR Development ( including Testing) | Neny, PG1
+ Update database ACA Structure
+ Update UI ACA
4 | ACA - CR Interfacing Development | Neny, PG1 | [7 empty] | sending data from ACA to confins & MFappl
5 | ACA - Data Cleansing | PG2 | [7 empty] | prepare datascript update, vaildate data
6 | ACA - UAT | Neny, PG1
CONFINS System
1 | Confins - Workshop and Assessment ACA | AdIns | [7 empty] | free - no cost
+ Create proposal CR SLIK
2 | Confins - CR Development ( including Testing) | AdIns | [7 empty] | free - no cost
+ Update database Confins Structure
+ Update Confins UI
3 | Confins - CR Interfacing Development | Devi | [7 empty] | sending data from Cofins to ACA & MFappl cost will be taken from Adins voucher
4 | Confins - Data Cleansing | Devi, PG2 | [7 empty] | get data structure first from Adins
5 | Confins - UAT | Devi
6 | SLIK Go Live & Post Go Live | Devi,Neny,PG1 | [7 empty] | if any operation cost impact will be consider
in current ACA & Confins Service
PG1
PG2
PG3