## Analisa
OpLease CR (request from Mr. Somad)
▪ Modify interface & minor logic
▪ Re-layout all report (html)
|  | ▪ Modify Billing Payment |  | User using OpLease (Phase #1 code)
OpLease code
Phase #1 | OpLease CR |  | Workshop OpLease | Development
| ▪ Data Historical |  | Phase #2 | OpLease Phase #2
| ▪ User Role Management |  |  | ▪ Billing Payment
▪ Report Framework
● Report
At this time OpLease CR will make a report framework as a foundation of report module on Development OpLease Phase # 2.
One of the functions of the report framework is to export reports into excel file, pdf, and html.
The problem is the making of the report layout will be done two times, at OpLease CR - Report Framework and OpLease CR request from Mr. Somad
● Billing Payment
In the current system, Billing payment only serves to record history so that no payment transactions.
Billing payment transactions will be done on Development OpLease Phase #2, but Mr. Somad asked to modify billing payment in order to conduct payment transactions.
The problem is the making of the billing payment transactions module will be done two times, OpLease CR request from Mr. Somad and Development OpLease Phase #2
Current System
Next System

## FINAL
SUMMARY TEST TANGGAL 18 - 21 MEI 2015
No | Module Name | Test Result (Current Condition) |  |  | Proposal to Solve Problem |  | Manhours Estimation | [5 empty] | Remarks | PIC role | PIC name (BSI) | PIC name (DSF) | PIC name | 2015-06-01 | [15 empty] | 2015-07-01
|  | No | Detail | Lampiran | No | Detail | Development | Update Doc. | UAT/SIT Script | Unit Test | UAT | Bug Fixing | [5 empty] | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Update document related to 1. Calculation OPL 2. Create New Agreement |  |  |  |  | Update document related to 1. Calculation OPL 2. Create New Agreement | 6 | [6 empty] | BA | Setiyono | (N/A) | bar: 2015-06-01 18
2 | UAT script creation for all case |  |  |  |  | UAT script creation for all case | 8 | [6 empty] | BA | Setiyono | (N/A) | bar: 2015-06-01 19
3 | Calculation OPL Step 1 | 1 | [End Date Usage Unit Plan] filled manually | 1 | 1.a | [End Date Usage Unit Plan] will be filled automatically by system based on lease period | 2.5 | 6 | 8 | 2 | 2 | 16 | Terdapat logic untuk menghitung end period date | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 2 | [Lease Period Plan] filled automatically |  | 2.a | [Lease Period Plan] will be filled manually to determine value of [End Date Usage Unit Plan] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
4 | Calculation OPL Step 3 | 1 | Value of [Lease Period] | 2 | 1.a | It will be filled automatically by system based on value of lease period on Calculation OPL Step 1 | 1.5 | [5 empty] | Terdapat logic untuk mengubah info budget | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 2 | Value of Maintenance Condition and Cost |  | 2.a | Value of [Total Maintenance Cost] is total budget during the period of lease | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
5 | Calculation OPL Step 4 | 1 | Value of [Mediator Fee Amount] filled automatically based on value of [Commission Amount], and un-editable | 3 | 1.a | [Mediator Fee Amount] will be filled manually | 1 | [5 empty] | Terdapat logic untuk menampilkan mediator fee | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
[5 empty] | 1.b | Value of [Mediator Fee Amount] < value of [Commission Amount] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
[5 empty] | 1.c | Utilize master tabel to determine value of [Mediator Fee Amount] (Next Development) | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
6 | Calculation OPL Step 5 | 1 | Value of [Lease Period] | 4 | 1.a | It will be filled automatically by system based on value of lease period on Calculation OPL Step 1 | 4 | [5 empty] | Sudah di handle pada perbaikan OPLCalculation Step 1 | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 2 | [Rate Insurances Income] field currently is disable |  | 2.a | Enable [Rate Insurances Income] field and set value same with [Commission Amount] rate | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 3 | [Interest Income] field currently is disable |  | 3.a | Enable [Interest Income] field and set value based on formula in Excel file | [6 empty] | Terdapat logic untuk menghitung interest income pada formula kalkulasi | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 4 | [Insurances Discount] field |  | 4.a | Remove [Insurances Discount] field from screen, because It isn't part of cost | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
[5 empty] | 4.b | Remove [Insurances Discount] component to calculate [Total Cost] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 5 | [Total Profit] label |  | 5.a | Change label of [Total Profit] to [Total Installment] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 6 | Value of [Insurances Income] |  | 6.a | Add label and value of [Insurances Income] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 7 | Value of [Total Income] |  | 7.a | Add label and value of [Total Income]. It will be filled automatically with formula [Total Income] = [Total Installment] + [Insurances income] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
[14 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
|  | 8 | Value of [Total Income After Lease Cost] |  | 8.a | Add label and value of [Total Income After Lease Cost]. It will be filled automatically with formula [Total Income After Lease Cost] = [Total Income - Total Cost] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
[14 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 19
8 | Unit test for Calculation step 1 - 5 | 9 |  |  |  | Unit test for Calculation step 1 - 5 | 3 | [6 empty] | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-06-01 22; 2015-06-01 24
9 | Create New Agreement | 1 | Value of [BAST Date] and [Start Date Usage] | 8 | 1.a | Value of [BAST Date] can be same with [Start Date Usage Unit] | 7.5 |  |  | 1 | 1 |  |  | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 2 | Value of [End Date Usage Unit] |  | 2.a | [End Date Usage Unit] will be filled automatically by system based on lease period | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 3 | Value of [Lease Period] |  | 3.a | It will be filled automatically by system based on value of lease period on Calculation OPL Step 1 | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 4 | Value of [First Due Date of Usage Unit] |  | 4.a | It will be filled automatically by system | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 5 | Value of [First Due Date of Payment] |  | 5.a | It will be filled automatically by system | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 6 | Value of [Number of Payment] |  | 6.a | It will be filled automatically by system | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 7 | Value of [Accessories] |  | 7.a | It will be filled automatically by system | [6 empty] | Terdapat logic untuk menampilkan info accessorie | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 8 | Value of [Carroserrie] |  | 8.a | It will be filled automatically by system | [6 empty] | Terdapat logic untuk menampilkan info carroserie | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 9 | Value of [STNK renewal] |  | 9.a | It will be filled automatically by system | [6 empty] | Terdapat logic untuk menampilkan info STNK renewal | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 10 | Value of [KEUR renewal] |  | 10.a | It will be filled automatically by system | [6 empty] | Terdapat logic untuk menampilkan info KEUR renewal | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
|  | 11 | Items of Add Unit (Object Lease) modal |  | 11.a | [Carroserrie] field and [Accessorrie] field will be separated | [6 empty] | Terdapat logic untuk input accessorie & carroserie secara terpisah. Perlu modifikasi database(tambah table) | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
[5 empty] | 11.b | Value of [Carroserrie] and [Accessorrie] will be filled automatically by system | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 23
10 | Unit test for Create New Agreement | 12 |  |  | 12 | Unit test for Create New Agreement | 2 | [6 empty] | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-06-01 24 to 2015-06-01 26; 2015-06-01 29
11 | Update document for 1. Service History Inquiry Detail 2. Billing Payment History | 9 |  |  |  | Update document for 1. Service History Inquiry Detail 2. Billing Payment History | 8 | [6 empty] | BA | Setiyono | (N/A) | bar: 2015-06-01 23 to 2015-06-01 25
12 | Service History Inquiry Detail | 1 | Workshop data |  | 1.a | Workshop data which appears in the list only the workshop with active status | 1.5 | 8 |  | 0.5 | 0.5 |  |  | PG | Dani | (N/A) | Dani | bar: 2015-06-01 25 to 2015-06-01 26
|  | 2 | Service detail |  | 1.a | Value of [PPN] will be filled manually | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 25 to 2015-06-01 26
[5 empty] | 1.b | Value of [PPh] will be filled manually | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 25 to 2015-06-01 26
|  | 3 | Value of [Maintenance Budget] |  | 3.a | Value of [Maintenance Budget] is total budget during the period of lease | [6 empty] | Terdapat logic untuk menampilkan informasi budget maintenance | PG | Dani | (N/A) | Dani | bar: 2015-06-01 25 to 2015-06-01 26
11 | Unit test for History Inquiry Detail | 4 |  |  |  | Unit test for History Inquiry Detail | 0.5 | [5 empty] | Terdapat logic untuk menampilkan informasi budget maintenance | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-06-01 26; 2015-06-01 29
12 | UAT execution for 1. Calculation step 1 - 5 2. Create New Agreement 3. Service History Inquiry Detail (include follow up feedback that raised during UAT) | 5 |  |  |  | UAT execution | 3.5 | [5 empty] | Terdapat logic untuk menampilkan informasi budget maintenance | BA | Setiyono | Deni K. | Setiyono | bar: 2015-06-01 29
13 | Billing Payment History | 1 | Value of [Expectation Collection Amount] included PPN and PPh | 9 | 1.a | Value of [Expectation Collection Amount] not included PPN and PPh | 24 |  |  | 8 | 8 |  | Terdapat proses: design add new table, layout interface, logic formula billing | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
|  | 2 | Value of [Billing Total] |  | 2.a | Change location of [Billing Total] field after [Expectation Collection Amount] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
[5 empty] | 2.b | Value of [Billing Total] not included PPN and PPh | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
|  | 3 | [Breakdown Total] field |  | 3.a | Add label and value of [Breakdown Total]. It will be filled automatically | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
|  | 4 | Value of [Overdue Amount] |  | 4.a | Value of [Overdue Amount] not included PPN and PPh, and included [Breakdown] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
|  | 5 | [Overdue PPN-PPh] field |  | 5.a | Add label and value of [Overdie PPN-PPh]. It will be filled automatically | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
|  | 6 | Penalty field |  | 6.a | Add label and value of [Expectation Penalty Collection Amount]. It will be filled automatically. | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
[6 empty] | [Expectation Penalty Collection Amount] = Total of penalty until today (follow date on server) | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
[5 empty] | 6.b | Add label and value of [Penalty Collection Amount]. It will be filled automatically. | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
[6 empty] | [Penalty Collection Amount] = Total of paid penalty until today (follow date on server) | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
[5 empty] | 6.c | Add label and value of [Overdue Penalty Amount]. It will be filled automatically. | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
[6 empty] | [Overdue Penalty Amount] = [Expectation Penalty Collection Amount] - [Penaly Collection Amount] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
|  | 7 | Change layout of Billing Payment History screen |  | 7.a | Change layout screen as attached file | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-06-01 30 to 2015-07-01 2
14 | Unit test for Billing Payment History | 8 |  |  |  | Unit test for Billing Payment History | 12 | [6 empty] | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-07-01 3; 2015-07-01 6 to 2015-07-01 7
16 | UAT execution for Billing Payment History (include follow up feedback that raised during UAT) | 10 |  |  |  | UAT execution for Billing Payment History | 8 | [6 empty] | BA | Setiyono | Deni K. | Setiyono | bar: 2015-07-01 7
17 | Update document for OPL report |  |  |  |  | Update document for OPL report | 2 | [6 empty] | BA | Setiyono | bar: 2015-07-01 2 to 2015-07-01 3; 2015-07-01 8
18 | Operating Lease Proposal Report | 1 | Layout Report | 5 | 1.a | Change layout report following sample | 8 | 2 |  | 0.5 | 0.5 |  | re-layout design report using html tagging | PG | Dani | (N/A) | Dani | bar: 2015-07-01 8
|  | 2 | Label and value of [Profit Amount] |  | 2.a | Change label and value of [Profit Amount] become [Total Income After Lease Cost]. Follow Calculation OPL Step 5 | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 8
[14 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 8
|  | 3 | Subject item is empty |  | 3.a | Add Subject item following sample | [6 empty] | development sudah di handle di 1.a | PG | Dani | (N/A) | Dani | bar: 2015-07-01 8
19 | Unit test for OpLease Proposal report | 4 |  |  |  | Unit test for OpLease Proposal report | 0.5 | [5 empty] | development sudah di handle di 1.a | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-07-01 9
20 | Operating Lease Calculation Attachment (report) | 1 | Layout Report | 6 | 1.a | Change layout report following sample | 8 |  |  | 0.5 | 0.5 |  | re-layout design report using html tagging | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
|  | 2 | Value of [Total Income] |  | 2.a | Value of [Total Income] = [Total Installment] + [Insurances Income] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
|  | 3 | [Adm Fee Income] item |  | 3.a | Remove [Adm Fee Income] item from screen | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
|  | 4 | [Overhead Fee] label |  | 4.a | Change label of [Overhead Fee] become [Lease Cost] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
|  | 5 | [Total Overhead Fee] label |  | 5.a | Change label of [Total Overhead Fee] become [Total Lease Cost] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
|  | 6 | [Income After Overhead Cost] item |  | 6.a | Change label of [Income After Overhead Cost] become [Income After Lease Cost] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
[5 empty] | 6.b | Value of [Income After Overhead Cost] = [Total Income] - [Total Lease Cost] | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 9
21 | Unit test for OpLease Calculation Attachment report | 7 |  |  | 7 | Unit test for OpLease Calculation Attachment report | 1.5 | [6 empty] | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-07-01 10
22 | Operating Lease Qoutation Report | 1 | [used car sales quotation] label | 7 | 1.a | Change label of [used car sales quotation] become [operating lease quotation] | 8 |  |  | 0.5 | 0.5 |  |  | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 2 | Layout Report |  | 2.a | Change layout report following sample | [6 empty] | re-layout design report using html tagging | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 3 | Checkbox less visible (gray) |  | 3.a | Change checkbox with color i.e blue | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 4 | Value of Insurance coverage |  | 4.a | The insurance coverage is the sum insured, not the value of premi | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
[5 empty] | 4.b | Nilai automobile sum insurared diisi dengan nilai pertanggungan basic premium | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
[5 empty] | 4.c | Add checkboc on insurance item | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 5 | Closing sentence on quotation |  | 5.a | Remove closing sentence on quotation | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 6 | Checkbox status on registration charges |  | 6.a | It will be filled automatically based on Calculation OPL Step 2 | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 7 | Date format (mm/dd/yyy) |  | 7.a | Remove label mm/dd/yyy on all report | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
[5 empty] | 7.b | Use date format dd-MMM-yyy | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
[5 empty] | 7.c | Change checkbox with color i.e blue | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
|  | 8 | Remark item on Insurance |  | 8.a | Add remark information on Insurance | [7 empty] | PG | Dani | (N/A) | Dani | bar: 2015-07-01 10
23 | Unit test for OpLease Quotation report |  |  |  |  | Unit test for OpLease Quotation report | 2.5 | [6 empty] | PG | Dani, Setiyono | (N/A) | Dani | bar: 2015-07-01 13
24 | UAT execution for all report : 1. OpLease proposal report 2. OpLease calculation attachment 3. Operating Lease Quotation Report (include follow up feedback that raised during UAT) |  |  |  |  | UAT execution for report Quotation report | 4.5 | [6 empty] | BA | Setiyono | Deni K. | Setiyono | bar: 2015-07-01 14
[6 empty] | Total Manhours | 128 | 16 | 8 | 13 | 13 | 16
[6 empty] | Total Mandays | 16 | 2 | 1 | 1.7 | 1.7 | 2
[6 empty] | Manhours for Programmer | 88
[6 empty] | Manhours for Business Analyst | 40
[6 empty] | Mandays for Programmer | 11
[6 empty] | Mandays for Business Analyst | 5
Legend:
Plan
Holiday

## contoh layout billing payment
TERM & CONDITION
Module dibuka pertanggal 30 Mei 2015
Expectation Collection Amount |  |  | Billing Total |  |  | Breakdown Total |  |  | Collection Amount |  |  | Overdue Amount | Overdue PPN - PPh
435840000 |  |  | 72640000 |  |  | 8160000 |  |  | 64480000 |  |  | 0 | 0
Expectation Penalty Coll Amount |  |  | Penalty Collection Amount |  |  | Overdue Penalty Amount
450240 |  |  | 450240 |  |  | 0
FORMAT BILLING PAYMENT HISTORY
Payment Schedule | Invoice Issue Date | Billing Amount | Breakdown Amount | Collection Billing Amount | VAT (10%) | PPH (2%) | Collection Date | Collection Amount | Overdue Days | Penalty Amount | Penalty Collection Date | Penalty Collection Amount
A | B | C | D | E | F | G | H | I | J | K | L | M
[5 empty] | (E x 10%) | (E x 2%) |  | (C - D + E - F) | (H - A) | (J x 1/30 x Penalty Rate x E)
2015-02-14 | 2015-02-01 | 18160000 | 0 | 18160000 | 1816000 | 363200 | 2015-02-14 | 19612800 | 0 | 0
2015-03-14 | 2015-03-01 | 18160000 | 0 | 10000000 | 1000000 | 200000 | 2015-03-14 | 10800000 | 0 | 0
2015-03-14 | 2015-03-01 | 18160000 | 0 | 8160000 | 816000 | 163200 | 2015-04-18 | 8812800 | 35 | 285600
2015-04-14 | 2015-04-01 | 18160000 | 5000000 | 13160000 | 1316000 | 263200 | 2015-04-18 | 14212800 | 4 | 52640
2015-05-14 | 2015-05-01 | 18160000 | 3160000 | 8000000 | 800000 | 160000 | 2015-05-14 | 8640000 | 0 | 0
2015-05-14 | 2015-05-01 | 18160000 | 0 | 7000000 | 700000 | 140000 | 2015-05-30 | 7560000 | 16 | 112000 | 2015-05-30 | 450240
2015-06-14 | 2015-06-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42169 | 0
2015-07-14 | 2015-07-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42199 | 0
2015-08-14 | 2015-08-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42230 | 0
2015-09-14 | 2015-09-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42261 | 0
2015-10-14 | 2015-10-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42291 | 0
2015-11-14 | 2015-11-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42322 | 0
2015-12-14 | 2015-12-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42352 | 0
2016-01-14 | 2016-01-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42383 | 0
2016-02-14 | 2016-02-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42414 | 0
2016-03-14 | 2016-03-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42443 | 0
2016-04-14 | 2016-04-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42474 | 0
2016-05-14 | 2016-05-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42504 | 0
2016-06-14 | 2016-06-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42535 | 0
2016-07-14 | 2016-07-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42565 | 0
2016-08-14 | 2016-08-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42596 | 0
2016-09-14 | 2016-09-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42627 | 0
2016-10-14 | 2016-10-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42657 | 0
2016-11-14 | 2016-11-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42688 | 0
2016-12-14 | 2016-12-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42718 | 0
2017-01-14 | 2017-01-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42749 | 0