## Analisa
OpLease CR (request from Mr. Somad)
▪ Modify interface & minor logic
▪ Re-layout all report (html)
|  | ▪ Modify Billing Payment |  | User using OpLease (Phase #1 code)
OpLease code
Phase #1 | OpLease CR |  | Workshop OpLease | Development
| ▪ Data Historical |  | Phase #2 | OpLease Phase #2
| ▪ User Role Management |  |  | ▪ Billing Payment
▪ Report Framework
● Report
At this time OpLease CR will make a report framework as a foundation of report module on Development OpLease Phase # 2.
One of the functions of the report framework is to export reports into excel file, pdf, and html.
The problem is the making of the report layout will be done two times, at OpLease CR - Report Framework and OpLease CR request from Mr. Somad
● Billing Payment
In the current system, Billing payment only serves to record history so that no payment transactions.
Billing payment transactions will be done on Development OpLease Phase #2, but Mr. Somad asked to modify billing payment in order to conduct payment transactions.
The problem is the making of the billing payment transactions module will be done two times, OpLease CR request from Mr. Somad and Development OpLease Phase #2
Current System
Next System

## FINAL
SUMMARY TEST TANGGAL 18 - 21 MEI 2015
Nama Module | Hasil Test |  |  | Proposal to Solve Problem |  | Manhours Estimation
| No | Detail | Lampiran | No | Detail | Development | Update Doc. | Unit Test | UAT
Calculation OPL Step 1 | 1 | Inputan "end date usage unit plan" | 1 | 1.a | Tanggal diisi secara otomatis | 2 | 8 | 16 | 24
| 2 | Tampilan " lease period plan" |  | 2.a | Diinput secara manual | 0.5
Calculation OPL Step 3 | 1 | Tampilan " lease period" | 2 | 1.a | Diisi secara otomatis mengikuti lease period plan di calculation OPL step 1 | 0.5
| 2 | Inputan "maintenance condition and cost" |  | 2.a | Isian budget biaya maintenance diinput berdasarkan budget selama periode transaksi | 1
Calculation OPL Step 4 | 1 | Inputan "mediator fee amount" | 3 | 1.a | Diinput secara manual | 0.5
|  |  |  | 1.b | Diprotect dengan rumus "input mediator fee < commission amount | 0.5
|  |  |  | 1.c | Dibuat master table mediator fee (NEXT)
Calculation OPL Step 5 | 1 | Tampilan " lease period plan" | 4 | 1.a | Diisi secara otomatis mengikuti lease period plan di calculation OPL step 1 | 0.5
| 2 | Tampilan "insurances income" |  | 2.a | Data tidak muncul | 0.5
| 3 | Tampilan "interest income" |  | 3.a | Data tidak muncul | 2
| 4 | Tampilan "insurances discount" |  | 4.a | Dihapus | 0.5
|  |  |  | 4.b | Insurances discount dikeluarkan dari rumus menghitung total cost | 0.5
| 5 | Tampilan "total profit" |  | 5.a | Istilah total profit diganti dengan total installment | 0.5
| 6 | Tampilan "insurances income" |  | 6.a | Tampilan insurances income harus ada dan diisi secara otomatis | 1
| 7 | Tampilan "total income" |  | 7.a | Tampilan total income harus ada dan diisi secara otomatis (total installment+insurances income) | 1
| 8 | Tampilan "total income after lease cost" |  | 8.a | Tampilan total income after lease cost harus ada dan diisi secara otomatis (total income - total cost) | 1
Operating Lease Proposal Report | 1 | Subject tidak ada isi | 5 | 1.a | Format operating lease proposal report mengikuti contoh | 8
| 2 | Baris profit amount |  | 2.a | Baris profit amount diganti dengan total income after lease cost dan diisi secara otomatis (sama dengan data di OPL Step 5 baris total income after lease cost) | 1
| 3 | Layout Report |  | 3.a | Layout belum rapi dan mengikuti contoh
Operating Lease Calculation Attachment | 1 | Layout Report | 6 | 1.a | Layout belum rapi dan mengikuti contoh | 8
| 2 | Nilai total income salah |  | 2.a | Nilai total income= total installment + insurances income | 0.5
| 3 | Baris adm fee income salah |  | 3.a | Baris adm fee income dihapuskan | 0.5
| 4 | Overhead fee |  | 4.a | Baris overhead fee diganti Lease cost | 0.5
| 5 | Total overhead fee |  | 5.a | Baris total overhead fee diganti total lease cost | 0.5
| 6 | Income after overhead cost salalh |  | 6.a | Baris income after overhead cost diganti dengan income after lease cost | 0.5
|  |  |  | 6.b | Nilai income after overhead cost = total income - total lease cost | 0.5
Operating Lease Qoutation Report | 1 | Tulisan used car sales quotation | 7 | 1.a | Tulisan diganti dengan operating lease quotation | 0.5
| 2 | Layout Report |  | 2.a | Layout report menyesuaikan contoh report | 8
| 3 | Checkbox kurang kelihatan |  | 3.a | Tanda centang pada checkbox dibuat berwarna biru | 0.5
| 4 | Nilai pertanggungan asuransi |  | 4.a | Nilai pertanggunan asuransi adalah nilai pertanggungan bukan nilai premi asuransi | 1
|  |  |  | 4.b | Nilai automobile sum insurared diisi dengan nilai pertanggungan basic premium | 0.5
|  |  |  | 4.c | Tambahkan checkbos pada item insurances | 0.5
| 5 | Kalimat penutup qoutation |  | 5.a | Kalimat penutup dihilangkan | 0.25
| 6 | Checkbox status untuk registration charges |  | 6.a | Seharusnya terdapat tanda centang jika nilai registration ada di calculation | 0.5
| 7 | Tulisan date (mm/dd/yyy) |  | 7.a | Tulisan data khususnya mm/dd/yyy dihilangkan | 0.25
|  |  |  | 7.b | Bulan dalam bentuk kalimat | 0.25
|  |  |  | 7.c | Tanda centang pada checkbox dibuat berwarna biru | 0.5
| 8 | Remark asuransi |  | 8.a | Ada input field | 0.25
Create New Agreement | 1 | Isian bast date dan isian start date usage | 8 | 1.a | Tanggal bast bisa sama dengan tanggal usage | 0.25
| 2 | Isian "end date usage unit" |  | 2.a | Tanggal diisi secara otomatis | 0.5
| 3 | Isian lease period (month) |  | 3.a | Hasil masih salah | 0.5
| 4 | Isian "first due date" |  | 4.a | Tanggal diisi secara otomatis | 0.5
| 5 | Isian "first due date payment" |  | 5.a | Tanggal diisi secara otomatis | 0.5
| 6 | Isian "number of payment" |  | 6.a | Diisi secara otomatis | 0.5
| 7 | Isian "accessories" |  | 7.a | Diisi secara otomatis | 0.5
| 8 | Isian "karoseri" |  | 8.a | Diisi secara otomatis | 0.5
| 9 | Isian "STNK renewal" |  | 9.a | Diisi secara otomatis | 0.5
| 10 | Isian "KEUR renewal" |  | 9.a | Diisi secara otomatis | 0.5
| 11 | Tampilan input Add Unit (object lease) |  | 10.a | Carroserie terpisah dari Accessoris | 3
|  |  |  | 10.b | Data terinput secara otomatis | 1
Service History Inquiry Detail | 1 | Workshop data |  | 1.a | Data workshop yang muncul dalam list hanya yang berstatus aktif | 0.5 | 8
| 2 | Service detail |  | 1.a | PPN diinput manual | 0.5
|  |  |  | 1.b | PPh diinput manual | 0.5
| 3 | Tampilan maintenance budget |  | 3.a | Seharusnya diisi secara otomatis dan merupakan budget untuk satu periode transaksi | 1
Billing Payment History | 1 | Tampilan "expectation collection amount" | 9 | 1.a | Tidak termasuk PPN dan PPh | 1
| 2 | Tampilan "billing total" |  | 2.a | Field dipindahkan setelah "expectation collection amount" | 1
|  |  |  | 2.b | Tidak termasuk PPN dan PPh | 1
| 3 | Tambahan field "breakdown total" |  | 3.a | Diisi secara otomatis | 1
| 4 | Tampilan "overdue amount" |  | 4.a | Tidak termasuk PPN , PPh dan sudah termasuk brakdown | 1
| 5 | Tambahan field "Overdue PPN-PPh" |  | 5.a | Diisi secara otomatis | 1
| 6 | Tambahan field khusus "penalty" |  | 6.a | rumus field expectation penalty collection amount: | 3
total penalty sampai dengan tanggal komputer
|  |  |  | 6.b | rumus field penalty collection amount: | 3
total penalty yang dibayarkan sampai dengan tanggal komputer
|  |  |  | 6.c | rumus field o/s penalty not yet paid: | 3
expectation penalty collection amount - penaly collection amount
| 7 | Revisi format billing payment history |  | 7.a | seperti terlampir | 8
[6 empty] | 79.75 | 16 | 16 | 24
[6 empty] | 10 | 2 | 2 | 3

## contoh layout billing payment
TERM & CONDITION
Module dibuka pertanggal 30 Mei 2015
Expectation Collection Amount |  |  | Billing Total |  |  | Breakdown Total |  |  | Collection Amount |  |  | Overdue Amount | Overdue PPN - PPh
435840000 |  |  | 72640000 |  |  | 8160000 |  |  | 64480000 |  |  | 0 | 0
Expectation Penalty Coll Amount |  |  | Penalty Collection Amount |  |  | Overdue Penalty Amount
450240 |  |  | 450240 |  |  | 0
FORMAT BILLING PAYMENT HISTORY
Payment Schedule | Invoice Issue Date | Billing Amount | Breakdown Amount | Collection Billing Amount | VAT (10%) | PPH (2%) | Collection Date | Collection Amount | Overdue Days | Penalty Amount | Penalty Collection Date | Penalty Collection Amount
A | B | C | D | E | F | G | H | I | J | K | L | M
[5 empty] | (E x 10%) | (E x 2%) |  | (C - D + E - F) | (H - A) | (J x 1/30 x Penalty Rate x E)
2015-02-14 | 2015-02-01 | 18160000 | 0 | 18160000 | 1816000 | 363200 | 2015-02-14 | 19612800 | 0 | 0
2015-03-14 | 2015-03-01 | 18160000 | 0 | 10000000 | 1000000 | 200000 | 2015-03-14 | 10800000 | 0 | 0
2015-03-14 | 2015-03-01 | 18160000 | 0 | 8160000 | 816000 | 163200 | 2015-04-18 | 8812800 | 35 | 285600
2015-04-14 | 2015-04-01 | 18160000 | 5000000 | 13160000 | 1316000 | 263200 | 2015-04-18 | 14212800 | 4 | 52640
2015-05-14 | 2015-05-01 | 18160000 | 3160000 | 8000000 | 800000 | 160000 | 2015-05-14 | 8640000 | 0 | 0
2015-05-14 | 2015-05-01 | 18160000 | 0 | 7000000 | 700000 | 140000 | 2015-05-30 | 7560000 | 16 | 112000 | 2015-05-30 | 450240
2015-06-14 | 2015-06-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42169 | 0
2015-07-14 | 2015-07-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42199 | 0
2015-08-14 | 2015-08-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42230 | 0
2015-09-14 | 2015-09-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42261 | 0
2015-10-14 | 2015-10-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42291 | 0
2015-11-14 | 2015-11-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42322 | 0
2015-12-14 | 2015-12-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42352 | 0
2016-01-14 | 2016-01-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42383 | 0
2016-02-14 | 2016-02-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42414 | 0
2016-03-14 | 2016-03-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42443 | 0
2016-04-14 | 2016-04-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42474 | 0
2016-05-14 | 2016-05-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42504 | 0
2016-06-14 | 2016-06-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42535 | 0
2016-07-14 | 2016-07-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42565 | 0
2016-08-14 | 2016-08-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42596 | 0
2016-09-14 | 2016-09-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42627 | 0
2016-10-14 | 2016-10-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42657 | 0
2016-11-14 | 2016-11-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42688 | 0
2016-12-14 | 2016-12-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42718 | 0
2017-01-14 | 2017-01-01 | 18160000 |  |  | 0 | 0 |  | 0 | -42749 | 0