## Sheet1
Activity | Duration (day) | Output | Status | (%) | Start Date | Actual Start | Complete | Duration | Remarks
Software Arsitektur
+ Update Software Arsitektur | 1 | Architecture document | Complete | 100 | 2015-04-01 | 2015-04-03 | 2015-04-06 | 2 days
User Management (replace existing)
+ Functional Spesification |  | Functional Specification Document
- User Management (Login, Create user, Assign Role, etc) | 3 |  | On Progrres
- Confirm to User (ITD) | 2
+ ERD | 1 | ERD - User Management Doc
+ Development
+ Development |  | Application ( OLSS Upgrade Version)
- Implement .Net Identity | 1
- Customize user role function | 1
- Implement to Existing Module | 2
+ Internal testing ( 12 cases - Normal/Alternate) | 2 | Test Plan, Test Case, Test result
+ UAT (ITD) | 3 | UAT Plan, UAT Script Doc - signed by ITD
Report Framework (replace existing)
+ Deploy RDLC framework | 1 | Application ( OLSS Upgrade Version)
+ Create sample of report ( 2 samples of report) | 1
+ Internal testing | 1 | Test Plan, Test Case, Test result
+ UAT | 1 | UAT Plan, UAT result signed by ITD
Log (baru) --> Not Include Historical report
+ Functional Spesification |  | Functional Specification Document
- Main process loging (process id number) | 2
- Confirm To User (ITD) | 2
+ ERD | 1 | ERD - Log Doc
+ Development | 5 | Application ( OLSS Upgrade Version)
+ Internal testing | 2 | Test Plan, Test Case, Test result
+ UAT ( 10 UAT scipts) | 4 | UAT Plan, UAT Script Doc - signed by ITD
Review Meeting | 4 | Review Record
Total Mandays | 40

## Sheet2
Activity |  |  | Duration (day) | Output | Status | (%) | Date |  | =Plan |  | =Actual
 | time axis 2015-04-01 to 2015-05-31
Environment preparation
Software Arsitektur
| ● Update Software Arsitektur |  | 1 | Architecture document | Complete | 100
User Management (replace existing) | bar: 2015-04-02; 2015-04-06
| ● Functional Spesification |  |  | Functional Specification Document
|  | ◦ User Management (Login, Create user, Assign Role, etc) | 3 |  | On Progress | bar: 2015-04-06 to 2015-04-07
|  | ◦ Confirm to User (ITD) | 2 | bar: 2015-04-08 to 2015-04-09
| ● ERD |  | 1 | ERD - User Management Doc
| ● Development |  |  | Application ( OLSS Upgrade Version)
|  | ◦ Implement .Net Identity | 1
|  | ◦ Customize user role function | 1
|  | ◦ Implement to Existing Module | 2
| ● Internal testing ( 12 cases - Normal/Alternate) |  | 2 | Test Plan, Test Case, Test result
| ● UAT (ITD) |  | 3 | UAT Plan, UAT Script Doc - signed by ITD
Report Framework (replace existing)
| ● Deploy RDLC framework |  | 1 | Application ( OLSS Upgrade Version)
| ● Create sample of report ( 2 samples of report) |  | 1
| ● Internal testing |  | 1 | Test Plan, Test Case, Test result
| ● UAT |  | 1 | UAT Plan, UAT result signed by ITD
Log (baru) --> Not Include Historical report
| ● Functional Spesification |  |  | Functional Specification Document
|  | ◦ Main process loging (process id number) | 2 |  | On Progress | 20 | bar: 2015-04-10; 2015-04-13
|  | ◦ Confirm To User (ITD) | 2 | bar: 2015-04-14 to 2015-04-15
| ● ERD |  | 1 | ERD - Log Doc | On Progress | 60 | bar: 2015-04-16
| ● Development |  | 5 | Application ( OLSS Upgrade Version) | On Progress | 40 | bar: 2015-04-17; 2015-04-20 to 2015-04-23
| ● Internal testing |  | 2 | Test Plan, Test Case, Test result
| ● UAT ( 10 UAT scipts) |  | 4 | UAT Plan, UAT Script Doc - signed by ITD
Review Meeting |  |  | 4 | Review Record
|  | Total Mandays | 40
Complete
On Progress