## Sheet1
Activity | Duration (day) | Output | Status | (%) | Start Date | Actual Start | Complete | Duration | Remarks
Software Arsitektur
+ Update Software Arsitektur | 1 | Architecture document | Complete | 100 | 2015-04-01 | 2015-04-03 | 2015-04-06 | 2 days
User Management (replace existing)
+ Functional Spesification |  | Functional Specification Document
- User Management (Login, Create user, Assign Role, etc) | 3 |  | On Progrres
- Confirm to User (ITD) | 2
+ ERD | 1 | ERD - User Management Doc
+ Development
+ Development |  | Application ( OLSS Upgrade Version)
- Implement .Net Identity | 1
- Customize user role function | 1
- Implement to Existing Module | 2
+ Internal testing ( 12 cases - Normal/Alternate) | 2 | Test Plan, Test Case, Test result
+ UAT (ITD) | 3 | UAT Plan, UAT Script Doc - signed by ITD
Report Framework (replace existing)
+ Deploy RDLC framework | 1 | Application ( OLSS Upgrade Version)
+ Create sample of report ( 2 samples of report) | 1
+ Internal testing | 1 | Test Plan, Test Case, Test result
+ UAT | 1 | UAT Plan, UAT result signed by ITD
Log (baru) --> Not Include Historical report
+ Functional Spesification |  | Functional Specification Document
- Main process loging (process id number) | 2
- Confirm To User (ITD) | 2
+ ERD | 1 | ERD - Log Doc
+ Development | 5 | Application ( OLSS Upgrade Version)
+ Internal testing | 2 | Test Plan, Test Case, Test result
+ UAT ( 10 UAT scipts) | 4 | UAT Plan, UAT Script Doc - signed by ITD
Review Meeting | 4 | Review Record
Total Mandays | 40

## Sheet2
No | Activity |  |  | Duration (day) | Output | Status | (%) |  |  | =Plan | [5 empty] | =Actual
[8 empty] | April 2015 | [29 empty] | May 2015
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Environment preparation
2 | Software Arsitektur
|  | ● Update Software Arsitektur |  | 1 | Architecture document | Complete | 100 | bar: April 2015 1
3 | Log (baru) --> Not Include Historical report
|  | ● Functional Spesification |  |  | Functional Specification Document
|  |  | ◦ Main process loging (process id number) | 2 |  | Complete | 100 | bar: April 2015 10; April 2015 13; April 2015 15
|  |  | ◦ Confirm To User (ITD) | 2 |  |  | 100 | bar: April 2015 16 to April 2015 17
|  | ● ERD |  | 1 | ERD - Log Doc | Complete | 100 | bar: April 2015 16
|  | ● Development |  | 5 | Application ( OLSS Upgrade Version) | Complete | 100 | bar: April 2015 17; April 2015 20 to April 2015 23
|  | ● Internal testing |  | 2 | Test Plan, Test Case, Test result | Complete | 100 | bar: April 2015 24; April 2015 27
|  | ● UAT ( 10 UAT scripts) |  | 4 | UAT Plan, UAT Script Doc - signed by ITD | bar: April 2015 28 to April 2015 30; May 2015 4; May 2015 27 to May 2015 28
4 | User Management (replace existing)
|  | ● Functional Spesification |  |  | Functional Specification Document
|  |  | ◦ User Management (Login, Create user, Assign Role, etc) | 3 |  | On Progress | 10 | bar: April 2015 6 to April 2015 7; April 2015 30; May 2015 4 to May 2015 5; May 2015 7
|  |  | ◦ Confirm to User (ITD) | 2 | bar: May 2015 4 to May 2015 6; May 2015 8
|  | ● ERD |  | 1 | ERD - User Management Doc | bar: May 2015 6 to May 2015 7
|  | ● Development |  |  | Application ( OLSS Upgrade Version)
|  |  | ◦ Implement .Net Identity | 1 | bar: May 2015 7; May 2015 11
|  |  | ◦ Customize user role function | 1 | bar: May 2015 8; May 2015 12
|  |  | ◦ Implement to Existing Module | 2 | bar: May 2015 11 to May 2015 14
|  | ● Internal testing ( 12 cases - Normal/Alternate) |  | 2 | Test Plan, Test Case, Test result | bar: May 2015 13 to May 2015 15; May 2015 18
|  | ● UAT (ITD) |  | 3 | UAT Plan, UAT Script Doc - signed by ITD | bar: May 2015 15; May 2015 18 to May 2015 20
5 | Report Framework (replace existing)
|  | ● Deploy RDLC framework |  | 1 | Application ( OLSS Upgrade Version) | bar: May 2015 20 to May 2015 21
|  | ● Create sample of report ( 2 samples of report) |  | 1 | bar: May 2015 21 to May 2015 22
|  | ● Internal testing |  | 1 | Test Plan, Test Case, Test result | bar: May 2015 22; May 2015 25
|  | ● UAT |  | 1 | UAT Plan, UAT result signed by ITD | bar: May 2015 25 to May 2015 26
6 | Review Meeting |  |  | 4 | Review Record | bar: May 2015 8; May 2015 15; May 2015 22; May 2015 26 to May 2015 29
|  |  | Total Mandays | 40
Complete
On Progress
=Plan
=Actual
=to YKK (project)
=Revisi
10
20
30
40
50
60
70
80
90
100