## 20140929-Issues
Id | Category | Assigned | Type | Milestone | Status | Priority | Due Date | Progress | Created | Last Update | Phase
TM14402A-89 | Coding Defects | Unassigned | Task | Iteration 1 | New | High | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | SIT
TM14402A-88 | Coding Defects | Unassigned | Bug | Iteration 1 | New | Mid | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | SIT
TM14402A-87 | Inquiry | Unassigned | Task | Iteration 1 | New | Mid | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | SWD
TM14402A-86 | Coding Defects | Unassigned | Bug | Iteration 1 | New | Mid | 10/1/2014 | 0% | 9/29/2014 | 9/29/2014 | SIT
TM14402A-85 | Coding Defects | Unassigned | Bug | Iteration 1 | New | Mid | 10/1/2014 | 0% | 9/29/2014 | 9/29/2014 | SIT
TM14402A-84 | Coding Defects | Unassigned | Bug | Iteration 1 | New | Mid | 10/1/2014 | 0% | 9/29/2014 | 9/29/2014 | SIT
TM14402A-83 | Design Defects | dani | Bug | Iteration 1 | New | Mid | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | Pre-UAT
TM14402A-82 | Coding Defects | dani | Bug | Iteration 1 | New | Mid | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | Pre-UAT
TM14402A-81 | Coding Defects | dani | Bug | Iteration 1 | New | Mid | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | Pre-UAT
TM14402A-80 | Coding Defects | asep | Task | Iteration 1 | New | Low | 9/30/2014 | 0% | 9/29/2014 | 9/29/2014 | Pre-UAT
TM14402A-79 | Coding Defects | asep | Bug | Iteration 1 | New | Stopper | 9/30/2014 | 0% | 9/27/2014 | 9/29/2014 | Pre-UAT
TM14402A-78 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/29/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-77 | Coding Defects | dani | Bug | Iteration 1 | Closed | Mid | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-76 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-75 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/29/2014 | SIT
TM14402A-74 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/29/2014 | SIT
TM14402A-73 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-72 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-71 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-70 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-69 | Design Defects | dani | Task | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-68 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-67 | Coding Defects | asep | Bug | Iteration 1 | Closed | Mid | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-66 | Coding Defects | Unassigned | Bug | Iteration 1 | Closed | Low | 9/29/2014 | 100% | 9/25/2014 | 9/26/2014 | UT
TM14402A-65 | Coding Defects | asep | Task | Iteration 1 | Closed | Low | 9/29/2014 | 100% | 9/25/2014 | 9/27/2014 | SWC
TM14402A-64 | Design Defects | asep | Bug | Iteration 1 | Closed | Mid | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-63 | Design Defects | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-62 | Coding Defects | dani | Bug | Iteration 1 | Closed | Mid | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-61 | Design Defects | dani | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-60 | Design Defects | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-59 | Peformance Issue | Unassigned | Task | Iteration 2 | New | Low | 10/10/2014 | 0% | 9/24/2014 | 9/29/2014 | UAT
TM14402A-58 | Coding Defects | Unassigned | Bug | Iteration 1 | New | Low | 9/29/2014 | 0% | 9/24/2014 | 9/29/2014 | UAT
TM14402A-57 | Coding Defects | Unassigned | Bug | Iteration 1 | Closed | Low | 9/26/2014 | 100% | 9/24/2014 | 9/27/2014 | SIT
TM14402A-56 | Coding Defects | Unassigned | Bug | Iteration 1 | Closed | Low | 9/26/2014 | 100% | 9/24/2014 | 9/27/2014 | SIT
TM14402A-55 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-54 | Design Defects | dani | Bug | Iteration 1 | Closed | Low | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-53 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-52 | Design Defects | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-51 | Design Defects | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-49 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-48 | Design Defects | asep | Bug | Iteration 1 | Closed | Low | 9/25/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-47 | Coding Defects | asep | Bug | Iteration 1 | Closed | Mid | 9/26/2014 | 100% | 9/23/2014 | 9/25/2014 | SIT
TM14402A-46 | Coding Defects | Unassigned | Bug | Iteration 1 | New | Low | 9/26/2014 | 0% | 9/23/2014 | 9/29/2014 | UAT
TM14402A-45 | Design Defects | deny | Bug | Iteration 1 | Closed | High | 9/26/2014 | 0% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-44 | Coding Defects | asep | Bug | Iteration 1 | New | Low | 9/29/2014 | 0% | 9/23/2014 | 9/29/2014 | Pre-UAT
TM14402A-43 | Design Defects | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-42 | Coding Defects | asep | Bug | Iteration 1 | Closed | Low | 9/29/2014 | 100% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-41 | Coding Defects | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-40 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/24/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-39 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-37 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-36 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-35 | Design Defects | dani | Bug | Iteration 1 | Closed | Mid | 9/24/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-34 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-33 | Design Defects | dani | Task | Iteration 1 | Closed | Mid | 9/26/2014 | 100% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-32 | Coding Defects | dani | Bug | Iteration 1 | Closed | Mid | 9/26/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-31 | Coding Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-30 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-29 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-28 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-27 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/26/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-26 | Coding Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-25 | Coding Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-24 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-23 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-22 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-21 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-20 | Data Defects | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-19 | Coding Defects | asep | Bug | Iteration 1 | Closed | Low | 9/23/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-16 | Pending task | dani | Task | Iteration 1 | Closed | Mid | 9/18/2014 | 100% | 9/17/2014 | 9/23/2014 | SWC
TM14402A-11 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/18/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-10 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-9 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-8 | Coding Defects | dani | Bug | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-7 | Pending task | deny | Task | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-6 | Inquiry | asep | Task | Iteration 1 | Closed | High | 9/16/2014 | 100% | 9/12/2014 | 9/23/2014 | SWC
TM14402A-5 | Coding Defects | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/12/2014 | 9/25/2014 | UT
TM14402A-4 | Pending task | dani | Task | Iteration 1 | Closed | High | 9/16/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC
TM14402A-3 | Coding Defects | asep | Task | Iteration 1 | Closed | High | 9/10/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC
TM14402A-2 | Coding Defects | dani | Task | Iteration 1 | Closed | High | 9/10/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC
TM14402A-1 | Pending task | deny | Task | Iteration 1 | Closed | High | 9/11/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC

## Sheet4
データの個数 / Id | 列ラベル
行ラベル | Bug | Task | 総計 | Date | Bugs | Closed
9/12/2014 | 1 | 1 | 2 | 9/12/2014 | 1 | 0
9/16/2014 | 4 | 1 | 5 | 9/16/2014 | 5 | 0
9/17/2014 |  | 1 | 1 | 9/17/2014 | 5 | 0
9/23/2014 | 28 | 1 | 29 | 9/23/2014 | 33 | 4
9/24/2014 | 9 | 1 | 10 | 9/24/2014 | 42 | 11
9/25/2014 | 6 | 1 | 7 | 9/25/2014 | 48 | 39
9/27/2014 | 12 | 1 | 13 | 9/27/2014 | 60 | 53
9/29/2014 | 7 | 3 | 10 | 9/29/2014 | 67 | 55
総計 | 67 | 10 | 77
Status | Closed
Type | Bug
行ラベル | データの個数 / Id
9/23/2014 | 4
9/24/2014 | 7
9/25/2014 | 28
9/26/2014 | 1
9/27/2014 | 14
9/29/2014 | 2
総計 | 56
as of 29/09/2014 17:34