## Sheet1
データの個数 / Id | 列ラベル
行ラベル | Bug | Task | 総計 | Date | Bugs | Closed
9/10/2014 |  | 4 | 4 | 9/10/2014 | 0
9/12/2014 | 1 | 1 | 2 | 9/12/2014 | 1
9/16/2014 | 4 | 1 | 5 | 9/16/2014 | 5
9/17/2014 |  | 1 | 1 | 9/17/2014 | 5
9/23/2014 | 28 | 1 | 29 | 9/23/2014 | 33 | 4
9/24/2014 | 9 | 1 | 10 | 9/24/2014 | 42 | 11
9/25/2014 | 6 | 1 | 7 | 9/25/2014 | 48 | 39
9/27/2014 | 12 | 1 | 13 | 9/27/2014 | 60 | 54
9/29/2014 | 7 | 3 | 10 | 9/29/2014 | 67 | 56
9/30/2014 |  | 1 | 1 | 9/30/2014 | 67 | 56
総計 | 67 | 15 | 82 | 10/1/2014 | 67 | 63
Status | Closed
Type | Bug
行ラベル | データの個数 / Id
10/1/2014 | 7
9/23/2014 | 4
9/24/2014 | 7
9/25/2014 | 28
9/26/2014 | 1
9/27/2014 | 14
9/29/2014 | 2
総計 | 63

## 20141001-Issues
Id | Title | Category | Owner | Assigned | Type | Milestone | Status | Priority | Due Date | Progress | Created | Last Update | Phase
TM14402A-90 | Do not hard code "LDAP:dipostar" in AccountController | Coding Defects | koib | asep | Task | Iteration 1 | Closed | Mid | 10/10/2014 | 100% | 9/30/2014 | 10/1/2014 | SWC
TM14402A-89 | Logging | Coding Defects | koib | Unassigned | Task | Iteration 1 | Closed | High | 10/3/2014 | 100% | 9/29/2014 | 10/1/2014 | SIT
TM14402A-88 | LastModified and LastModifiedBy are not set after update | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | Mid | 9/30/2014 | 100% | 9/29/2014 | 10/1/2014 | SIT
TM14402A-87 | [Spec Confirmation] non ASCII characters | Inquiry | koib | Unassigned | Task | Iteration 1 | New | Mid | 10/3/2014 | 0% | 9/29/2014 | 10/1/2014 | SWD
TM14402A-86 | Date picker range and SQL Server datetime range | Coding Defects | koib | dani | Bug | Iteration 1 | New | Mid | 10/1/2014 | 0% | 9/29/2014 | 9/30/2014 | SIT
TM14402A-85 | Text box has no limited length | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | Mid | 10/1/2014 | 100% | 9/29/2014 | 10/1/2014 | SIT
TM14402A-84 | Date picker hungs up when illegal date was inputed | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | Mid | 10/1/2014 | 100% | 9/29/2014 | 10/1/2014 | SIT
TM14402A-83 | In edit and view detail screon on the each of master data module; status indicator (such as draft, submitted, active, inactive) still not displayed on the screen (on the top-righth side) | Design Defects | deny | dani | Bug | Iteration 1 | Closed | Mid | 9/30/2014 | 100% | 9/29/2014 | 10/1/2014 | Pre-UAT
TM14402A-82 | In edit screon on the each of master data module; customer code, supplier code, and product code should not be able to edit. | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | Mid | 9/30/2014 | 100% | 9/29/2014 | 10/1/2014 | Pre-UAT
TM14402A-81 | On the Supplier Module: Main supplier code, still not having validation. It should be mandatory field. | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | Mid | 9/30/2014 | 100% | 9/29/2014 | 10/1/2014 | Pre-UAT
TM14402A-80 | Do not use Console.WriteLine | Coding Defects | koib | asep | Task | Iteration 1 | Closed | Low | 9/30/2014 | 100% | 9/29/2014 | 10/1/2014 | Pre-UAT
TM14402A-79 | Integration Maters: If user already sign out, then sign within input [user name] without [password], user should not be able to login. | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | Stopper | 9/30/2014 | 100% | 9/27/2014 | 10/1/2014 | Pre-UAT
TM14402A-78 | (UI Layout) Ommit some menu in the home screen. | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | High | 9/29/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-77 | The order of [supplier code] is should be before [supplier category]. | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | Mid | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-76 | On the User and Role Module: When press enter button after finished fill out the fields, the triggering should not be submitted, but it should be saved. | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-75 | On the Customer, Supplier and Product: When deactivate the records, the allert message should be notified state as "deactivated" not "inserted" | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/29/2014 | SIT
TM14402A-74 | On the Customer, Supplier and Product: When activate the records, the allert message should be notified state as "activated" not "inserted" | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/29/2014 | SIT
TM14402A-73 | On the Customer, Supplier and Product: When submit the records, the allert message should be notified state as "submitted" not "inserted" | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-72 | On the User and Role Module : When deactivate the records, the allert message should be notified state as "deactivated" not "inserted" | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-71 | On the User and Role Module : When activate the records, the allert message should be notified state as "activated" not "inserted" | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-70 | On the User and Role Module : When submit the records, the allert message should be notified state as "submitted" not "inserted" | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-69 | Order of the fields and columns in the product information should be user friendly. | Design Defects | deny | dani | Task | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-68 | Back button on the add user and add role is not exist. | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-67 | Validation err. on the user module ( does not proper with type of validation) | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | Mid | 9/27/2014 | 100% | 9/27/2014 | 9/27/2014 | SIT
TM14402A-66 | Sign in page issue | Coding Defects | koib | Unassigned | Bug | Iteration 1 | Closed | Low | 9/29/2014 | 100% | 9/25/2014 | 9/26/2014 | UT
TM14402A-65 | [Common] do not use hard coded value "Anonymous" | Coding Defects | koib | asep | Task | Iteration 1 | Closed | Low | 9/29/2014 | 100% | 9/25/2014 | 9/27/2014 | SWC
TM14402A-64 | SIT.0.6 Back button is not exist on User & Role Screen | Design Defects | deny | asep | Bug | Iteration 1 | Closed | Mid | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-63 | SIT.05 Role matrix management for user and super user still not implemented. | Design Defects | deny | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-62 | SIT 0.4 CreatedBy always "DIPO DIPO" on Customer, Supplier and Product. | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | Mid | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-61 | SIT.0.2 Is Active and Is Delete Rule still not implemented on Customer Module, Supplier Module and Product Module. | Design Defects | deny | dani | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-60 | SIT.0.1 Is Active and Is Delete Rule still not implemented on User Module and Role Module. | Design Defects | deny | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/25/2014 | 9/25/2014 | SIT
TM14402A-59 | minimized jquery should be used on test and production environment | Peformance Issue | koib | Unassigned | Task | Iteration 2 | New | Low | 10/10/2014 | 0% | 9/24/2014 | 9/29/2014 | UAT
TM14402A-58 | It is an error to use a section registered as allowDefinition='MachineToApplication' beyond application level | Coding Defects | koib | Unassigned | Bug | Iteration 1 | New | Low | 10/3/2014 | 0% | 9/24/2014 | 10/1/2014 | UAT
TM14402A-57 | An object with the same key already exists in the ObjectStateManager. | Coding Defects | koib | Unassigned | Bug | Iteration 1 | Closed | Low | 9/26/2014 | 100% | 9/24/2014 | 9/27/2014 | SIT
TM14402A-56 | Cannot implicitly convert type 'bool' to 'byte?' | Coding Defects | koib | Unassigned | Bug | Iteration 1 | Closed | Low | 9/26/2014 | 100% | 9/24/2014 | 9/27/2014 | SIT
TM14402A-55 | 21.1 UI Errorr in the on View Detail Screen; There is no button for perform change status of product (product module) | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-54 | 21.1 UI Errorr in the [Maintenance and Other Information] panel on View Detail Screen (product module) | Design Defects | deny | dani | Bug | Iteration 1 | Closed | Low | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-53 | 19.4 - 20.3 Data mandatory still not implemented on the Add and Edit Product Screen (on Product Module) | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-52 | 19.3 - 20.2 Wrong data format still can be added on the system. (on Add/ Edit New Product Screen) | Design Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-51 | 19.2 Existing data still can be process to added. (on product module) | Design Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-49 | 16.1 Supplier category is not appear in detail view screen | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | High | 9/25/2014 | 100% | 9/24/2014 | 9/25/2014 | UT
TM14402A-48 | 13.1 UI Error in view detail screen, on tab credit info. | Design Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/25/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-47 | SIT 0.3 CreatedBy always "DIPO DIPO" on User and Role Module. | Coding Defects | koib | asep | Bug | Iteration 1 | Closed | Mid | 9/26/2014 | 100% | 9/23/2014 | 9/25/2014 | SIT
TM14402A-46 | [Common] show NN entries selection is reset | Coding Defects | koib | Unassigned | Bug | Iteration 1 | New | Low | 10/3/2014 | 0% | 9/23/2014 | 10/1/2014 | UAT
TM14402A-45 | 15.1 Supplier data cannot be distinguished | Design Defects | koib | deny | Bug | Iteration 1 | Closed | High | 9/26/2014 | 0% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-44 | [Common] Browser size problem? | Coding Defects | koib | asep | Bug | Iteration 1 | New | Low | 10/1/2014 | 0% | 9/23/2014 | 10/1/2014 | Pre-UAT
TM14402A-43 | [Common] Validation Design Defects in All function | Design Defects | asep | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-42 | [Common] multiple submit was not prevented | Coding Defects | koib | asep | Bug | Iteration 1 | Closed | Low | 9/29/2014 | 100% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-41 | [Common] textbox for numerical data must have "text-align: right" | Coding Defects | koib | asep | Bug | Iteration 1 | Closed | High | 9/27/2014 | 100% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-40 | 14.1 Failed to perform changes status of Customer record | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/24/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-39 | 12.1 In edit customer function, some data cannot be saved. | Coding Defects | deny | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-37 | 18.1 Activation does not work on Supplier module | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-36 | 17.1 Go Public Company in details screen is wrong. (On Supplier module) | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-35 | 11.1 Number of employee data type should be text not number. (On customer and Supplier Module) | Design Defects | deny | dani | Bug | Iteration 1 | Closed | Mid | 9/24/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-34 | 16.1 Supplier group was not saved | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-33 | 16.1 cannot recognize the cause from error message | Design Defects | koib | dani | Task | Iteration 1 | Closed | Mid | 9/26/2014 | 100% | 9/23/2014 | 9/27/2014 | SIT
TM14402A-32 | 15.2 date picker does not disapear | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | Mid | 9/26/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-31 | 2.1 When click sign out button on the screen, has found error. | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-30 | 10.1 Change status features on the Role Function cannot be tested, there is no existing data (Data maters), same problem with test case 7.2 | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-29 | 9.1 View detail function cannot be tested, there is no existing data (Data maters), same problem with test case 7.2 | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-28 | 8.1 In the Role screen, Edit function cannot works. (Data maters), same problem with test case 7.2 | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-27 | 15.2 duplicate check seems not be implemented | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | High | 9/26/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-26 | 7.2 In the User screen, there is no existing data (Data maters). | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-25 | 7.1 On the Add Role screen, after click [save as draft] or [submit], the transaction process is failure (data cannot be added.) | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-24 | 6.1 Change status features on the User Function cannot be tested, there is no existing data (Data maters), same problem with test case 3.2 | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-23 | 5.1 View detail function cannot be tested, there is no existing data (Data maters), same problem with test case 3.2 | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-22 | 15.1 Keyword Filtering not working on the Supplier list screen | Coding Defects | koib | dani | Bug | Iteration 1 | Closed | High | 9/23/2014 | 100% | 9/23/2014 | 9/24/2014 | UT
TM14402A-21 | 4.1 In the User screen, Edit function cannot works. (Data maters), same problem with test case 3.2 | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-20 | 3.2 In the User screen, there is no existing data (Data maters). | Data Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/24/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-19 | 3.1 On the Add User screen, after click [save as draft], save transaction process is failure (data cannot be added.) | Coding Defects | deny | asep | Bug | Iteration 1 | Closed | Low | 9/23/2014 | 100% | 9/23/2014 | 9/25/2014 | UT
TM14402A-16 | Adding validation Information text for wrong data input | Pending task | dani | dani | Task | Iteration 1 | Closed | Mid | 9/18/2014 | 100% | 9/17/2014 | 9/23/2014 | SWC
TM14402A-11 | Save as Draft Still not Working | Coding Defects | asep | dani | Bug | Iteration 1 | Closed | High | 9/18/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-10 | CV Maintenance Not Appear in Customer Edit and Customer Detail | Coding Defects | asep | dani | Bug | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-9 | Internal Rating Not Appear in Customer Detail | Coding Defects | asep | dani | Bug | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-8 | Information Acquisition Date Not Appear | Coding Defects | asep | dani | Bug | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-7 | Drafting a unit testing for master data module | Pending task | deny | deny | Task | Iteration 1 | Closed | High | 9/17/2014 | 100% | 9/16/2014 | 9/23/2014 | SWC
TM14402A-6 | Need Sample User Account for Development Purpose | Inquiry | deny | asep | Task | Iteration 1 | Closed | High | 9/16/2014 | 100% | 9/12/2014 | 9/23/2014 | SWC
TM14402A-5 | LDAP Authentication Issue | Coding Defects | asep | asep | Bug | Iteration 1 | Closed | Stopper | 9/25/2014 | 100% | 9/12/2014 | 9/25/2014 | UT
TM14402A-4 | Complete a status handling for master data module | Pending task | deny | dani | Task | Iteration 1 | Closed | High | 9/16/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC
TM14402A-3 | Complete validation functions on the user roles module | Coding Defects | deny | asep | Task | Iteration 1 | Closed | High | 9/10/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC
TM14402A-2 | Complete CRUD functions on the customer Information module | Coding Defects | deny | dani | Task | Iteration 1 | Closed | High | 9/10/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC
TM14402A-1 | Drafting functional specification for Master Data module | Pending task | deny | deny | Task | Iteration 1 | Closed | High | 9/11/2014 | 100% | 9/10/2014 | 9/23/2014 | SWC