## Rundown
Rundown Production Installation
■Preconditions
OS | Windows Server 2012 was properly installed and running (for DB and APP)
The servers are able to access via remote desktop with administrator privilege
The servers are able to access internet to download necessary software including Windows Update
execute by administrator: netsh winhttp import proxy source=ie (to confirm, execute netsh winhttp show proxy )
.net framework 4.5.2 and necessary Windows Update patches are properly applied
Infra PIC has already informed necessary information to connect servers with administrator privilege
APP | IIS features are already enabled
DB | Procurement provide SQL Server install media and infra team mounted the media to the PROD environment
No | Date | Activity | Description | Start time | Finish time | PIC | Remarks
101 | Friday, 12 December 2014 | Database Installation | Install SQL Server 2012 standard 64bit | ? | ? | Mr. Erry | already done by 11 Dec
102 |  |  | Configure to allow network access | ? | ? | Mr. Erry
103 |  |  | Apply Service Pack 2 and MS Update | 10:00 | 11:30 | Mr. Erry
104 |  | Configure IIS | Configure W3SVC log to record sc-bytes and cs-bytes | 10:30 | 10:35 | Mr. Koibuchi
105 |  |  | Configure MIME type to add json, woff | 10:40 | 10:55 | Mr. Koibuchi
106 |  |  | Enable ASP.NET on IIS | 11:15 | 11:30 | Mr. Koibuchi | ASP.NET, HTTP Activation
107 |  | Configure Web Site | Create c:\olss\web, c:\olss\log and allow Everyone Full Control | 11:30 | 11:35 | Mr. Koibuchi | also enable Application Initialization
108 |  |  | Create new application pool using .net 4 | 11:35 | 11:40 | Mr. Koibuchi
109 |  |  | Create Virtual Directory and assign d:\olss\web as physical directory | 11:45 | 11:50 | Mr. Koibuchi
110 |  |  | Select created application pool for the application | 11:50 | 11:55 | Mr. Koibuchi
111 |  | Other | Turn on ASP.NET State Service and set service property to run automatically | 11:55 | 12:00 | Mr. Koibuchi
201 | Saturday, 13 December | Basic connection test | Test DB connection using test program | 15:00 | 15:15 | Mr. Koibuchi
202 |  |  | Test LDAP connection authentication using test program | 15:15 | 15:30 | Mr. Koibuchi
203 |  | Prepare Database | Restore database object from latest Dev | 15:30 | 16:00 | Mr. Koibuchi
|  |  | Create SQL Server Login user | 16:00 | 16:10 | Mr. Koibuchi
|  |  | Create SQL Server Database user to access olss_prod and map to login | 16:00 | 16:10 | Mr. Koibuchi
204 |  | Deploy application | Copy OLSS application files to the d:\olss\web\ | 16:10 | 16:20 | Mr. Koibuchi
205 |  |  | Configure connection string in the web.config to point production database | 16:10 | 16:20 | Mr. Koibuchi | database name "olss_prod"
206 |  |  | Configure connection string in the web.config to point DSF Active Directory | 16:10 | 16:20 | Mr. Koibuchi | LDAP://dipostar
207 |  |  | Configure web.config to use session state service | 16:10 | 16:20 | Mr. Koibuchi | 127.0.0.1:42424
208 |  |  | Configure web.config for logging | 16:10 | 16:20 | Mr. Koibuchi | (for test app) TraceLevel = Verbose Prefix = olss_test Retention = 10 LogSaveDir = D:\olss\log
209 |  | Test | test application | 16:10 | 16:15 | Mr. Koibuchi | Login, click all menu, retrieve data, create data (used Customer function)
| Wednesday, 17 December | System closing | user announcement |  |  | Mr. Deny | by email
|  |  | shutdown 10.1.1.37/olss/ | 17:30 | 17:30 | Mr. Koibuchi | C:\Users\Administrator>iisreset /stop Attempting stop... Internet services successfully stopped
|  |  | Backup database 10.1.1.37 | 17:30 | 17:40 | Mr. Koibuchi | QA20141217173145.zip
|  | Deploy application | build application for production environment on development server by build script | 18:50 | 18:52 | Mr. Koibuchi
|  |  | edit web.config | 18:52 | 18:55 | Mr. Koibuchi | <appSettings> <add key="Dsf.Lib.TraceLevel" value="Verbose" /> <add key="Dsf.Lib.LogPrefix" value="olss_prod" /> <add key="Dsf.Lib.LogRetentionDays" value="50" /> <add key="Dsf.Lib.LogSaveDir" value="D:\olss\log" /> </appSettings> ・・・ <sessionState mode="StateServer" timeout="1080" stateConnectionString="tcpip=127.0.0.1:42424"></sessionState>
|  |  | copy all application files to production server | 18:55 | 18:55 | Mr. Koibuchi
|  | Migration | Prepare migration database | 17:45 | 2:00 | Mr. Asep
|  |  | Backup development database | 3:00 | 3:00 |  | dev20141217173746.zip
|  |  | Restore backup file into production server | 3:00 | 3:00 | Mr. Koibuchi | olss_dev.bak --> olss_prod
|  |  | Take new database full backup | 3:00 | 3:00 | Mr. Koibuchi
|  | Test | Execute test | 3:00 | 3:30 | Dani, Siva
|  |  | Check logs | 3:30 | 3:30 | Mr. Koibuchi
|  |  | Restore database | 3:30 | 3:30 | Mr. Koibuchi
|  |  | Cleanup logs | 3:30 | 3:30 | Mr. Koibuchi
| Thursday, 18 December | Announcement | send announcement mail to users | 9:21 | 9:21 | Mr. Deny
|  |  | put SVN tag for latest revision | 12:00 | 12:00 | Mr. Koibuchi

## Sheet2
user config

## Data
olss on 10.1.1.37
Table | Rows
Customer | 34
CustomerBusinessSector | 0
CustomerDetailInfo | 69
Menu | 0
Product | 67
ProductBrand | 220
ProductCategory | 23
ProductModel | 3842
ProductType | 4
Role | 4
Supplier | 5306
SupplierCategory | 4
SupplierCorporateInfo | 0
SupplierGroup | 70
SupplierPaymentInfo | 0
sysdiagrams | 4
User | 14